## PHR WITH WIP & AR
|  | LiRo Financial Tracking Sheet: | [5 empty] | CM | [12 empty] | 2019-12-09
Project Info |  | Baseline Data | [6 empty] | Previous Pay Period Data |  |  |  | Current Pay Period Data | [5 empty] | Projected Financial Outcome
Project # | Project Name | Project Manager Name | (A) BU Min. Multiplier | (B) Project (Target) Multiplier | (C) Contract Value ($) | (D) Direct Labor Budget ($) (D = C/B) | (E) Planning Direct Labor Rate/Hr. ($) | (F) Planned Hours (Hrs) (F=D/E) | Previous Est. Comp. Date | Previous Estimated Hours to Complete | (G) Previous Total Hours Required (Prev. N) | (H) Total Hours Expended To Date (Hrs) | (I) Direct Labor Cost to Date ($) | (J) Current Average Direct Labor Rate ($/Hr) ( J = I/H) | (K) Current Estimated Hours to Complete (Hrs) (K = G-H) | (L) Estimated Cost to Complete in Dollars ($) (L = K*J) | (M) Current Project Level Estimated Completion Date | (N) Total Projected Hours (N = H+K) | (O) Percentage Completed (Hours) (O = H/N) | (P) Total Direct Labor to Completion ($) (P = N*J) | (Q) Projected Multiplier (Q = C/P) | (R) Direct Labor Variance ($) R=C(1/Min(A,B)-1/Q) | (Z) Last Pay Period Hours Charged
07-31-200B | NYCDOS Marine Transfer St LIRO-URS 50-50 | Blond, Lawrence | 2.04 | 0 | 7064982.5 | 0 | 0 | 0 | 2019-09-30 | 3.17 | 56429.69 | 56425.62 | 3091682.32 | 54.79 | -266.93 | -16000.84 | 2019-09-30 | 56158.69 | 100.48 | 3075681.25 | 2.3 | 391756.1 | 2
09-06-100B | PLA ANAYLSES FOR VARIOUS PROJECTS ASNEED | Hurley, Joseph | 2.04 | 2.57 | 89127.64 | 34680.02 | 40 | 867 |  | 622.2 | 559.8 | 97 | 8873.8 | 91.48 | 622.2 | 51999.01 |  | 719.2 | 13.49 | 60872.81 | 1.46 | -17202.44 | 14
10-58-515 | CUNY - Baruch College - Field Bld | Gaspari, James | 2.04 | 2.5 | 9897934 | 3959173.6 | 61 | 64907.85 | 2010-07-30 | 34824.24 | 73736.98 | 38912.74 | 2774762.65 | 71.31 | 32426.55 | 1642201.04 | 2010-07-30 | 71339.29 | 54.55 | 4417123.54 | 2.24 | 438762.82 | 276
11-68-0533 | Hudson River Park Trust Pier 40 Construc | Franco, Frank | 2.04 | 1.96 | 6363852.47 | 3246863.48 | 42.69 | 76049.43 | 2019-03-30 | 19580.88 | 74863.63 | 55282.75 | 2663240.1 | 48.17 | 16432.99 | 401406.39 | 2019-03-30 | 71715.74 | 77.09 | 3063713.56 | 2.08 | 182319.01 | 0
11-82-0265 | NYCDDC - MCC Theater Fit Outs | Franco, Frank | 2.04 | 1.35 | 1458138 | 1080102.22 | 48.73 | 22167.2 | 2019-04-01 | 3103.21 | 34189.21 | 31086 | 1546307.91 | 49.74 | 3103.21 | 145407.03 | 2019-04-01 | 34189.21 | 90.92 | 1691714.81 | 0.86 | -610194.6 | 15
12-147-0278.04 | NYCHA CCTV | Nazzaro, Dennis | 2.04 | 2 | 2696540.23 | 1348270.17 | 39.17 | 34422.46 | 2018-12-31 | 14173.83 | 35149.33 | 20975.5 | 834663.7 | 39.79 | 13490.55 | 515454.71 | 2018-12-31 | 34466.05 | 60.86 | 1350118.39 | 2 | -1815.55 | 0
12-147-0278.11 | NYCHA Exterior Lighting | Mo, Thomas | 2.04 | 2.1 | 1685020 | 802390.47 | 42.7 | 18791.6 | 2016-01-31 | 1008.19 | 20598.19 | 19590 | 835845.68 | 42.67 | 913.78 | 36640.35 | 2016-01-31 | 20503.78 | 95.54 | 872486.06 | 1.93 | -45930.36 | 0
13-011-0376 | SUCF New Medical and Research Bldg CM | Burke, Stephen | 2.04 | 1.85 | 9599999 | 5189188.64 | 59.89 | 86638.93 | 2019-06-01 | 41749.56 | 124144.48 | 82391.8 | 5410596.22 | 65.67 | 41664.53 | 2273883.35 | 2019-06-01 | 124056.33 | 66.41 | 7684479.41 | 1.25 | -2510380 | 269
13-017-0265 | NYCDDC PLA Study & Implementation Projec | Bendetti, Michael | 2.04 | 2.15 | 5000 | 2325.58 | 81.89 | 28.4 | 2013-03-31 | 8.4 | 28.4 | 20 | 1637.56 | 81.88 | 8.4 | 687.78 | 2013-03-31 | 28.4 | 70.42 | 2325.34 | 2.15 | 125.4 | 0
13-017-0265.04 | DDC- New Westchester Square Library | Hurley, Joseph | 2.04 | 2.2 | 18630.48 | 8468.4 | 84.54 | 100.17 | 2017-08-31 | 60.17 | 100.17 | 40 | 3381.4 | 84.54 | 60.17 | 5086.47 | 2017-08-31 | 100.17 | 39.93 | 8467.87 | 2.2 | 664.19 | 0
13-045-0248 | NCDPW Nassau Family & Matrimonial Court | Bendetti, Michael | 2.04 | 2.25 | 50000 | 22222.22 | 62.73 | 354.25 | 2013-07-03 | 0.03 | 701.03 | 701 | 43975.3 | 62.73 | 0.03 | 1.88 | 2013-07-03 | 701.03 | 100 | 43977.18 | 1.14 | -19349.85 | 0
13-050-0265 | NYCDDC Reno and Rehab West 59th CM | Bendetti, Michael | 2.04 | 1.95 | 5635778 | 2890142.56 | 64.96 | 44491.11 | 2016-04-01 | 32634.02 | 90274.98 | 57640.8 | 3462688.28 | 60.07 | 32584.18 | 2085241.92 | 2016-04-01 | 90224.98 | 63.89 | 5547930.26 | 1.02 | 43790.04 | 528.5
13-064-0113 | DASNY Term On-Call CM | Franco, Frank | 2.04 | 2.15 | 5174507.34 | 2412206.96 | 45.61 | 52891.86 | 2017-12-31 | 19648.51 | 65650.09 | 46001.5 | 2177953.71 | 47.35 | 15567.34 | 632453.31 | 2017-12-31 | 61568.84 | 74.72 | 2810480.12 | 1.84 | -127053.75 | 65
13-068-0113.09 | DASNY CCTV & LAC Analysis at NYCHA Locat | Mo, Thomas | 2.04 | 2.15 | 235063.5 | 109331.86 | 65.05 | 1680.73 | 2016-02-03 | 943.6 | 2073.1 | 1129.5 | 59883.5 | 53.02 | 551.23 | 49446.18 | 2016-02-03 | 1680.73 | 67.2 | 109329.68 | 2.15 | 5895.35 | 0
13-068-0113.10 | DASNY Conjunction Design & Security Svcs | Mo, Thomas | 2.04 | 2.15 | 1210135.8 | 562853.87 | 49.45 | 11383.32 | 2016-06-30 | 5436.13 | 14028.13 | 8592 | 428233.31 | 49.84 | 3464.32 | 164814.96 | 2016-06-30 | 12056.32 | 71.27 | 593224.2 | 2.04 | 28842.5 | 0
13-115-0090 | CUNY Macaulay Honors College Roof Top Re | Gaspari, James | 2.04 | 2 | 685359.94 | 342679.97 | 79.98 | 4284.38 | 2014-08-29 | 1020.91 | 4312.91 | 3292 | 262131.69 | 79.63 | 992.25 | 80050.64 | 2014-08-29 | 4284.25 | 76.84 | 342182.32 | 2 | 0 | 0
13-124-0113 | DASNY Energy Performance Design and CM | Ribeiro, Raymond | 2.04 | 2.27 | 828338 | 365104.05 | 41.5 | 8798.68 | 2020-03-31 | 455.02 | 5325.05 | 5169.75 | 260292.35 | 50.35 | 127.51 | 5088.81 | 2020-03-31 | 5297.26 | 97.59 | 265381.16 | 3.12 | 140547.17 | 147.75
13-142-0275 | NYCEDC On Call Facilities Management Con | Bradley, Daniel | 2.04 | 2.1 | 861014.32 | 410006.82 | 53.96 | 7597.86 | 2014-08-29 | 0.04 | 8362.54 | 8362.5 | 453630.67 | 54.25 | -340.87 | -18637.63 | 2014-08-29 | 8021.63 | 104.25 | 434993.01 | 1.98 | -13446.05 | 2.5
14-012-0282.Q | NYCSCA Emergency Program 2013 Queens | Radafshar, Bijan | 2.04 | 0 | 0 | 0 | 0 | 0 | 2016-01-16 | 0 | 135 | 135 | 5681.87 | 42.09 | -135 | -5681.87 | 2016-01-16 | 0 | 0 | 0 | 0 | 0 | 0
14-058-0286.06 | NYPA Cumberland HPS Boiler Replacement | Ribeiro, Raymond | 2.04 | 2.2 | 181094 | 82315.46 | 74.66 | 1102.47 | 2018-01-01 | 218.11 | 1536.61 | 1318.5 | 97837.71 | 74.2 | 218.11 | 16437.37 | 2018-01-01 | 1536.61 | 85.81 | 114275.07 | 1.58 | -25518.68 | 0
14-058-0286.07 | NYPA Lincoln Hospital - HVAC Upgrade | Ribeiro, Raymond | 2.04 | 2.59 | 1476098 | 570076.79 | 44.78 | 12731.79 | 2018-12-31 | 6409.63 | 8738 | 7031.43 | 369569.89 | 52.56 | 6222.56 | 387842.95 | 2018-12-31 | 13253.99 | 53.05 | 757412.84 | 1.95 | -4063.06 | 142
14-058-0286.08 | NYPA CUNY Boiler Repair Services-ASRC | Ribeiro, Raymond | 2.04 | 2.2 | 106400 | 48363.63 | 49.96 | 968.08 | 2018-01-01 | 890.08 | 968.08 | 78 | 6389.38 | 81.92 | 890.08 | 41665.39 | 2018-01-01 | 968.08 | 8.06 | 48054.77 | 2.21 | 4124.39 | 0
14-058-0286.09 | NYPA Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.2 | 50000 | 22727.27 | 40 | 568.18 | 2018-06-01 | 550.68 | 568.18 | 17.5 | -25388.4 | -1450.77 | 550.68 | 22027.2 | 2018-06-01 | 568.18 | 3.08 | 22727.2 | 2.2 | 1782.53 | 0
14-058-0286.10 | NYPA Lincoln Hospital - Cooling Tower | Ribeiro, Raymond | 2.04 | 2.2 | 619920 | 281781.81 | 71.41 | 3945.8 | 2018-01-01 | 569.95 | 3936.95 | 3367 | 241123.24 | 71.61 | 569.95 | 40587.83 | 2018-01-01 | 3936.95 | 85.52 | 281711.06 | 2.2 | 22100.53 | 27
14-058-0286.11 | NYPA Grand Ave. Bus Depot Gen Upgrade | Ribeiro, Raymond | 2.04 | 2.4 | 220000 | 91515.15 | 40 | 2287.87 |  | 473.19 | 805.51 | 731.5 | 45246.62 | 61.85 | 473.19 | 32285.82 |  | 1204.69 | 60.72 | 77854.9 | 2.83 | 29934.58 | 0
14-058-0286.12 | NYPA Fresh Pond Bus Depot-HVAC Upgrade | Ribeiro, Raymond | 2.04 | 2.51 | 1230197 | 489376.7 | 43.04 | 11371.42 | 2018-01-01 | 6668.78 | 11117.71 | 4594.75 | 229993.25 | 50.06 | 6614.96 | 267669.92 | 2018-01-01 | 11209.71 | 40.99 | 497663.17 | 2.47 | 108512.87 | 19.5
14-058-0286.13 | NYPA CUNY Boiler Repairs- Queens College | Ribeiro, Raymond | 2.04 | 2.2 | 114500 | 52045.45 | 82.19 | 633.2 | 2018-01-01 | 278.04 | 847.04 | 569 | 46541.92 | 81.8 | 278.04 | 21765.47 | 2018-01-01 | 847.04 | 67.18 | 68307.39 | 1.68 | -12296.16 | 0
14-058-0286.14 | NYPA Bronx Community College Utility | Gaspari, James | 2.04 | 2.27 | 2483769.89 | 1096048.51 | 42.48 | 25802.94 | 2022-07-01 | 2696.85 | 7201.51 | 6390.5 | 338965.69 | 53.04 | 2696.86 | 135836.93 | 2022-07-01 | 9087.36 | 70.32 | 474802.63 | 5.23 | 742607.55 | 184.75
14-058-0286.17 | NYPA CUNY Boiler Repairs- Hunter College | Ribeiro, Raymond | 2.04 | 2.1 | 13200 | 6285.71 | 84.24 | 74.62 | 2018-12-31 | 27.13 | 79.13 | 52 | 4130.98 | 79.44 | 27.13 | 2155.26 | 2018-12-31 | 79.13 | 65.71 | 6286.24 | 2.1 | 184.87 | 0
14-058-0286.18 | NYPA CUNY Boiler Repairs- Voohies Hall C | Ribeiro, Raymond | 2.04 | 2.1 | 14000 | 6666.67 | 84.24 | 79.14 | 2018-12-31 | 45.14 | 79.14 | 34 | 2864.16 | 84.24 | 45.14 | 3802.59 | 2018-12-31 | 79.14 | 42.96 | 6666.75 | 2.1 | 196.08 | 0
14-058-0286.19 | NYPA CUNY Boiler Repairs- Bklyn College | Ribeiro, Raymond | 2.04 | 2.1 | 51020 | 24295.24 | 46.78 | 519.4 | 2018-12-31 | 477.6 | 513.6 | 36 | 2833.04 | 78.7 | 477.6 | 21461.72 | 2018-12-31 | 513.6 | 7.01 | 24294.76 | 2.1 | 714.57 | 0
14-058-0286.21 | NYPA CUNY Bronx CC Piping Upgrade | White, William | 2.04 | 2.1 | 196658 | 93646.67 | 73.22 | 1278.98 | 2019-08-01 | 252.94 | 2012.5 | 2012.5 | 130425.46 | 64.81 | -733.52 | -47537.73 | 2019-08-01 | 1278.98 | 157.35 | 82887.73 | 2.37 | 13422.92 | 20
14-059-0113 | DASNY Hostos Community College WR | Ribeiro, Raymond | 2.04 | 2.14 | 235817 | 109998.29 | 64.87 | 1695.66 | 2019-11-15 | 619.24 | 1955.51 | 1376.25 | 87102.09 | 63.29 | 579.26 | 43056.37 | 2019-11-15 | 1955.51 | 70.38 | 130158.45 | 1.81 | -14625.62 | 46.5
14-059-0113.01 | DASNY JV Hostos CC Variable Freq. Drives | Barbosa, Marco | 2.04 | 2.1 | 346746 | 165117.14 | 56.48 | 2923.25 | 2015-10-31 | 615.87 | 2326.36 | 2306 | 140110.93 | 60.76 | 615.87 | 26088.66 | 2015-10-31 | 2921.87 | 78.92 | 166199.6 | 2.09 | 3782.19 | 0
14-059-0113.02 | DASNY York College BMS Upgrade | Ribeiro, Raymond | 2.04 | 2.54 | 402878.54 | 158613.6 | 48.24 | 3288.27 | 2018-12-30 | 566.82 | 2676.01 | 2676 | 130491.28 | 48.76 | 566.82 | 30064.7 | 2018-12-30 | 3242.82 | 82.52 | 160555.97 | 2.51 | 36956.24 | 0
14-088-0290.01 | NYSPRHP Upper Plaza Term Contract 2014 | Franco, Frank | 2.04 | 2.12 | 96342.13 | 45444.4 | 40 | 1136.11 | 2018-12-30 | 1136.11 | 1136.11 | 0 | 0 | 0 | 1136.11 | 45444.4 | 2018-12-30 | 1136.11 | 0 | 45444.4 | 2.12 | 1782.13 | 0
14-088-0290.14 | NYSPRHP RCSP - Electrical Upgrade | Franco, Frank | 2.04 | 2.1 | 130520 | 62152.38 | 55.42 | 1121.46 | 2019-09-01 | 537.48 | 2500.76 | 1963.25 | 123379.83 | 62.84 | 537.51 | 26574.4 | 2019-09-01 | 2500.76 | 78.51 | 149954.24 | 0.87 | -85309.09 | 95.5
14-088-0290.15 | NYSPRHP E. River State Park Classroom Bl | Franco, Frank | 2.04 | 2.1 | 30000 | 14285.71 | 69.98 | 204.14 | 2019-09-01 | 43.26 | 43.26 | 0 | -79.45 | 0 | 43.26 | 3027.33 | 2019-09-01 | 43.26 | 0 | 3027.33 | 9.91 | 11678.64 | 0
14-094-0275 | NYCEDC Box Street Newtown Barge Parks CM | Bradley, Daniel | 2.04 | 2.4 | 2600190.8 | 1083412.83 | 62.06 | 17457.41 | 2019-12-31 | 5144.28 | 24007.53 | 18863.25 | 1025678.48 | 54.37 | 3798.63 | 252992.95 | 2019-12-31 | 22661.88 | 83.24 | 1278671.45 | 2.03 | 143573.42 | 8
14-121-0090 | CUNY Brooklyn College Ingersoll Hall Ext | Gaspari, James | 2.04 | 2.15 | 3389527.87 | 1576524.59 | 70.27 | 22435.75 | 2017-07-13 | 2736.75 | 19962.75 | 17226 | 1260230.6 | 73.16 | 2674.63 | 159363.11 | 2017-07-13 | 19900.63 | 86.56 | 1419593.77 | 2.39 | 241987.46 | 188.5
15-016-0276 | FDNY CM Services | Blond, Lawrence | 2.04 | 2.1 | 7564504 | 3602144.85 | 51.84 | 69486.31 | 2018-08-01 | 8406.65 | 71252.9 | 62848.75 | 3290620.32 | 52.36 | 8017.73 | 384039.66 | 2018-08-01 | 70866.48 | 88.69 | 3674659.99 | 2.06 | 33319.19 | 0
15-034-0113 | DASNY OMH South Beach Psychiatric | Barbosa, Marco | 2.04 | 2.1 | 2404751.89 | 1145119.95 | 41.04 | 27902.6 | 2015-10-31 | 1727.57 | 9596.01 | 8531.1 | 438212.41 | 51.37 | 1726.44 | 70224.61 | 2015-10-31 | 10257.54 | 83.17 | 508437.04 | 4.73 | 670288.64 | 154.25
15-035-0278 | NYCHA Ingersoll Houses | Nazzaro, Dennis | 2.04 | 2 | 3078197 | 1539098.5 | 40 | 38477.47 | 2017-03-11 | 38477.47 | 38477.47 | 0 | 0 | 0 | 38477.47 | 1539098.8 | 2017-03-11 | 38477.47 | 0 | 1539098.8 | 2 | 0 | 0
15-036-0278 | NYCHA Whitman Houses | Choudhury, Faisal | 2.04 | 2.1 | 2428126 | 1156250.47 | 49.62 | 23302.21 | 2017-03-11 | 8205.72 | 34315.47 | 26109.75 | 1296496.32 | 49.66 | 8205.72 | 405043.33 | 2017-03-11 | 34315.47 | 76.09 | 1701539.75 | 1.43 | -374623.4 | -4813.75
15-049-0265 | NYCDDC Hurricane Sandy-Affected Resident | Pavlakos, Giannoula | 2.05 | 3.75 | 49976066 | 13326950.93 | 54.07 | 246475.88 | 2020-04-28 | 188921.56 | 381727.86 | 192803.15 | 10071913.93 | 52.24 | 123631.11 | 6923419.65 | 2020-04-28 | 316434.26 | 60.93 | 16995333.42 | 2.94 | 11027433.83 | 907
15-049-0265.01 | NYCDDC Hurricane Sandy-Affected | Pavlakos, Giannoula | 2.04 | 3 | 398217 | 132739 | 57.05 | 2326.74 | 2017-08-31 | 732.76 | 25205.27 | 24492.95 | 1174584.64 | 47.96 | -12101.22 | -576855.28 | 2017-08-31 | 12391.73 | 197.66 | 597729.35 | 0.67 | 60550.27 | 22.5
15-092-0282.Q | NYCSCA Emergency Program 2015 Queens | Radafshar, Bijan | 2.04 | 2.4 | 29970.34 | 12487.64 | 46.72 | 267.29 | 2017-07-23 | 0 | 394.5 | 394.5 | 18431.24 | 46.72 | -127.21 | -5943.32 | 2017-07-23 | 267.29 | 147.59 | 12487.93 | 2.4 | 2203.7 | 0
15-116-0278 | NYCHA CM Sandy Recovery at Red Hook E&W | Nazzaro, Dennis | 2.04 | 2 | 12714236 | 6357118.04 | 46.83 | 135745.09 | 2018-03-30 | 95018.85 | 136893.3 | 47144.75 | 2255930.8 | 47.85 | 94577.38 | 4321406.89 | 2018-03-30 | 141722.13 | 33.27 | 6577337.66 | 1.93 | -199117.33 | 882
15-121-0278.04 | NYCHA Roofing Restoration/Rooftop Repair | Wong, David | 2.04 | 2.2 | 72354 | 32888.19 | 76.26 | 431.26 | 2020-03-01 | 6 | 560.5 | 554.5 | 42745.2 | 77.09 | -117.24 | -9617.72 | 2020-03-01 | 437.26 | 126.81 | 33127.49 | 2.18 | 2579.46 | 0
15-121-0278.05 | NYCHA Melrose Houses Roofing Restoration | Wong, David | 2.04 | 2.2 | 931896.79 | 423589.45 | 45.35 | 9340.62 | 2020-07-10 | 4321.13 | 11500.43 | 7179.3 | 335747.06 | 46.77 | 3669.9 | 186063.95 | 2020-07-10 | 10849.2 | 66.17 | 521811 | 1.79 | -65922.28 | 430
15-121-0278.06 | NYCHA Webster Houses Roofing Restoration | Wong, David | 2.04 | 2.2 | 634580.08 | 288445.49 | 40 | 7211.14 | 2020-07-10 | 3755.56 | 7996.56 | 4241 | 198593.82 | 46.83 | 3755.56 | 184903.99 | 2020-07-10 | 7996.56 | 53.04 | 383497.82 | 1.65 | -72451.71 | 335
15-121-0278.07 | NYCHA Eastchester Houses Roofing Restor | Wong, David | 2.04 | 2.2 | 1079068.02 | 490485.47 | 40 | 12262.13 | 2020-07-10 | 8132.9 | 12953.9 | 4821 | 217982.48 | 45.22 | 8132.9 | 369616.23 | 2020-07-10 | 12953.9 | 37.22 | 587598.69 | 1.84 | -59814.81 | 456
16-018-0271 | NYCDOS On-Call Services Reno & Rehab | Caggiano, Anthony | 2.04 | 2.1 | 5275045.6 | 2511926.48 | 53.13 | 47283.09 | 2019-01-06 | 37295.18 | 71177.69 | 34028.25 | 1911370.83 | 56.17 | 35976.42 | 1956836.24 | 2019-01-06 | 70004.67 | 48.61 | 3868207.11 | 1.36 | -1131421.72 | 195.5
16-024-0090.01 | CUNY On Call Lehman College Labs Rounds | Fitzpatrick, Lawrence | 2.04 | 2.3 | 634432 | 275840 | 46.04 | 5991.55 | 2019-05-31 | 346.55 | 6824.19 | 6824 | 315239.71 | 46.2 | 97.3 | 4151.44 | 2019-05-31 | 6921.3 | 98.59 | 319391.14 | 1.99 | -8081.46 | 7
16-025-1256.10 | HTFC APMS MCM - Construction Management | Massa, Joseph | 2.04 | 2.38 | 6782871.48 | 2849946 | 40 | 71248.65 | 2020-03-31 | 11472.79 | 61774.54 | 50301.75 | 2883579.88 | 57.33 | 11472.79 | 616305.16 | 2020-03-31 | 61774.54 | 81.43 | 3499885.18 | 1.94 | -167229.36 | 424
16-052-0290.02 | NYSDPR Penn Fountain Park | Franco, Frank | 2.04 | 2.2 | 127051.27 | 57750.58 | 74.15 | 778.83 | 2019-12-31 | 0.03 | 848.53 | 848.5 | 62689.43 | 73.88 | 0.03 | 2.22 | 2019-12-31 | 848.53 | 100 | 62691.65 | 2.03 | -306.8 | 0
16-069-0278.01 | NYCHA CM Svcs Lincoln Houses Minor Elect | Nazzaro, Dennis | 2.04 | 2.2 | 451510.59 | 205232.09 | 40.85 | 5024.06 | 2018-12-30 | 4883.85 | 5151.35 | 267.5 | 19034.77 | 71.16 | 4756.56 | 186321.15 | 2018-12-30 | 5024.06 | 5.32 | 205355.92 | 2.2 | 15981.1 | 0
16-069-0278.02 | NYCHA Playgrounds CM Svcs | Nazzaro, Dennis | 2.04 | 2.1 | 49219.6 | 23437.9 | 40 | 585.94 |  | 383.44 | 299.71 | 202.5 | 7201.47 | 35.56 | 336.94 | 12242.2 |  | 539.44 | 37.54 | 19443.67 | 2.53 | 4658.19 | 46.5
16-076-0270.02 | NYCPR Tiffany St. Pier Special Inspec | Reo, Jennifer | 2.04 | 2.1 | 620 | 295.24 | 75.51 | 3.91 | 2019-01-18 | 1.91 | 7 | 7 | 547.97 | 78.28 | -3.09 | -241.89 | 2019-01-18 | 3.91 | 179.03 | 306.08 | 2.03 | -1.5 | 0
16-076-0270.04 | NYCPR Brookville Park Spec Insp-Tennis | Reo, Jennifer | 2.04 | 2.1 | 620 | 295.24 | 76.69 | 3.85 | 2019-01-18 | 0 | 27 | 27 | 2069.04 | 76.63 | -23.15 | -1774.01 | 2019-01-18 | 3.85 | 701.3 | 295.03 | 2.1 | 8.68 | 0
16-076-0270.11 | NYCPR - NYS Pavillion - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 21600 | 10285.71 | 76.93 | 133.7 | 2019-11-12 | 131.95 | 134.2 | 2.25 | 174.18 | 77.41 | 131.95 | 10214.69 | 2019-11-12 | 134.2 | 1.68 | 10388.87 | 2.08 | 203.62 | 0
16-076-0270.12 | NYCPR - Shore Rd Fld Hs - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 13500 | 6428.57 | 76.93 | 83.56 | 2019-11-12 | 51.81 | 87.81 | 36 | 2829.46 | 78.6 | 51.81 | 4072.06 | 2019-11-12 | 87.81 | 41 | 6901.52 | 1.96 | -270.11 | 2.75
16-076-0270.13 | NYCPR - West Plgd CS - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 18000 | 8571.43 | 76.93 | 111.42 | 2019-11-12 | 103.17 | 111.42 | 8.25 | 640.12 | 77.59 | 103.17 | 8004.99 | 2019-11-12 | 111.42 | 7.4 | 8645.11 | 2.08 | 169.68 | 0
16-076-0270.14 | NYCPR - Brownsville Rec Ctr - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 12500 | 5952.38 | 76.93 | 77.37 | 2019-11-12 | 67.62 | 78.37 | 10.75 | 841.71 | 78.3 | 67.62 | 5294.55 | 2019-11-12 | 78.37 | 13.72 | 6136.26 | 2.04 | 0 | 5.75
16-076-0270.15 | NYCPR - Marine Pk Plgd - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 9000 | 4285.71 | 76.93 | 55.71 | 2019-11-12 | 21.21 | 62.46 | 41.25 | 3239.88 | 78.54 | 21.21 | 1665.89 | 2019-11-12 | 62.46 | 66.04 | 4905.77 | 1.83 | -506.27 | 0
16-076-0270.16 | NYCPR - Canarsie CS - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 13500 | 6428.57 | 76.93 | 83.56 | 2019-11-12 | 77.31 | 83.81 | 6.5 | 500.58 | 77.01 | 77.31 | 5953.82 | 2019-11-12 | 83.81 | 7.76 | 6454.4 | 2.09 | 158.32 | 0
16-076-0270.17 | NYCPR - Reconstruct Bloomingdale Plgd | Choudhury, Faisal | 2.04 | 2.1 | 317400 | 151142.86 | 44.1 | 3427.28 | 2020-01-15 | 1108.27 | 3804.02 | 2695.75 | 132053.24 | 48.99 | 1108.27 | 54289.39 | 2020-01-15 | 3804.02 | 70.87 | 186342.62 | 1.7 | -31117.65 | 77
16-076-0270.18 | NYCPR - Reconstruct Garrison Plgd | Choudhury, Faisal | 2.04 | 2.1 | 446200 | 212476.19 | 46 | 4619.05 | 2020-01-15 | 2861 | 5130 | 2269 | 104524.4 | 46.07 | 2861 | 131795.63 | 2020-01-15 | 5130 | 44.23 | 236320.02 | 1.89 | -17359.17 | 87
16-076-0270.19 | NYCPR - CM Svcs St Mary's Greenstreets | Choudhury, Faisal | 2.04 | 2.1 | 134132 | 63872.38 | 51.96 | 1229.26 | 2019-11-01 | 732.89 | 1742.89 | 1010 | 46992.83 | 46.53 | 732.89 | 34099.58 | 2019-11-01 | 1742.89 | 57.95 | 81092.4 | 1.65 | -15541.14 | 6
16-080-0270.01 | NYCPR Reconstruct New Comfort Stations | Massa, Joseph | 2.04 | 2.05 | 2695321 | 1314790.72 | 55.01 | 23901.76 | 2019-01-18 | 1643.58 | 23150.34 | 22275.25 | 1238732.55 | 55.61 | 740.66 | 54494.24 | 2019-01-18 | 23015.91 | 96.78 | 1293226.82 | 2.08 | 27228.39 | 160
16-080-0270.13 | NYCPR Lincoln Terrace Park Special Insp | Reo, Jennifer | 2.04 | 2.1 | 25200 | 12000 | 76.15 | 157.58 | 2019-11-16 | 138.58 | 159.58 | 21 | 1632.92 | 77.76 | 138.58 | 10775.72 | 2019-11-16 | 159.58 | 13.16 | 12408.64 | 2.03 | -60.85 | 1
16-080-0270.14 | NYCPR CM Svcs for St. Mary's Ballfields | Choudhury, Faisal | 2.04 | 2.1 | 358000 | 170476.19 | 40.68 | 4190.66 | 2020-04-01 | 2907.71 | 4789.21 | 1881.5 | 92038.98 | 48.92 | 2907.71 | 142238.98 | 2020-04-01 | 4789.21 | 39.29 | 234277.95 | 1.53 | -58496.73 | 82
16-080-0270.15 | NYCPR Recon of Elizabeth H. Berger Plaza | Choudhury, Faisal | 2.04 | 2.2 | 325600 | 148000 | 40 | 3700 |  | 2912 | 788 | 788 | 33096 | 42 | 2832 | 118944 |  | 3620 | 21.77 | 152040 | 2.14 | 7458.31 | 80
16-342-0275.01 | EDC Estimating Svcs Willoughby Square Pk | Frysztacki, Edward | 2.04 | 2.3 | 19000 | 8260.87 | 68.97 | 119.77 |  | 6.78 | 124.78 | 118 | 8247.4 | 69.89 | 6.78 | 473.88 |  | 124.78 | 94.57 | 8721.28 | 2.18 | 598.13 | 0
16-379-0275 | NYCEDC NYPD JFK Site A - Closeout | Reo, Jennifer | 2.04 | 2 | 223104 | 111552 | 52.31 | 2132.4 | 2019-06-30 | 252.91 | 2025.92 | 1827.5 | 108096.41 | 59.15 | 252.92 | 13883.24 | 2019-06-30 | 2080.42 | 87.84 | 121979.66 | 1.83 | -10457.38 | 18
17-040-0286.01 | NYPA VNB Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 5120613 | 1862041.09 | 110.07 | 16916.88 | 2018-07-01 | 16368.31 | 22429.31 | 6061 | 487169.78 | 80.38 | 12096.81 | 1210469.82 | 2018-07-01 | 18157.81 | 33.38 | 1697639.6 | 3.02 | 904896.57 | 9
17-040-0286.02 | NYPA RFK Queens Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 1804774 | 656281.45 | 42.11 | 15584.93 | 2018-07-01 | 14814.77 | 21614.52 | 6799.75 | 375567.63 | 55.23 | 14493.77 | 654796.28 | 2018-07-01 | 21293.52 | 31.93 | 1030363.88 | 1.75 | 185168.33 | 0
17-040-0286.03 | NYPA RFK Harlem Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 1175397 | 427417.09 | 44.51 | 9602.72 | 2018-07-01 | 9091.77 | 14824.52 | 5733.75 | 315051.01 | 54.95 | 5176.52 | 158743.25 | 2018-07-01 | 10910.27 | 52.55 | 473794.24 | 2.48 | 163755 | 0
17-040-0286.04 | NYPA RFK Bronx Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 645525 | 234736.36 | 41.24 | 5691.96 | 2018-07-01 | 5105.52 | 10629.77 | 5524.25 | 306125.78 | 55.41 | 167.77 | -72545.49 | 2018-07-01 | 5692.02 | 97.05 | 233580.29 | 2.76 | 82547.95 | 0
17-040-0286.06 | NYPA TNB Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 2287790 | 831923.64 | 57.69 | 14420.59 | 2018-07-01 | 13981.29 | 18843.04 | 4861.75 | 305255.82 | 62.79 | 9381.04 | 591166.89 | 2018-07-01 | 14242.79 | 34.13 | 896422.69 | 2.55 | 224293.14 | 0
17-078-1387 | Breaking Ground Prince George Rehab | Ribeiro, Raymond | 2.04 | 1 | 856268 | 856268 | 57.19 | 14972.34 | 2017-12-31 | 4645.23 | 11408.73 | 6763.5 | 387788.48 | 57.34 | 4645.23 | 266336.45 | 2017-12-31 | 11408.73 | 59.28 | 654124.9 | 1.31 | 202628.31 | 0
17-078-1387.02 | Breaking Ground-Prince George Sidewalk | Ribeiro, Raymond | 2.04 | 2.5 | 60000 | 24000 | 40 | 600 |  | 23 | 577 | 577 | 34981.49 | 60.63 | 23 | 1394.41 |  | 600 | 96.17 | 36375.9 | 1.65 | -6951.87 | 0
17-078-1387.03 | Breaking Ground-Prince George Fire Pump | Ribeiro, Raymond | 2.04 | 2.1 | 15000 | 7142.86 | 40 | 178.57 |  | 115.57 | 63 | 63 | 5715.36 | 90.72 | 115.57 | 10484.51 |  | 178.57 | 35.28 | 16199.87 | 0.93 | -8776.09 | 0
17-080-0282 | SCA Mentor Program-Administration | Fotopoulos, Georgia | 2.04 | 1.73 | 8949174 | 5172932.95 | 45.29 | 114217.99 | 2019-06-02 | 0 | 39451.23 | 39448.2 | 1735065.06 | 43.98 | 3.03 | 133.27 | 2019-06-02 | 39451.23 | 99.99 | 1735198.44 | 5.16 | 3438596.9 | 580.7
17-080-0282.M | SCA Mentor Program-MANHATTAN | Fotopoulos, Georgia | 2.04 | 1.73 | 989078.58 | 571721.72 | 40.24 | 14207.09 | 2019-06-02 | 8682.26 | 13341.63 | 7143 | 291597.02 | 40.82 | 8094.54 | 328580.83 | 2019-06-02 | 15237.54 | 46.88 | 620177.84 | 1.59 | -48719.81 | 333
17-080-0282.X | SCA Mentor Program-BRONX | Fotopoulos, Georgia | 2.04 | 1.73 | 1197536.82 | 692217.82 | 41.67 | 16613.87 | 2019-06-02 | 9093.37 | 12175.72 | 7055 | 302799.69 | 42.92 | 7985.1 | 332562.69 | 2019-06-02 | 15040.1 | 46.91 | 635362.36 | 1.88 | 56734.57 | 278
17-082-0290 | OPRHP-Jones Beach State Park | Franco, Frank | 2.04 | 2.07 | 967137 | 467215.94 | 63.67 | 7338.09 | 2018-09-30 | 192.84 | 7383.09 | 7190.25 | 459832.29 | 63.95 | 192.84 | 12332.54 | 2018-09-30 | 7383.09 | 97.39 | 472164.85 | 2.05 | 2312.62 | 0
17-082-0290.01 | OPRHP Jones Beach Basketball Courts | Franco, Frank | 2.04 | 2.07 | 235134 | 113591.3 | 105.2 | 1079.81 | 2019-10-01 | 1465.52 | 2686.52 | 1221 | 63225.98 | 51.78 | 1465.52 | 74087.67 | 2019-10-01 | 2686.52 | 45.45 | 137313.65 | 1.71 | -21722.29 | 3
17-082-0290.02 | OPRHP - Jones Beach Central Mall | Franco, Frank | 2.04 | 2.07 | 257010 | 124159.42 | 40 | 3103.99 |  | 0.03 | 305.78 | 305.75 | 15912.66 | 52.04 | 0.03 | 1.56 |  | 305.78 | 99.99 | 15914.22 | 16.15 | 110071.36 | 0
17-086-0265 | NYCDDC Disaster Recovery: On-Call | Aidikoff, Brant | 2.04 | 2 | 200000 | 100000 | 61.18 | 1634.64 | 2019-06-08 | 716.15 | 535.01 | 132.5 | 12852.98 | 97 | 716.15 | 52603.91 | 2019-06-08 | 848.65 | 15.61 | 65456.89 | 3.06 | 34425.18 | 0
17-095-0407.01 | Town of Babylon Gilgo Potable Water | Ribeiro, Raymond | 2.04 | 2.5 | 21225 | 8490 | 79.07 | 107.37 | 2019-09-01 | 220.73 | 397.33 | 194.6 | 16182.43 | 83.16 | 69.82 | -3085.77 | 2019-09-01 | 264.42 | 73.6 | 13096.67 | 1.62 | -2708.28 | 0
17-095-0407.02 | Town of Babylon America Venice Bridges | Ribeiro, Raymond | 2.04 | 2.5 | 274862.2 | 109944.88 | 90.92 | 1209.29 | 2019-09-01 | 1134.1 | 2272.28 | 1229.7 | 105878.5 | 86.1 | 1012.61 | 53882.27 | 2019-09-01 | 2242.31 | 54.84 | 159760.77 | 1.72 | -14205.86 | 46
17-095-0407.03 | Town of Babylon Captree Emerg Generators | Ribeiro, Raymond | 2.04 | 2.5 | 40791.38 | 16316.55 | 85.37 | 191.12 | 2019-09-01 | 204.16 | 444.36 | 240.2 | 20898.73 | 87.01 | 204.16 | 11180.72 | 2019-09-01 | 444.36 | 54.06 | 32079.44 | 1.27 | -12014.08 | 0
17-095-0407.04 | Town of Babylon Carls River Watershed | Ribeiro, Raymond | 2.04 | 2.5 | 258104 | 103241.6 | 46.02 | 2243.42 | 2019-09-01 | 1653.52 | 1930.22 | 276.7 | 23787.03 | 85.97 | 1653.52 | 81686.57 | 2019-09-01 | 1930.22 | 14.34 | 105473.6 | 2.45 | 20931.56 | 0
17-095-0407.05 | Town of Babylon Amityville Waterfront | Ribeiro, Raymond | 2.04 | 2.5 | 118781.09 | 47512.44 | 82.55 | 575.55 | 2019-09-01 | 492.76 | 1092.56 | 599.8 | 49946.49 | 83.27 | 457.81 | 24617.34 | 2019-09-01 | 1057.61 | 56.71 | 74563.83 | 1.59 | -9782.44 | 8
17-095-0407.06 | Town of Babylon-Babylon Coastal Outfall | Ribeiro, Raymond | 2.04 | 2.5 | 94325 | 37730 | 49.27 | 765.85 | 2019-09-01 | 422.79 | 646.79 | 224 | 16643 | 74.3 | 400.83 | 17044.56 | 2019-09-01 | 624.83 | 35.85 | 33687.56 | 2.8 | 12574.16 | 0
17-095-0407.07 | Town of Babylon Captree Road Stabilizati | Ribeiro, Raymond | 2.04 | 2.5 | 80737 | 32294.8 | 50.54 | 639.05 | 2019-09-01 | 543.01 | 658.46 | 115.45 | 9826.48 | 85.11 | 537.66 | 23675.94 | 2019-09-01 | 653.11 | 17.68 | 33502.41 | 2.41 | 6083.08 | 0
17-095-0407.08 | Town of Babylon Oakbeach Stabilization | Ribeiro, Raymond | 2.04 | 2.5 | 80700 | 32280 | 54.35 | 593.92 | 2019-09-01 | 495.9 | 605.35 | 109.45 | 9459.99 | 86.43 | 495.9 | 24177.05 | 2019-09-01 | 605.35 | 18.08 | 33637.04 | 2.4 | 5908.02 | 0
17-095-0407.09 | Town of Babylon Araca Stabilization | Ribeiro, Raymond | 2.04 | 2.5 | 80700 | 32280 | 51.32 | 629 | 2019-09-01 | 480.95 | 695.4 | 214.45 | 18864.49 | 87.97 | 463.76 | 36500.99 | 2019-09-01 | 678.21 | 31.62 | 55365.48 | 1.46 | -15761.15 | 0
17-095-0407.10 | Town of Babylon Little East Neck Road | Ribeiro, Raymond | 2.04 | 2.5 | 23767.48 | 9506.99 | 53.36 | 178.18 | 2019-09-01 | 254.09 | 380.89 | 126.8 | 10891.77 | 85.9 | 241.08 | 20143.54 | 2019-09-01 | 367.88 | 34.47 | 31035.3 | 0.77 | -19386.45 | 0
17-120-0113.01 | DASNY Security Enhancement Project NYCHA | Mo, Thomas | 2.04 | 2.1 | 789344 | 375878.11 | 47.19 | 7965.03 | 2018-06-30 | 1855.6 | 5549.6 | 3694 | 177887.05 | 48.16 | 1855.6 | 85069.79 | 2018-06-30 | 5549.6 | 66.56 | 262956.84 | 3 | 123881.31 | 0
17-120-0113.02 | DASNY Site Lighting Replacement Project | Mo, Thomas | 2.04 | 2.1 | 519206.91 | 247241.38 | 52.12 | 4743.52 | 2018-12-31 | 1616.17 | 5117.42 | 3501.25 | 183865.08 | 52.51 | 1616.17 | 79255.23 | 2018-12-31 | 5117.42 | 68.42 | 263120.3 | 1.97 | -8664.23 | 0
17-120-0113.03 | DASNY Security Projects at Various NYCHA | Mo, Thomas | 2.04 | 2.1 | 44474.33 | 21178.22 | 40 | 529.46 | 2018-12-31 | 529.46 | 529.46 | 0 | 0 | 0 | 529.46 | 21178.4 | 2018-12-31 | 529.46 | 0 | 21178.4 | 2.1 | 622.92 | 0
17-120-0113.05 | DASNY BMCC - Feeder Project | Franco, Frank | 2.04 | 2.1 | 170811.68 | 81338.9 | 82.34 | 987.84 | 2019-11-09 | 540.84 | 996.84 | 456 | 37547.04 | 82.34 | 540.84 | 44532.77 | 2019-11-09 | 996.84 | 45.74 | 82079.81 | 2.08 | 1610.22 | 0
17-120-0113.08 | DASNY BMCC - Generator Project | Franco, Frank | 2.04 | 2.1 | 293956.47 | 139979.27 | 81.34 | 1720.92 | 2019-11-09 | 301.98 | 2047.48 | 1745.5 | 145339.09 | 83.27 | 301.98 | 25144.37 | 2019-11-09 | 2047.48 | 85.25 | 170483.46 | 1.72 | -26808.62 | 16
17-120-0113.09 | DASNY BMCC - GYM AHU | Franco, Frank | 2.04 | 2.1 | 172538.05 | 82160.98 | 81.87 | 1003.55 | 2019-11-09 | 307.2 | 1072.2 | 765 | 62722.74 | 81.99 | 307.2 | 25187.48 | 2019-11-09 | 1072.2 | 71.35 | 87910.22 | 1.96 | -3452.14 | 0
17-120-0113.10 | DASNY Minnewaska State Park Phase 1 | Franco, Frank | 2.04 | 2.1 | 1804604 | 859335.24 | 59.62 | 14413.54 | 2019-11-09 | 153.82 | 4850.13 | 4850 | 293384.19 | 60.49 | 0.13 | 7.86 | 2019-11-09 | 4850.13 | 100 | 293392.08 | 6.15 | 591178.26 | 253.5
17-120-0113.12 | DASNY- NYCHA Quality of Life | Mo, Thomas | 2.04 | 2.1 | 1522554 | 725025.7 | 61.12 | 11861.63 | 2019-04-30 | 6755.72 | 13255.49 | 7157.75 | 387129.25 | 54.09 | 6606.93 | 413899.23 | 2019-04-30 | 13764.68 | 52 | 801028.51 | 1.9 | -55065.05 | 205
17-120-0113.13 | DASNY Fahnestock State Park | Franco, Frank | 2.04 | 2.1 | 265000 | 126190.48 | 33.74 | 3739.58 | 2019-11-09 | 3610.22 | 4852.12 | 1246.75 | 77060.95 | 61.81 | 3499.23 | 162253.42 | 2019-11-09 | 4745.98 | 26.27 | 239314.37 | 1.11 | -113861.63 | 219.25
17-120-0113.14 | DASNY - BMCC Plaza Restoration | Franco, Frank | 2.04 | 2.1 | 530300 | 252523.81 | 65.45 | 3858.27 | 2019-12-01 | 1296.72 | 4805.72 | 3509 | 233495.75 | 66.54 | 1296.72 | 86286.29 | 2019-12-01 | 4805.72 | 73.02 | 319782.03 | 1.66 | -59506.85 | 153
17-120-0113.15 | DASNY - Harriman State Park | Franco, Frank | 2.04 | 1.92 | 302680 | 157542.86 | 54.41 | 2895.51 | 2020-01-01 | 1390.47 | 2249.77 | 859.3 | 57483.57 | 66.9 | 1390.47 | 64144.46 | 2020-01-01 | 2249.77 | 38.2 | 121628.03 | 2.49 | 39859.12 | 3
17-120-0113.17 | DASNY - York College | Franco, Frank | 2.04 | 2.1 | 417845 | 198973.81 | 40 | 4974.35 |  | 4596.35 | 378 | 378 | 30916.83 | 81.79 | 4511.35 | 368985.84 |  | 4889.35 | 7.73 | 399902.67 | 1.04 | -196948.06 | 85
17-120-0113.20 | DASNY- York College BMS Controls | Ribeiro, Raymond | 2.15 | 2.1 | 497233 | 236777.62 | 40 | 5919.44 |  | 0 | 537.03 | 537 | 35298.76 | 65.73 | 0.03 | 1.97 |  | 537.03 | 99.99 | 35300.73 | 14.09 | 201487.84 | 23
17-122-0275 | NYCEDC Andrew Haswell Green Pk - PH 2 | Bradley, Daniel | 2.04 | 2.1 | 2187728 | 1041775.24 | 42.31 | 24622.73 | 2021-07-01 | 23591.32 | 24785.57 | 1194.25 | 85490.67 | 71.59 | 23591.32 | 972798.08 | 2021-07-01 | 24785.57 | 4.82 | 1058288.75 | 2.07 | 14032.19 | 0
17-126-0376 | SUCF Downstate Medical-Upgrade UHB Elec | Burke, Stephen | 2.04 | 2 | 1875079.5 | 937539.75 | 101.75 | 9214.04 | 2025-05-01 | 8596.66 | 10710.92 | 2188 | 154179.12 | 70.47 | 8522.92 | 756594.54 | 2025-05-01 | 10710.92 | 20.43 | 910773.66 | 2.06 | 25295.8 | 67
17-132-0275 | NYCEDC Bushwick Inlet Demolition | Reo, Jennifer | 2.04 | 2.08 | 1166557 | 560844.71 | 47.04 | 11922.1 | 2019-09-01 | 5182 | 12293 | 7111 | 385603.97 | 54.23 | 5182 | 270319.2 | 2019-09-01 | 12293 | 57.85 | 655923.19 | 1.78 | -83862.68 | 37.5
17-134-0136 | Erie County Med Emerg Dept Modernization | Kreuzer, Robert | 2.08 | 2.1 | 1058282.59 | 503944.1 | 45.16 | 11159.36 | 2019-03-01 | 4068.48 | 11625.88 | 7615 | 349837.82 | 45.94 | 4028.48 | 185991.54 | 2019-03-01 | 11643.48 | 65.4 | 535829.35 | 1.98 | -17735.08 | 180
17-141-0267 | NYCDEP Constr of Right of Way Green Infr | Ribeiro, Raymond | 2.04 | 2.05 | 1915764.72 | 936355.26 | 57.09 | 16401.84 | 2020-06-01 | 1897.34 | 10490.34 | 8593 | 550209.4 | 64.03 | 1897.34 | 126199.22 | 2020-06-01 | 10490.34 | 81.91 | 676408.58 | 2.83 | 262408.64 | 99
17-141-0267.02 | NYCDEP Water Meter Installation at NYCHA | Ribeiro, Raymond | 2.04 | 2.1 | 1028883 | 489944.29 | 50.99 | 9609.31 | 2020-03-31 | 5878.98 | 19461.48 | 13582.5 | 709116.08 | 52.21 | 5878.98 | 304456.59 | 2020-03-31 | 19461.48 | 69.79 | 1013572.63 | 1.02 | -506315.19 | 97.75
17-141-0267.03 | NYCDEP - Amawalk Dam Ogee Spillway | Ribeiro, Raymond | 2.04 | 2.1 | 432802.63 | 206096.49 | 71.46 | 2884.15 |  | 2675.09 | 608.88 | 54 | 4425.89 | 81.96 | 2675.09 | 188252.32 |  | 2729.09 | 1.98 | 192678.21 | 2.25 | 19480.62 | 0
17-141-0267.04 | NYCDEP- WQMON-ENT2 Construction of Above | Ribeiro, Raymond | 2.04 | 2.06 | 327288.16 | 158553.59 | 40 | 3963.85 |  | 2929.85 | 1894.81 | 1034 | 51388.56 | 49.7 | 2833.85 | 129467.69 |  | 3867.85 | 26.73 | 180856.26 | 1.81 | -20494.14 | 96
17-141-0267.05 | NYCDEP- 26W-13G Elec and Special Inspect | Ribeiro, Raymond | 2.07 | 2.12 | 26898.73 | 12667.54 | 40 | 316.69 |  | 122.94 | 193.75 | 193.75 | 10452.01 | 53.95 | 115.69 | 7848.42 |  | 309.44 | 62.61 | 18300.43 | 1.47 | -5383.1 | 7.25
17-146-0265.01 | NYCDDC Crossroads Renovations-CJCREN | Bendetti, Michael | 2.04 | 2.25 | 6498560 | 2888248.89 | 73.36 | 39370.67 | 2020-12-31 | 7401.95 | 27969.95 | 20568 | 1405335.23 | 68.33 | 7401.95 | 505536.15 | 2020-12-31 | 27969.95 | 73.54 | 1910871.45 | 3.4 | 1276286.68 | 261
17-146-0265.02 | NYCDDC - Horizon Renovations | Bendetti, Michael | 2.04 | 2.15 | 5844976 | 2718593.49 | 64.34 | 42253.55 | 2020-12-31 | 10318.94 | 27187.69 | 16868.75 | 1047842.7 | 62.12 | 10318.94 | 640985.62 | 2020-12-31 | 27187.69 | 62.05 | 1688828.34 | 3.46 | 1175884.89 | 256
17-146-0265.03 | NYCDDC Recon Harper St Asphalt Plant | Reo, Jennifer | 2.04 | 1.69 | 2154040 | 1277020 | 59.55 | 21444.62 | 2022-09-15 | 21211.73 | 21469.98 | 258.25 | 20143.18 | 78 | 21211.73 | 1264764.36 | 2022-09-15 | 21469.98 | 1.2 | 1284907.55 | 1.68 | -8201.78 | 10
17-153-0113 | DASNY-at-Risk Tower 3 Renov Buffalo S | Kreuzer, Robert | 2.04 | 2.35 | 769397.59 | 327403.23 | 49.24 | 6648.96 | 2019-10-09 | 1069.78 | 7757.28 | 6687.5 | 334368.86 | 50 | 976.31 | 47105.62 | 2019-10-09 | 7663.81 | 87.26 | 381474.48 | 2.02 | -4017.78 | 88
17-159-0865 | NYU Winthrop Hosp - Program Management | Franco, Frank | 2.04 | 2.05 | 1104778 | 538916.08 | 59.37 | 9077.61 | 2018-07-01 | 6129.57 | 10205.57 | 4076 | 292591.31 | 71.78 | 5667.66 | 297950.36 | 2018-07-01 | 9743.66 | 41.83 | 590541.69 | 1.87 | -49190.68 | 0
17-169-0112 | Diocese Of Rockville Centre - On Call | Pfister, Frank | 2.04 | 2.37 | 277949.9 | 117340.07 | 53.31 | 2201.06 | 2018-11-14 | 246.79 | 2356.45 | 2149.75 | 114670.21 | 53.34 | 109.36 | 6272.02 | 2018-11-14 | 2259.11 | 95.16 | 120942.22 | 2.3 | 15296.76 | 3.5
18-007-0248.01 | NCDPW On-Call Building Design | Bendetti, Michael | 2.44 | 2.1 | 52828.6 | 25156.48 | 63.8 | 394.33 | 2018-07-03 | 69.63 | 534.63 | 465 | 29040.71 | 62.45 | 46.85 | 2727.57 | 2018-07-03 | 511.85 | 90.85 | 31768.27 | 1.66 | -6607.03 | 0
18-024-0132 | ECHDC Canalside Interpretive Structures | Kreuzer, Robert | 2.04 | 2 | 738515.56 | 369257.78 | 41.44 | 8910.96 | 2019-08-01 | 7771.25 | 9521 | 1749.75 | 109660.98 | 62.67 | 7771.25 | 391466.92 | 2019-08-01 | 9521 | 18.38 | 501127.9 | 1.47 | -132680.19 | 60
18-138-0271 | DSNY BKLYN Community District 3 Facility | Choudhury, Faisal | 2.04 | 2.1 | 7410613 | 3528863.34 | 80.43 | 43876.64 | 2024-05-31 | 39569.52 | 44694.52 | 5125 | 318949.89 | 62.23 | 39501.97 | 2247601.24 | 2024-05-31 | 44626.97 | 11.48 | 2566551.12 | 2.89 | 1068776.01 | 334
18-213-0283 | NYIT PM Svcs Campus Commons & Wisser Lib | Burke, Stephen | 2.04 | 2.2 | 2425000 | 1102272.73 | 42.99 | 25638.74 | 2022-07-15 | 25123.74 | 25816.74 | 693 | 71789.57 | 103.59 | 25012.74 | 1037449.55 | 2022-07-15 | 25705.74 | 2.7 | 1109239.12 | 2.19 | 79508.32 | 0
18-272-0282.Q | NYCSCA Emergency Program 2018 Queens | Radafshar, Bijan | 2.04 | 1.16 | 305318.96 | 263206 | 38.19 | 6892.88 | 2021-09-01 | 4859.88 | 3118.61 | 2211 | 89147.84 | 40.32 | 4656.88 | 186035.42 | 2021-09-01 | 6867.88 | 32.19 | 275183.26 | 1.11 | -12376.46 | 25
18-281-0136 | ECMC-Owners's Rep-Multiple Construction | Kreuzer, Robert | 2.04 | 2 | 327000 | 163500 | 44.05 | 3711.73 | 2018-12-31 | 298.29 | 2821.04 | 2522.75 | 114334.98 | 45.32 | 298.29 | 12978.15 | 2018-12-31 | 2821.04 | 89.43 | 127313.13 | 2.57 | 36044.53 | 82
18-339-0380 | SUNY Stony Brook-OR Svcs W. Apts- Bldg K | Burke, Stephen | 2.04 | 2.1 | 789891 | 376138.57 | 42.47 | 8857.44 | 2021-08-03 | 6868.62 | 8986.72 | 2178.75 | 149982.79 | 68.84 | 6868.62 | 463456.18 | 2021-08-03 | 9047.37 | 24.08 | 613438.98 | 1.29 | -224932.87 | 171
18-360-0315.02 | WSP - E. River State Park Classroom Bldg | Franco, Frank | 2.27 | 2.2 | 56000 | 25454.54 | 40 | 636.36 | 2019-04-01 | 619.71 | 529.26 | 165.5 | 11661.27 | 70.46 | 619.71 | 43640.2 | 2019-04-01 | 785.21 | 21.08 | 55301.47 | 1.01 | -28901.29 | 0
18-360-0315.03 | WSP - RCSP Shoreline | Franco, Frank | 2.04 | 2.2 | 204707 | 93048.64 | 40 | 2326.22 |  | 0.01 | 385.01 | 385 | 23974.31 | 62.27 | 0.01 | 0.62 |  | 385.01 | 100 | 23974.93 | 8.54 | 76376.19 | 0
18-360-0315.04 | WSP - RCSP Upper Plaza | Franco, Frank | 2.04 | 2.2 | 204707 | 93048.64 | 40 | 2326.22 |  | 180.09 | 1391.09 | 1211 | 78866.01 | 65.12 | 180.09 | 11728.31 |  | 1391.09 | 87.05 | 90594.32 | 2.26 | 9768.25 | 0
19-009-0270 | NYCP&R CM Svcs for Battery Carousel Supp | Choudhury, Faisal | 2.04 | 1 | 24870 | 24870 | 59.92 | 415.05 | 2019-01-01 | 397.05 | 415.05 | 18 | 1091.44 | 60.64 | 397.05 | 24075.35 | 2019-01-01 | 415.05 | 4.34 | 25166.79 | 0.99 | -251.21 | 0
19-013-0031 | BPCA - CM Svcs for Community Ctr Leak Re | Franco, Frank | 2.04 | 2.1 | 352800 | 168000 | 40 | 4200 | 2020-03-15 | 3268.93 | 4293.93 | 1025 | 66965.45 | 65.33 | 3268.93 | 206184.27 | 2020-03-15 | 4293.93 | 23.87 | 273149.72 | 1.29 | -99915.99 | 75
19-015-0376.01 | SUNY Downstate Med Ctr Isolation/Oper Rm | Burke, Stephen | 2.04 | 2.1 | 763400 | 363523.81 | 40 | 9088.09 |  | 8874.1 | 9114.1 | 240 | 22167.72 | 92.37 | 8874.1 | 378618.54 |  | 9114.1 | 2.63 | 400786.26 | 1.9 | -26225.01 | 17
19-015-0376.02 | SUNY Purchase HVAC Reno-Dance Bldg 29 | Burke, Stephen | 2.04 | 2.1 | 203000 | 96666.67 | 103.57 | 933.35 |  | 83.35 | 850 | 850 | 53651.61 | 63.12 | 79.35 | 5008.54 |  | 929.35 | 91.46 | 58660.14 | 3.46 | 40839.28 | 4
19-015-0376.03 | SUNY Demo 34th St Park Garage 141057-01 | Burke, Stephen | 2.04 | 2.1 | 275814 | 131340 | 40 | 3283.5 |  | 3159 | 3334 | 175 | 18111.12 | 103.49 | 3159 | 138541.6 |  | 3334 | 5.25 | 156652.72 | 1.76 | -21445.63 | 30
19-018-0276.01 | FDNY-EMS20 - Multi Component Renovation | Blum, Walter | 2.04 | 2.1 | 354856 | 168979.05 | 63.93 | 2643.19 | 2020-01-31 | 846.83 | 3528.83 | 2682 | 177392.09 | 66.14 | 846.83 | 56010.79 | 2020-01-31 | 3528.83 | 76 | 233402.89 | 1.52 | -59508.88 | 117
19-018-0276.02 | FDNY - EC-24 Female Firefighter Toilet U | Reo, Jennifer | 2.04 | 2.1 | 357390 | 170185.71 | 56.77 | 2997.81 | 2020-02-28 | 994.36 | 3642.86 | 2648.5 | 150343.86 | 56.77 | 994.36 | 56445.5 | 2020-02-28 | 3642.86 | 72.7 | 206789.35 | 1.73 | -31392.64 | 107
19-018-0276.03 | FDNY- EC253 Multi-Component Reno COMM#2 | Reo, Jennifer | 2.04 | 2.1 | 355700.52 | 169381.2 | 71.68 | 2363.02 | 2020-01-31 | 801.2 | 2641.45 | 1840.25 | 111652.28 | 60.67 | 801.2 | 48610.68 | 2020-01-31 | 2641.45 | 69.67 | 160262.95 | 2.22 | 14137.54 | 11
19-018-0276.04 | FDNY FEMA Fiber Project-FINO-Proof of Co | Blum, Walter | 2.15 | 2.1 | 11349 | 5404.29 | 40 | 135.11 |  | 135.11 | 135.11 | 0 | 0 | 0 | 135.11 | 5404.4 |  | 135.11 | 0 | 5404.4 | 2.1 | 0 | 0
19-030-0821 | Roswell 2019 Term Constr Agreement | Kreuzer, Robert | 2.04 | 2 | 469379.81 | 234689.96 | 40.93 | 5733.33 |  | 810.12 | 5470.12 | 5399.5 | 241522.62 | 44.73 | -89.92 | -2276.23 |  | 5309.58 | 101.69 | 239246.38 | 1.96 | -3575.79 | 330.75
19-034-0269 | DHS - CM Svcs Reno Proj at Shelter Site | Franco, Frank | 2.05 | 2.1 | 2227621.2 | 1060772 | 55.89 | 18980.01 | 2022-11-12 | 25947.59 | 18710.29 | 1205.25 | 75301.87 | 62.48 | 25925.59 | 1527195.99 | 2022-11-12 | 27130.84 | 4.44 | 1602497.86 | 1.39 | -264361.22 | 146
19-065-0113.01 | DASNY - FIT 30% Cost Estimate | Frysztacki, Edward | 2.04 | 1.9 | 60000 | 31578.95 | 65.59 | 481.46 |  | 258.47 | 756.97 | 498.5 | 32998.77 | 66.2 | 258.47 | 17109.71 |  | 756.97 | 65.85 | 50108.48 | 1.2 | -18421.05 | 0
19-072-0347.01 | RIOC - Motorgate Garage | Franco, Frank | 2.04 | 2.1 | 1327600 | 632190.48 | 40 | 15804.76 |  | 14594.01 | 1210.75 | 1210.75 | 84166.49 | 69.52 | 14525.01 | 1009720.45 |  | 15735.76 | 7.69 | 1093886.93 | 1.21 | -446405.77 | 69
19-072-0347.02 | RIOC - Bridges | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 13.22 | 494.47 | 481.25 | 33488.18 | 69.59 | 13.22 | 919.92 |  | 494.47 | 97.33 | 34408.11 | 0 | 0 | 0
19-072-0347.03 | RIOC - Lighthouse Restoration | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 0 | 101.51 | 101.5 | 5674.26 | 55.9 | 0.01 | 0.56 |  | 101.51 | 99.99 | 5674.82 | 0 | 0 | 9
19-072-0347.04 | RIOC - Seawall Railings | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 0 | 80.25 | 80.25 | 6025.94 | 75.09 | -80.25 | -6025.94 |  | 0 | 0 | 0 | 0 | 0 | 0
19-072-0347.05 | RIOC - Youth Center | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 0 | 899.5 | 899.5 | 54301.85 | 60.37 | -899.5 | -54301.85 |  | 0 | 0 | 0 | 0 | 0 | 85
19-072-0347.06 | RIOC - Water Distribution | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 740.06 | 33.75 | 33.75 | 2185.83 | 64.77 | 740.06 | 45048 |  | 773.81 | 4.36 | 47233.83 | 1.38 | -15294.75 | 0
19-072-0347.07 | RIOC - AVAC Upgrades | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 668.56 | 105.25 | 105.25 | 7364.46 | 69.97 | 651.56 | 34700.28 |  | 756.81 | 13.91 | 42064.74 | 1.55 | -10115.31 | 17
19-072-0347.08 | RIOC - Sportspark Renovation | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 476.19 | 770.44 | 294.25 | 21417.49 | 72.79 | 479.56 | 19292.89 |  | 773.81 | 38.03 | 40710.38 | 1.6 | -8924.01 | 8.5
19-072-0347.09 | RIOC - Octagon Field | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 247.62 | 635.75 | 635.75 | 45004.13 | 70.79 | 138.06 | 3041.85 |  | 773.81 | 82.16 | 48045.97 | 1.35 | -16217.74 | 3
19-072-0347.10 | RIOC - Small Pox Hospital | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 692.06 | 557.94 | 81.75 | 6101.35 | 74.63 | 690.06 | 35009.63 |  | 771.81 | 10.59 | 41110.98 | 1.58 | -9308.77 | 2
19-072-0347.11 | RIOC - Octogon Field Phase 2 | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 231.25 | 353.26 | 353.25 | 24859.53 | 70.37 | 224.76 | 18398.06 |  | 578.01 | 61.11 | 43257.59 | 1.5 | -10681.82 | 57.5
19-072-0347.12 | RIOC - Firefighters Field | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 693.5 | 619 | 119 | 8631.22 | 72.53 | 683 | 33273.22 |  | 802 | 14.84 | 41904.44 | 1.55 | -9429.82 | 10.5
19-072-0347.13 | RIOC - Hope Memorial | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 709.5 | 103 | 103 | 7363.48 | 71.49 | 698.5 | 37087.82 |  | 801.5 | 12.85 | 44451.3 | 1.46 | -11966.4 | 11
19-072-0347.14 | RIOC - Blackwell House | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 643.25 | 169.25 | 169.25 | 11399.56 | 67.35 | 614.75 | 41191.99 |  | 784 | 21.59 | 52591.55 | 1.24 | -20079.36 | 28.5
19-072-0347.15 | RIOC - SOSP Rip Rap Reventment | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 632 | 180.5 | 180.5 | 13270.19 | 73.52 | 629 | 25070.69 |  | 809.5 | 22.3 | 38340.88 | 1.7 | -5879.8 | 3
19-072-0347.16 | RIOC - AVAC Maintenance | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 799 | 326 | 13.5 | 1144.26 | 84.76 | 799 | 53735.74 |  | 812.5 | 1.66 | 54880 | 1.18 | -22553.19 | 0
19-072-0347.17 | RIOC - Assessments & Graphics | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 812.5 | 812.5 | 0 | 0 | 0 | 812.5 | 32500 |  | 812.5 | 0 | 32500 | 2 | 0 | 0
19-072-0347.18 | RIOC - Misc OR Requests | Engblom, Trevor | 2.04 | 2 | 20000 | 10000 | 40 | 250 |  | 0 | 623.53 | 623.5 | 43472.72 | 69.72 | 0.03 | 2.09 |  | 623.53 | 100 | 43474.81 | 0.46 | -33478.26 | 64.5
19-072-0347.19 | RIOC - Tramway Elevator | Engblom, Trevor | 2.11 | 2 | 411800 | 205900 | 40 | 5147.5 |  | 5123 | 5147.5 | 24.5 | 1333.42 | 54.43 | 5123 | 205540.29 |  | 5147.5 | 0.48 | 206873.71 | 1.99 | -973.47 | 24.5
19-082-0093 | Columbia University CM Svcs Lerner Hall | Burke, Stephen | 2.04 | 2.1 | 60000 | 28571.43 | 40 | 714.27 |  | 515.2 | 521.11 | 223.5 | 18376.68 | 82.22 | 490.77 | 20091.2 |  | 714.27 | 31.29 | 38467.88 | 1.56 | -9005.07 | 0
19-117-0278.01 | NYCHA-Boiler Replacemnt-Sotomayor Houses | Choudhury, Faisal | 2.04 | 2.2 | 5549782 | 2522628.18 | 40 | 63065.7 |  | 58369.95 | 7779.78 | 4695.75 | 268772.26 | 57.24 | 57881.95 | 3259848.38 |  | 62577.7 | 7.5 | 3528620.62 | 1.57 | -808290.96 | 488
19-117-0278.02 | NYCHA-Boiler Replacemnt-Taft Houses | Choudhury, Faisal | 2.04 | 2.2 | 4080108 | 1854594.54 | 40 | 46364.86 |  | 4507.03 | 4013.04 | 4013 | 229618.87 | 57.22 | 4507.07 | 265105.79 |  | 8520.07 | 47.1 | 494724.67 | 8.25 | 1506052.7 | 377
19-117-0278.03 | NYCHA - Harborview Terrace Balconies | Wong, David | 2.15 | 2.2 | 1652037 | 750925.91 | 40 | 18773.14 |  | 18773.14 | 18773.14 | 0 | 0 | 0 | 18773.14 | 750925.6 |  | 18773.14 | 0 | 750925.6 | 2.2 | 17463.39 | 0
19-117-0278.04 | NYCHA-Ingersoll Exter Reno Contract 2 | Choudhury, Faisal | 2.04 | 2.2 | 3826218 | 1739190 | 40 | 43479.75 |  | 42928.75 | 551 | 551 | 29042.13 | 52.71 | 42808.75 | 2256365.31 |  | 43359.75 | 1.27 | 2285407.44 | 1.67 | -415551.44 | 120
19-117-0278.05 | NYCHA-Ingersoll Exter Reno Contract 1 | Choudhury, Faisal | 2.04 | 2.2 | 2970852 | 1350387.27 | 40 | 33759.68 |  | 33645.68 | 114 | 114 | 5381.94 | 47.21 | 33597.68 | 1586146.47 |  | 33711.68 | 0.34 | 1591528.41 | 1.87 | -132390.91 | 48
19-117-0278.06 | NYCHA-Whitman Houses Exterior Renovation | Choudhury, Faisal | 2.04 | 2.2 | 2699379 | 1226990.45 | 40 | 30674.76 |  | 25548.51 | 5126.25 | 5126.25 | 288742.59 | 56.33 | 20614.26 | 1161124.58 |  | 25740.51 | 19.92 | 1449867.17 | 1.86 | -128054.03 | 4934.25
19-133-0865 | NYUWH WSA Renovations at 120 Mineola Blv | Ansari, Kamran | 2.04 | 2.03 | 178384 | 87873.89 | 40 | 2196.85 |  | 1794.85 | 402 | 402 | 33583.08 | 83.54 | 1794.85 | 149941.77 |  | 2196.85 | 18.3 | 183524.85 | 0.97 | -96027.14 | 0
19-133-0865.02 | NYUWH - Hospital Lab Planning | Ansari, Kamran | 2.04 | 2.03 | 80000 | 39408.87 | 40 | 985.22 |  | 673.22 | 312 | 312 | 26064.48 | 83.54 | 673.22 | 56240.8 |  | 985.22 | 31.67 | 82305.28 | 0.97 | -43065.36 | 0
19-133-0865.03 | NYUWH-Wound Care Relocation from 120 MB | Ansari, Kamran | 2.04 | 2.03 | 96000 | 47290.64 | 40 | 1182.27 |  | 949.27 | 233 | 233 | 19464.82 | 83.54 | 949.27 | 79302.02 |  | 1182.27 | 19.71 | 98766.84 | 0.97 | -51678.43 | 0
19-133-0865.04 | NYUWH - Medivator DSD Scope Washer | Ansari, Kamran | 2.04 | 2.03 | 6000 | 2955.67 | 40 | 73.89 |  | 41.89 | 32 | 32 | 2673.28 | 83.54 | 41.89 | 3499.49 |  | 73.89 | 43.31 | 6172.77 | 0.97 | -3229.9 | 0
19-195-0290.01 | OPRHP - RCSP - South Playground | Franco, Frank | 2.15 | 2.1 | 338300 | 161095.24 | 40 | 4027.38 |  | 0 | 480.53 | 480.5 | 29696.68 | 61.8 | 0.03 | 1.85 |  | 480.53 | 99.99 | 29698.53 | 11.39 | 131393.75 | 145.5
19-195-0290.02 | OPRHP - RCSP - Electrical Upgrade | Franco, Frank | 2.15 | 2.1 | 338300 | 161095.24 | 40 | 4027.38 |  | 367 | 367 | 0 | 0 | 0 | 367 | 14680 |  | 367 | 0 | 14680 | 23.04 | 146412.08 | 0
19-201-0248.01 | NCDPW - Mission 4 CPM Scheduler | Hurley, Joseph | 2.15 | 2.2 | 73000 | 33181.82 | 40 | 829.55 |  | 764.55 | 65 | 65 | 4360.9 | 67.09 | 764.55 | 51294.25 |  | 829.55 | 7.84 | 55655.15 | 1.31 | -21771.7 | 0
19-217-0271 | DSNY Bronx District 9, 10, 11 Facility | Choudhury, Faisal | 2.15 | 2.1 | 14384757 | 6849884.29 | 40 | 171247.11 |  | 170308.36 | 164352.21 | 938.75 | 67233.74 | 71.62 | 170249.36 | 7026796.26 |  | 171188.11 | 0.55 | 7094030.01 | 2.03 | -245760.35 | 59
19-225-0282 | NYCSCA - CM Contingent & Temp Staffing | Frangas, Andrew | 2.15 | 1.97 | 1250000 | 634517.77 | 40 | 15862.94 |  | 12585.94 | 3277 | 3277 | 174123.45 | 53.14 | 11928.94 | 633844.47 |  | 15205.94 | 21.55 | 807967.93 | 1.55 | -171933.85 | 657
19-238-0270 | NYCP&R - Highbridge Park Comfort Station | Hurley, Joseph | 2.15 | 2.4 | 15109.73 | 6295.72 | 40 | 157.39 |  | 102.39 | 55 | 55 | 5009.08 | 91.07 | 97.39 | 8869.71 |  | 152.39 | 36.09 | 13878.79 | 1.09 | -6834.36 | 5
19-242-2292 | Broad Channel VFD-PLA Feasibility Study | Hurley, Joseph | 2.15 | 2.57 | 13572.89 | 5281.28 | 40 | 132.03 |  | 69.03 | 63 | 63 | 5713.08 | 90.68 | 69.03 | 6259.9 |  | 132.03 | 47.72 | 11972.98 | 1.13 | -5698.43 | 0
19-243-0031.01 | Battery Pk Resiliency- Feasibility Analy | Franco, Frank | 2.15 | 2.4 | 29495.62 | 12289.84 | 40 | 307.25 |  | 241.25 | 66 | 66 | 5800.08 | 87.88 | 241.25 | 21201.05 |  | 307.25 | 21.48 | 27001.13 | 1.09 | -13341.31 | 0
19-243-0031.02 | Battery Pk City - Rockefeller Park | Franco, Frank | 2.15 | 2.4 | 84000 | 35000 | 40 | 875 |  | 866 | 875 | 9 | 555.84 | 61.76 | 866 | 53484.16 |  | 875 | 1.03 | 54040 | 1.55 | -15123.78 | 9
19-247-1139 | USDOT- PM Oversight Svcs | Valdemira, Vincent | 2.15 | 2.17 | 1602650 | 738548.39 | 40 | 18463.71 |  | 18461.71 | 18463.71 | 2 | 224.08 | 112.04 | 18461.71 | 2068449.99 |  | 18463.71 | 0.01 | 2068674.07 | 0.77 | -1335945.03 | 2
19-248-0245 | MTA-IQ for Federal Construction Projects | Valdemira, Vincent | 2.15 | 2.1 | 30018 | 14294.29 | 40 | 357.36 |  | 296.61 | 60.75 | 60.75 | 5123.54 | 84.34 | 256.11 | 21599.83 |  | 316.86 | 19.17 | 26723.37 | 1.12 | -12507.5 | 40.5