## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | MEP | Allaben, Jonah | 14-080-0248 |  | NCDPW Bay Park E3 HVAC and Plumbing | 148750 | 133142 | 826 | 826 | 2018-06-08 | 11/16/2018 - no action12/21/2018 - no action8/27/2019 - JRA - Awaiting milestone - WIP is recoverable. The next milestone is construction completion. | [6 empty] | N |  | N
2 | MEP | Allaben, Jonah | 14-080-0248 | MEPSDC |  |  |  |  | 826
3 | MEP | Allaben, Jonah | 18-029-0245 |  | MTA-NYC Transit E. NY Bus Depot-HVAC Upg | 508200 | 407862 | 66583 | 9584 | 2019-09-27 | [7 empty] | N |  | N
4 | MEP | Allaben, Jonah | 18-029-0245 | 1 |  |  |  |  | 6423
5 | MEP | Allaben, Jonah | 18-029-0245 | 2 |  |  |  |  | 3160
6 | MEP | Allaben, Jonah | 18-116-0238 |  | TBTA HC-64 HLCT Svc Bldg Elec Rehab | 416737 | 322665 | 9050 | 5018 | 2019-10-11 | 11/27/19 – Jonah Allaben;90% complete with construction;Date invoice is expected to be issued: 12/10;Projected amount of next invoice: $49,600;WIP Category (F)Notes: aged WIP associated with time billed to closeout phase and will be cleared for closeout invoice. | [6 empty] | N |  | N
7 | MEP | Allaben, Jonah | 18-116-0238 | 1 |  |  |  |  | 294
8 | MEP | Allaben, Jonah | 18-116-0238 | 4 |  |  |  |  | 4472
9 | MEP | Allaben, Jonah | 18-116-0238 | 6 |  |  |  |  | 252
10 | MEP | Allaben, Jonah | 18-308-0090 |  | CUNY - BMCC Cooling Tower EPC | 305507 | 298793 | 17162 | 10757 | 2019-08-31 | 11/27/2019 - MSa no invoice expected; WIP is related to "Construction Documents - QC" task which was included in the previous invoice for early payment. WIP category: G. |  | 1828 |  |  |  |  | N |  | N
11 | MEP | Allaben, Jonah | 18-308-0090 | 3 |  |  |  |  | 10757 |  | 12/21/2018 - JRA preparing inv 90% progress inv $59,347 HWT preparing
12 | MEP | Allaben, Jonah | 18-308-0090 | [10 empty] | 1827.8 | 18308.004 | 2019-08-13 | 11/27/2019 - MSa;Cause of AR delay: client asked for the two tasks be in separate invoices since they are under different agreements;Last date of client contact: 11/4/2019;Individual contacted at client: John Ferretti;Expected date of payment: TBD - HT sent separate invoices on 11/15/19;
Total |  |  |  |  | 93621 | 52369 |  |  | 0 | 1828