## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | MEP | Blanch, Richard | 14-062-0267 |  | NYCDEP Pine Hill Tannersville and Grand | 292550 | 239099 | 2579 | 0 | 2019-11-08 | 12/2/19 RNBProject status - In ConstructionDate invoice is expected to be issued: Invoiced 11-27-19Projected amount of next invoice: Cleare WIP monthly during constructionWIP Category (E, F, G): G |  | 5000 |  |  |  |  | N |  | N
2 | MEP | Blanch, Richard | 14-062-0267 | [10 empty] | 5000 | 014062.018-R | 2018-05-23 | 12-2-19 RNBAR status: Invoices adjusted and just reissued 11-26-19 per clients request. Previous invoices applied to bid phase erroneously by client.Last date of client contact: 11-20-19Individual contacted at client: Mladen NovakovicExpected date payment will be received: 12-31-19AR Category (A, B, C, or D): B
3 | MEP | Blanch, Richard | 17-010-0344 |  | RHA Arch,MEP & Structural Services | 132772 | 72059 | 7497 | 7057 | 2019-08-30 | 12/2/19 RNBProject Status- Federal Neighborhood Ph 20 ---in negotiation for additional fee for added effort for site plan approval process documentsDate invoice is expected to be issued: 12-27-19Projected amount of next invoice: Clear WIPWIP Category (E, F, G): F | [6 empty] | N |  | N
4 | MEP | Blanch, Richard | 17-010-0344 | 6 |  |  |  |  | 428
5 | MEP | Blanch, Richard | 17-010-0344 | 11 |  |  |  |  | 1649
6 | MEP | Blanch, Richard | 17-010-0344 | 15 |  |  |  |  | 440
7 | MEP | Blanch, Richard | 17-010-0344 | 17 |  |  |  |  | 2145 |  | 5-30-18 RNB - WIP and sub invoices sent to RHA this month.
8 | MEP | Blanch, Richard | 17-010-0344 | 18 |  |  |  |  | 220 |  | 5-30-18 RNB - WIP and sub invoices sent to RHA this month.
9 | MEP | Blanch, Richard | 17-010-0344 | 19 |  |  |  |  | 330 |  | 6/4/19 Generate Invoice - Clear WIP 8/22/18 - RB - Invoice Sep 2018.9/21/2018 - RB & HWT to work on10/23 - create a draft invoice for RB to review11/16/18 - RB re-send pending12/21/2018 - draft inv ph 18 shirley st1-23-2019 - RB - architectura - new invoice. RB sending info to HT
10 | MEP | Blanch, Richard | 17-010-0344 | 20 |  |  |  |  | 1846 |  | 6/4/19 Generate Invoice - Clear WIP 8/22/18 - RB - Invoice Sep 2018.9/21/2018 - RB & HWT to work on10/23 - create a draft invoice for RB to review11/16/18 - RB re-send pending12/21/2018 - draft inv ph 18 shirley st1-23-2019 - RB - architectura - new invoice. RB sending info to HT
11 | MEP | Blanch, Richard | 17-010-0344 | [10 empty] | -19.39 | 017010.PH3-2 | 2017-08-25 | 6/13/18 - Overpayment made on Invoice #17010.ph3-2. Notified Rick Blanch on 6/13/18. Asked if a check should be sent to client. hwt5-28-18 Lin Stango w/ RHA noted that RHA had large Grant to propcess so had staff issue but would be processing invoices by week 1 of June
12 | MEP | Blanch, Richard | 17-037-0195 |  | National Grid-Melville HUB Facility | 37835 | 37835 | 0 | 0 | 2019-01-18 | 8/22/2018 - RB - follow up with client to complete project. inv Sep 2018 to complete9/21/2018 - still in Constr-- approx invl end oct 201810/23 - waiting for constr completion approx end Nov11/16/18 - RB same as 10/23 RB to call natl grid12/21/2018 - RB bill out contract value1-23-2019 - RB official PO's came late. bill to contract value and pull all wip |  | 1129 |  |  |  |  | N |  | N
13 | MEP | Blanch, Richard | 17-037-0195 | [10 empty] | 79 | 17037.004 | 2018-04-03 | 8/12/19 - RB e-mailed back and forth with Brian Key @ brian.key@nationalgrid.com, with no satifying results on this outstanding portion of the invoice.
14 | MEP | Blanch, Richard | 17-037-0195 | [10 empty] | 1050 | 17037.005 | 2019-01-28 | 12-2-19AR status: Client indicates fully paid. MSA notes that if NG pays within 30days they can take discount for outstanding amount. Last date of client contact: 9-9-19Individual contacted at client: Brian KeyExpected date payment will be received: NAAR Category (A, B, C, or D): NA
15 | MEP | Blanch, Richard | 17-038-1430 |  | Regent Companies - Michigan Apartments | 186400 | 138106 | 16044 | 16044 | 2018-05-25 | 12/2/19 RNBProject Status- Design - client waiting for City Buffalo site approvalDate invoice is expected to be issued: TBD - as soon as design restarts ( anticipated January)Projected amount of next invoice: Clear WIPWIP Category (E, F, G): F | [6 empty] | N |  | N
16 | MEP | Blanch, Richard | 17-038-1430 | 1 |  |  |  |  | 10434
17 | MEP | Blanch, Richard | 17-038-1430 | 2 |  |  |  |  | 590
18 | MEP | Blanch, Richard | 17-038-1430 | 3 |  |  |  |  | 5019
19 | MEP | Blanch, Richard | 17-038-1430 | [10 empty] | -20454.43 | 17038.007 | 2018-09-21
20 | MEP | Blanch, Richard | 17-038-1430 | [10 empty] | 20454.43 | 0017038.007R | 2018-09-21
21 | MEP | Blanch, Richard | 17-096-0195 |  | National Grid-Melville Call Ctr-RTU Inv | 8185 | 8185 | 0 | 0 | 2019-01-04 | 8/22/18 - RB - follow up with client to complete project. inv Sep 2018 to complete9/21/2018 - Still in Constr - nv end of oct 201811/16/18 - RB to call natl grid. will inform mon Nov 2012/21/2018 - RB bill to match PO1-23-2019 - bill to max contract value and pull all wip8-10-19 RB contacted National Grid manager Devraj Balbir. Dev mistakenly thought he had paid the outstanding 5k invoice, however had paid the other NG project 17-037. Dev to process ASAP this invoice. |  | 5000 |  |  |  |  | N |  | N
22 | MEP | Blanch, Richard | 17-096-0195 | [10 empty] | 3500 | 17096.002 | 2018-04-03 | 12-2-19 RNBAR status - NG acknowleded error in their accounting ( applied to wrong invoice)Last date of client contact: 11-15-19Individual contacted at client: Devraj BalbirExpected date payment will be received: 12-31-19AR Category (A, B, C, or D): B
23 | MEP | Blanch, Richard | 17-096-0195 | [10 empty] | 1500 | 17096.003 | 2019-02-08 | 12-2-19 RNBAR status - NG acknowleded error in their accounting ( applied to wrong invoice)Last date of client contact: 11-15-19Individual contacted at client: Devraj BalbirExpected date payment will be received: 12-31-19AR Category (A, B, C, or D): B
24 | MEP | Blanch, Richard | 17-110-1484 |  | RCS Arch-Delaware 130-138 GSA 3rd flr | 52355 | 52355 | 0 | 0 | 2019-01-18 | 6/4/19 Awaiting milestone- Effective multiplier is equal to or greater than 2.1 and less than 2.5. Chnageorder pending for extras services during construction. April 26, 2018PM: Rick BlanchDelay WIP: Direct client RCS Architects has asked for addtional $ 2800 for LiRo to cover WIP for SDC. I will check bi-weekly for update, and ideally will draft invlice for full $ 2800 by mid May. 5-30-18 RNB Two tasks ( security mods, and TICS review) will be approved for SDC effort to clear WIP - in negotiation expect resolution in June. 8/22/18 - RB - 6 invoices totaling approx $ 7900 and then wait re:remainder.conversation bet RB & HT.9/21/2018 - multiple chg orders can be billed- 6 separate invoices.10/23 - 2 new phases. clear wip. chg orders ea 7500 for inv to clear WIP.11/16/18 - RB to amend PIF to inv approx Dec12/21/2018 - RB bill out contract value CA phase though NTE1-23-2019 - RB - client requests full invoice with details. reformat last invoice into phases. |  | 7878 |  |  |  |  | N |  | N
25 | MEP | Blanch, Richard | 17-110-1484 | [10 empty] | 7878.28 | 0017110.004R | 2019-01-25 | 12-2-19 RNBAR status - RB and Helen Travis reviewing invoices w client - confustion w regards to tasks and feesLast date of client contact: 11-22-19Individual contacted at client: Bob SpahnExpected date payment will be received: 12-31-19 at least partial paymentAR Category (A, B, C, or D): A
26 | MEP | Blanch, Richard | 18-214-0134 |  | Erie County DPW-Health Lab-RTU Replaceme | 59500 | 33050 | 7337 | 3572 | 2019-09-13 | 12/2/19 RNBProject Status- In ConstructionDate invoice is expected to be issued: 12-27-19Projected amount of next invoice: Clear WIPWIP Category (E, F, G): EChange order approved for $10,000 design contingiency and billed. | [6 empty] | N |  | N
27 | MEP | Blanch, Richard | 18-214-0134 | 1 |  |  |  |  | 270
28 | MEP | Blanch, Richard | 18-214-0134 | 2 |  |  |  |  | 94
29 | MEP | Blanch, Richard | 18-214-0134 | 3 |  |  |  |  | 3208
30 | MEP | Blanch, Richard | 18-256-0134 |  | ECDPW-Erie County Holding Ctr - Kitchen | 38080 | 23300 | 2294 | 2294 | 2019-08-30 | 12/2/19 RNBProject Status- In ConstructionDate invoice is expected to be issued: 12-27-19Projected amount of next invoice: Clear WIPWIP Category (E, F, G): F | 3353 | [5 empty] | N |  | N
31 | MEP | Blanch, Richard | 18-256-0134 | 1 |  |  |  |  | 787
32 | MEP | Blanch, Richard | 18-256-0134 | 3 |  |  |  |  | 1507
33 | MEP | Blanch, Richard | 18-277-0301 |  | NFTA - MEP Term | 74547 | 49820 | 47863 | 33581 | 2019-08-02 | 12/2/19 RNBProject Status- 98% Design Submitted for AHU7 and SOGR Final Report SubmittedDate invoice is expected to be issued: 12-10-19Projected amount of next invoice: Clear WIP for 2 phases ( AHU7 & SOGR Report)WIP Category (E, F, G): F | [6 empty] | N |  | N
34 | MEP | Blanch, Richard | 18-277-0301 | 1 |  |  |  |  | 12264
35 | MEP | Blanch, Richard | 18-277-0301 | 4 |  |  |  |  | 9006
36 | MEP | Blanch, Richard | 18-277-0301 | 5 |  |  |  |  | 12310
37 | MEP | Blanch, Richard | 18-277-0301 | [10 empty] | -2585.75 | 000000000ADV | 2019-07-09
38 | MEP | Blanch, Richard | 18-277-0301 | [10 empty] | -0.01 | 18277PH1.001 | 2019-04-02
39 | MEP | Blanch, Richard | 18-277-0301 | [10 empty] | -564.25 | 18277PH4.001 | 2019-04-02
40 | MEP | Blanch, Richard | 18-284-1987 |  | Dean Architects PLLC- Queens Self Storag | 19200 | 19200 | 3322 | 3225 | 2019-01-18 | 12/2/19 RNBProject Status - In Construction. Fee for Design only and client paid in full. Changer Order requested for SDCDate invoice is expected to be issued: TBDProjected amount of next invoice: WIPWIP Category (E, F, G):F | [6 empty] | N |  | N
41 | MEP | Blanch, Richard | 18-284-1987 | 1 |  |  |  |  | 3225
42 | MEP | Blanch, Richard | 19-101-2169 |  | True North Rochester Prep Audits | 25395 | 30376 | 281 | 0 | 2019-08-30 | 12/2/19 RNBProject Status- Final reports submittedDate invoice is expected to be issued: 12-10-19Projected amount of next invoice: Clear WIP & $ 6450 approved CO to be included w final invoiceWIP Category (E, F, G): EEffort for reports exceeded expectations. | 3115 | [5 empty] | N |  | N
43 | MEP | Blanch, Richard | 19-171-0541 |  | Vill of Macedon-Architectura -Emerg Svcs | 9500 | 9500 | 0 | 0 | 2019-08-30 | 12/2/19 RNBProject Status- Project completeDate invoice is expected to be issued: NAProjected amount of next invoice: No WIP - project completeWIP Category (E, F, G): G | 9500 | [5 empty] | N |  | N
44 | MEP | Blanch, Richard | 19-174-2232 |  | Heritage Christian Daycare | 18790 | 13153 | 420 | 420 | 2019-08-30 | 12/2/19 RNBProject Status- Client waiting for site approvalDate invoice is expected to be issued: 12-10-19Projected amount of next invoice: $ 3,300 ( 90% of fee)WIP Category( E,F,G): EInvoice to be sent this month for 90% and CO to be requested discussed with client week of 12-2. | [6 empty] | N |  | N
45 | MEP | Blanch, Richard | 19-174-2232 | 1 |  |  |  |  | 420
46 | MEP | Blanch, Richard | 19-193-0195 |  | National Grid - HUB RTU Scoping | 7985 | 0 | 6566 | 5667 |  | 12/2/19 RNBProject Status- In ConstructionDate invoice is expected to be issued: 12-27-19Projected amount of next invoice: Clear all WIPWIP Category (E, F, G): G | [6 empty] | N |  | N
47 | MEP | Blanch, Richard | 19-193-0195 | 1 |  |  |  |  | 5667
Total |  |  |  |  | 94203 | 143719 |  |  | 15968 | 19007