## PHR WITH WIP & AR
[7 empty] | Boston CM : WIP and AR Tracking |  |  |  | 2019-12-16 |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Project Name | Contract Amount | LiRo Billed Fee | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Boston CM | Kovacs, Steve | 15-374-1807 |  | Mayo Reg. Hosp. Patient Floor/MEP | 488475 | 417227 | 17014 | 2843 | 2019-04-24 | KB 11/13/19-Letter was sent to client on 11/8 outlining the proposed plan to address mech issues. Pending Client approval. (Estimated cost for repairs is $180K. We expect the open AR to be paid once mech. units are performing properly).10/24/19-The roof top mechanical unit is not performing to the spec and the client wants repairs/replacement for the unit. Todd Chase submitted options to the client for their review and approval.(one-repair/one-replacement) We are at risk fo the open AR of $147K and the open WIP of $14K. In addition we are at risk for any costs associated witht he repair/replacement of the unit plus open punch list items. repair est at $70K and replacement at $200K. |  | 146173 |  |  |  |  | N |  | Y
2 | Boston CM | Kovacs, Steve | 15-374-1807 | 17010 |  |  |  |  | 253
3 | Boston CM | Kovacs, Steve | 15-374-1807 | 19010 |  |  |  |  | 1150
4 | Boston CM | Kovacs, Steve | 15-374-1807 | ACSUPP |  |  |  |  | 1440
5 | Boston CM | Kovacs, Steve | 15-374-1807 | [10 empty] | 146172.79 | MB-000002253 | 2018-01-31 | KB 11/13/19-Letter was sent to client on 11/8 outlining the proposed plan to address mech issues. Pending Client approval. (Estimated cost for repairs is $180K. We expect the open AR to be paid once mech. units are performing properly).10/24/19-The roof top mechanical unit is not performing to the spec and the client wants repairs/replacement for the unit. Todd Chase submitted options to the client for their review and approval.(one-repair/one-replacement) We are at risk fo the open AR of $147K and the open WIP of $14K. In addition we are at risk for any costs associated witht he repair/replacement of the unit plus open punch list items. repair est at $70K and replacement at $200K.
6 | Boston CM | Kovacs, Steve | 15-375-1835 |  | RFGH - Add/Reno | 902575 | 879081 | 0 | 0 | 2018-01-31 | 11/16/19 Client is holding payment until mechanical issues with Pharmacy are resolved. AR of $63K is at RISK as client does not want us to make repairs, they want a check for repairs to be done by others. We are also at risk for any costs that are negotiated to make repairs by others. Steve Kovacs is reaching out to the client for documentation as to what they are looking for in reference to costs for the repairs. |  | 47145 |  |  |  |  | N |  | Y
7 | Boston CM | Kovacs, Steve | 15-375-1835 | [10 empty] | 47145 | MB-000002252 | 2018-01-31 | 11/16/19 Client is holding payment until mechanical issues with Pharmacy are resolved. AR of $63K is at RISK as client does not want us to make repairs, they want a check for repairs to be done by others. We are also at risk for any costs that are negotiated to make repairs by others. Steve Kovacs is reaching out to the client for documentation as to what they are looking for in reference to costs for the repairs.
8 | Boston CM | Kovacs, Steve | 16-454-1815 |  | PMB Cap Inv - Growth Facility | 386440 | 275474 | 0 | 0 | 2019-10-25 | 11/19/19-SK advised that DG overbilled the client in the amount of $14K |  | 1949 |  |  |  |  | N |  | N
9 | Boston CM | Kovacs, Steve | 16-454-1815 | [10 empty] | -6892.22 | MB-000002303 | 2019-01-23 | 11/19/19- after the adjustment for the 50% reduction in the AR of $47,477 the total AR is $31,891.90 and Steve Kovacs is working on collection.
10 | Boston CM | Kovacs, Steve | 16-454-1815 | [10 empty] | 8841.41 | MB-000002354 | 2019-05-14 | 11/19/19- after the adjustment for the 50% reduction in the AR of $47,477 the total AR is $31,891.90 and Steve Kovacs is working on collection.
11 | Boston CM | Kovacs, Steve | 19-093-1818 |  | SHC Brockton ASC Reno | 233900 | 26837 | 12995 | 7089 | 2019-06-21 | 11/19/19-Steve Kovacks reviewing the status of the project to see if it has re-started. | [6 empty] | N |  | N
12 | Boston CM | Kovacs, Steve | 19-093-1818 | 1 |  |  |  |  | 4887
13 | Boston CM | Kovacs, Steve | 19-093-1818 | 2 |  |  |  |  | 183
14 | Boston CM | Kovacs, Steve | 19-093-1818 | 3 |  |  |  |  | 2019
Total | [5 empty] | 2011390 | 1598619 | 30009 | 9932 | [6 empty] | 0 | 195267