## PHR WITH WIP & AR
[7 empty] | Boston MEP : WIP and AR Tracking |  |  | 2019-12-13 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/10/2019 | WIP > 60 as of 12/10/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Boston MEP | Chase, Todd | 18-106-1826 |  | Lincoln/Haney - Sara Pepper | 13300 | 10300 | 5756 | 5756 | 2019-08-31 | JP 11/7/19 - this WIP needs to be written off - project is not moving forward and was over run.JP 10/21/19 - no change on this - this project is not moving forward and was overrun and needs to be wriiten offJP 9/16/19 - same as previous note - this needs to be written off as this project was overrun and the project is not moving forward.JP 8/20/19 Voided this invoice waiting for it to be posted by LiRo - the outstanding WIP will need to be written off as this project was over run and no where to bill this time. Multiplier is approxx 2.24 with the W/o after invoice is posted.W/O will be approx $5,800.00JP 4/9 - spoke to Todd Chase - this project is just going to bid - waiting for CA to start before this can be billed | [6 empty] | N |  | N
2 | Boston MEP | Chase, Todd | 18-106-1826 | CONDOC |  |  |  |  | 5756
3 | Boston MEP | Chase, Todd | 19-112-1824 |  | UMass Burbank Campus Steam Pressure Redu | 52500 | 35265 | 2585 | 0 | 2019-08-30 |  | 6000 | [5 empty] | N |  | N
Total |  |  |  |  | 8341 | 11512 |  |  | 6000 | 0