## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Burke, Stephen | 13-011-0376 |  | SUCF New Medical and Research Bldg CM | 9599999 | 9899480 | 104802 | 8238 | 2019-10-25 | 10/28/2019: Amendment that includes $501,835 for LiRo staffing in final stage of approval with SUCF. Amendment for execution expected within days. |  | 1 |  |  |  |  | N |  | N
2 | CM | Burke, Stephen | 13-011-0376 | FITOUT |  |  |  |  | 8238
3 | CM | Burke, Stephen | 13-011-0376 | [10 empty] | 0.83 | 00000000018L | 2019-07-15
4 | CM | Burke, Stephen | 17-126-0376 |  | SUCF Downstate Medical-Upgrade UHB Elec | 1875080 | 239948 | 123704 | 59250 | 2019-08-30 |  | 27182 | [5 empty] | N |  | N
5 | CM | Burke, Stephen | 17-126-0376 | BRANCH |  |  |  |  | 55964 |  | project will not start until 2018
6 | CM | Burke, Stephen | 17-126-0376 | PRECON |  |  |  |  | 3286
7 | CM | Burke, Stephen | 18-212-1934 |  | College of New Rochelle-Envelope Repairs | 144556 | 23520 | 0 | 0 | 2019-04-26 |  |  | 19992 |  |  |  |  | N |  | N
8 | CM | Burke, Stephen | 18-212-1934 | [10 empty] | 19992 | 00000000002A | 2019-05-13 | 10/28/19: Invoice 1 paid. Balance subject to proceeds of bankruptcy sale.
9 | CM | Burke, Stephen | 19-015-0376.01 |  | SUNY Downstate Med Ctr Isolation/Oper Rm | 763400 | 0 | 50343 | 36520 |  | 10/28/19: There is nothing restricting submission of an invoice. | [6 empty] | N |  | N
10 | CM | Burke, Stephen | 19-015-0376.01 | 1 |  |  |  |  | 36520
11 | CM | Burke, Stephen | 19-082-0093 |  | Columbia University CM Svcs Lerner Hall | 60000 | 0 | 38591 | 38591 | 2019-08-31 | 10/28/19: Phase 1 of lump sum contract complete. Invoice to be submitted week of 10/28. | [6 empty] | N | 2018-12-03 | N
12 | CM | Burke, Stephen | 19-082-0093 | 1 |  |  |  |  | 36693
13 | CM | Burke, Stephen | 19-082-0093 | 2 |  |  |  |  | 1563
14 | CM | Burke, Stephen | 19-082-0093 | 3 |  |  |  |  | 336
Total |  |  |  |  | 317440 | 285199 |  |  | 27182 | 19993