## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Caggiano, Anthony | 16-018-0271 |  | NYCDOS On-Call Services Reno & Rehab | 6420648 | 3849129 | 1036030 | 940059 | 2019-10-31 | 12/15/2019 AR $ 1.3M (51 Invoices), includes cuts (12 invoices) @$ 127K , awaiting response- DSNY has requested we incorp billing into 4 invoices by year, working on details currently. WIP $ 360K, with $ 188 awaiting supplementals, $ 60K + current pay to be billed after 10/25 pay, estimate $ 100K - $200K possible loss. | 136339 | 640681 |  |  |  |  | N |  | Y
2 | CM | Caggiano, Anthony | 16-018-0271 | 1 |  |  |  |  | 6559
3 | CM | Caggiano, Anthony | 16-018-0271 | 2.1 |  |  |  |  | 18693
4 | CM | Caggiano, Anthony | 16-018-0271 | 3 |  |  |  |  | 9351
5 | CM | Caggiano, Anthony | 16-018-0271 | 4 |  |  |  |  | 18027
6 | CM | Caggiano, Anthony | 16-018-0271 | 6 |  |  |  |  | 128678
7 | CM | Caggiano, Anthony | 16-018-0271 | 7 |  |  |  |  | 3049
8 | CM | Caggiano, Anthony | 16-018-0271 | 8 |  |  |  |  | 142262
9 | CM | Caggiano, Anthony | 16-018-0271 | 9 |  |  |  |  | 1294
10 | CM | Caggiano, Anthony | 16-018-0271 | 10 |  |  |  |  | 1294
11 | CM | Caggiano, Anthony | 16-018-0271 | 11 |  |  |  |  | 899
12 | CM | Caggiano, Anthony | 16-018-0271 | 12 |  |  |  |  | 2606
13 | CM | Caggiano, Anthony | 16-018-0271 | 13 |  |  |  |  | 1264
14 | CM | Caggiano, Anthony | 16-018-0271 | 14 |  |  |  |  | 1254
15 | CM | Caggiano, Anthony | 16-018-0271 | 15 |  |  |  |  | 899
16 | CM | Caggiano, Anthony | 16-018-0271 | 16 |  |  |  |  | 30587
17 | CM | Caggiano, Anthony | 16-018-0271 | 17 |  |  |  |  | 397
18 | CM | Caggiano, Anthony | 16-018-0271 | 19 |  |  |  |  | 72475
19 | CM | Caggiano, Anthony | 16-018-0271 | 20 |  |  |  |  | 1162
20 | CM | Caggiano, Anthony | 16-018-0271 | 21 |  |  |  |  | 2696
21 | CM | Caggiano, Anthony | 16-018-0271 | 22 |  |  |  |  | 336
22 | CM | Caggiano, Anthony | 16-018-0271 | 23 |  |  |  |  | 8440
23 | CM | Caggiano, Anthony | 16-018-0271 | 24 |  |  |  |  | 6860
24 | CM | Caggiano, Anthony | 16-018-0271 | 25 |  |  |  |  | 4622
25 | CM | Caggiano, Anthony | 16-018-0271 | 26 |  |  |  |  | 115909
26 | CM | Caggiano, Anthony | 16-018-0271 | 27 |  |  |  |  | 13522
27 | CM | Caggiano, Anthony | 16-018-0271 | 30 |  |  |  |  | 3197
28 | CM | Caggiano, Anthony | 16-018-0271 | 30.A |  |  |  |  | 7511
29 | CM | Caggiano, Anthony | 16-018-0271 | 34 |  |  |  |  | 422
30 | CM | Caggiano, Anthony | 16-018-0271 | 35 |  |  |  |  | 1895
31 | CM | Caggiano, Anthony | 16-018-0271 | 35.1 |  |  |  |  | 2134
32 | CM | Caggiano, Anthony | 16-018-0271 | 36 |  |  |  |  | 1945
33 | CM | Caggiano, Anthony | 16-018-0271 | 38 |  |  |  |  | 1593
34 | CM | Caggiano, Anthony | 16-018-0271 | 38.1 |  |  |  |  | 1344
35 | CM | Caggiano, Anthony | 16-018-0271 | 39 |  |  |  |  | 4664
36 | CM | Caggiano, Anthony | 16-018-0271 | 41 |  |  |  |  | 4331
37 | CM | Caggiano, Anthony | 16-018-0271 | 42 |  |  |  |  | 221559
38 | CM | Caggiano, Anthony | 16-018-0271 | 43 |  |  |  |  | 1563
39 | CM | Caggiano, Anthony | 16-018-0271 | 46 |  |  |  |  | 3976
40 | CM | Caggiano, Anthony | 16-018-0271 | 46.1 |  |  |  |  | 1500
41 | CM | Caggiano, Anthony | 16-018-0271 | 47 |  |  |  |  | 533
42 | CM | Caggiano, Anthony | 16-018-0271 | 48 |  |  |  |  | 3338
43 | CM | Caggiano, Anthony | 16-018-0271 | 49 |  |  |  |  | 6729
44 | CM | Caggiano, Anthony | 16-018-0271 | 50 |  |  |  |  | 296
45 | CM | Caggiano, Anthony | 16-018-0271 | 50.1 |  |  |  |  | 5224
46 | CM | Caggiano, Anthony | 16-018-0271 | 51 |  |  |  |  | 393
47 | CM | Caggiano, Anthony | 16-018-0271 | 52A |  |  |  |  | 9340
48 | CM | Caggiano, Anthony | 16-018-0271 | 53 |  |  |  |  | 336
49 | CM | Caggiano, Anthony | 16-018-0271 | 55 |  |  |  |  | 336
50 | CM | Caggiano, Anthony | 16-018-0271 | 57 |  |  |  |  | 336
51 | CM | Caggiano, Anthony | 16-018-0271 | 58 |  |  |  |  | -910
52 | CM | Caggiano, Anthony | 16-018-0271 | 59 |  |  |  |  | 4728
53 | CM | Caggiano, Anthony | 16-018-0271 | 61 |  |  |  |  | 8237
54 | CM | Caggiano, Anthony | 16-018-0271 | 64 |  |  |  |  | 3566
55 | CM | Caggiano, Anthony | 16-018-0271 | 65 |  |  |  |  | 2947
56 | CM | Caggiano, Anthony | 16-018-0271 | 66 |  |  |  |  | 361
57 | CM | Caggiano, Anthony | 16-018-0271 | 68 |  |  |  |  | 99
58 | CM | Caggiano, Anthony | 16-018-0271 | 70 |  |  |  |  | 9274
59 | CM | Caggiano, Anthony | 16-018-0271 | 71 |  |  |  |  | 366
60 | CM | Caggiano, Anthony | 16-018-0271 | 74 |  |  |  |  | -294
61 | CM | Caggiano, Anthony | 16-018-0271 | 77 |  |  |  |  | 236
62 | CM | Caggiano, Anthony | 16-018-0271 | 79 |  |  |  |  | 404
63 | CM | Caggiano, Anthony | 16-018-0271 | 80 |  |  |  |  | 634
64 | CM | Caggiano, Anthony | 16-018-0271 | 83 |  |  |  |  | 1190
65 | CM | Caggiano, Anthony | 16-018-0271 | 84 |  |  |  |  | 18052
66 | CM | Caggiano, Anthony | 16-018-0271 | 85 |  |  |  |  | 1818
67 | CM | Caggiano, Anthony | 16-018-0271 | 89 |  |  |  |  | 648
68 | CM | Caggiano, Anthony | 16-018-0271 | 90 |  |  |  |  | 79
69 | CM | Caggiano, Anthony | 16-018-0271 | 92 |  |  |  |  | 315 |  | 6/15/19- Bill Crinnion has taken over the Invoicing and financial review and is working directly with Allanson Prescot of Sanitation. We are at risk for approx $100K in Cuts and $25K in WIP/AR with no supplementals.
70 | CM | Caggiano, Anthony | 16-018-0271 | 93 |  |  |  |  | 10533 |  | 8/26/19-LT and JM met with Asst Commissioner; old work orders are now registered and invoices being processed. All cuts are being resubmitted review and discussions with EOA. New Contract in the amount of $6.6?? is with Comptrollers Office. We are at risk for approx $100K in Cuts and $75K in WIP/AR with no supplementals or required back-up documentation.
71 | CM | Caggiano, Anthony | 16-018-0271 | 94 |  |  |  |  | 146 |  | 8/26/19-LT and JM met with Asst Commissioner; old work orders are now registered and invoices being processed. All cuts are being resubmitted review and discussions with EOA. New Contract in the amount of $6.6?? is with Comptrollers Office. We are at risk for approx $100K in Cuts and $75K in WIP/AR with no supplementals or required back-up documentation.
72 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 15915.17 | 2 | 2017-05-18
73 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 5438 | 00000007-WO8 | 2018-08-10
74 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 89489.48 | 00000009-TO6 | 2019-07-05
75 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 67587.24 | 00000009-WO8 | 2019-05-10
76 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 5237.8 | 0000001-TO23 | 2019-06-17
77 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 12531.11 | 0000001-WO18 | 2019-04-24
78 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 5315 | 0000001-WO20 | 2018-08-07
79 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 6400.8 | 0000001-WO24 | 2018-07-11
80 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 4622.1 | 0000001-WO25 | 2019-04-29
81 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 6720 | 0000001-WO27 | 2018-10-22 | DSNY cut Caggaino 40 hours , noting they s/b rebilled, should be rebilled
82 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 3378.06 | 0000001-WO39 | 2019-04-25
83 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 394.86 | 0000001-WO48 | 2018-06-27
84 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 2909.75 | 0000001-WO57 | 2019-04-25
85 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 25834.62 | 0000001-WO61 | 2019-01-31
86 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 9263.65 | 0000001-WO70 | 2019-04-25
87 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 168.28 | 0000001-WO78 | 2019-03-06
88 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 17375.53 | 0000001-WO84 | 2019-05-13
89 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 5521.57 | 0000001-WO89 | 2019-07-31
90 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 2532.81 | 0000002-WO12 | 2019-04-24
91 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | -1152.54 | 0000002-WO23 | 2018-07-11
92 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 99677.7 | 0000002-WO42 | 2019-05-15
93 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 5292.6 | 0000004-WO-8 | 2018-03-01
94 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 44610.55 | 0000004-WO74 | 2019-08-14
95 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | -5238.4 | 000001-TO.23 | 2017-11-30 | Invoice should be voided , together with 1-WO23
96 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 120958.82 | 000001-WO2.1 | 2019-05-10
97 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 7434 | 000001-WO29A | 2019-03-08
98 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 7488.52 | 000001-WO30A | 2019-03-08
99 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 5431.32 | 00000TO6INV3 | 2017-07-01
100 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 29632.48 | 00000WO6INV1 | 2017-03-29
101 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 7665 | 00000WO8INV6 | 2018-08-08
102 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 1400 | 00001-WO36.1 | 2018-07-02
103 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 3786 | 00002-TO50.1 | 2019-07-18
104 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 4821.44 | 0000INV6-WO6 | 2018-05-28
105 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 3458.27 | 0000WO6-INV5 | 2018-03-15
106 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 9239.99 | 0000WO8-INV5 | 2018-03-15
107 | CM | Caggiano, Anthony | 16-018-0271 | [10 empty] | 9539.75 | 000WO43-INV1 | 2018-09-26
108 | Env | Caggiano, Anthony | 10-88-205.01 |  | DESIGN BUILD FOR REMOVAL/UPGRADE/REPLACE | 1269603 | 1071235 | 0 | 0 | 2015-04-17 |  |  | 53553 |  |  |  |  | N |  | N
109 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 872.97 | 1 | 2011-01-20 | SZ12/4/19 Per Tony he has not heard back from NYCDDC regaring his proposal. He spoke with Lou & Joe and stated if he does not get a response by end of year he will put in a claim.SZ 11/8/2019 Per tony today he proposed to NYCDDC that they pay 92% of total invoice leaving the 4 sites open that are in dispute. He expects to know there decision Nov 20th.
110 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 879.73 | 2 | 2011-05-11
111 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 722.48 | 3 | 2011-03-11
112 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 559.76 | 4 | 2011-04-01
113 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 78.31 | 4 | 2011-08-04
114 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 858.87 | 5 | 2011-05-12
115 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 697.14 | 6 | 2011-05-27
116 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 778.36 | 7 | 2011-07-11
117 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 820.55 | 8 | 2011-08-01
118 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 51.99 | 8 | 2011-10-06
119 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1025.17 | 9 | 2011-10-03
120 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1943.37 | 10 | 2011-11-01
121 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1307.44 | 11 | 2011-11-29
122 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1101.68 | 12 | 2011-12-20
123 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 34.19 | 12 | 2012-01-23
124 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1621.82 | 13 | 2012-01-16
125 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1329.02 | 14 | 2012-02-09
126 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1400.71 | 15 | 2012-03-07
127 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1998.67 | 16 | 2012-04-02
128 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1921.92 | 17 | 2012-05-09
129 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 422.52 | 17 | 2012-07-16
130 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 2281.17 | 18 | 2012-06-07
131 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1952.91 | 19 | 2012-07-12
132 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 484.69 | 20 | 2012-09-21
133 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 3277.62 | 20 | 2012-08-10
134 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 2046.25 | 21 | 2012-09-13
135 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 443 | 21 | 2012-12-12
136 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 398.31 | 22 | 2012-12-12
137 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1375.78 | 22 | 2012-10-08
138 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 25.21 | 23 | 2013-06-07
139 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 2737.24 | 23 | 2012-11-30
140 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1527.92 | 24 | 2013-01-07
141 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 3479.29 | 25 | 2013-03-15
142 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 4103.38 | 26 | 2013-04-24
143 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1913.74 | 27 | 2013-05-24
144 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | -11.32 | 27 | 2013-06-27
145 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 1187.75 | 28 | 2013-06-21
146 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 869.85 | 29 | 2013-07-16
147 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 886.72 | 30 | 2013-08-12
148 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 840.06 | 31 | 2013-09-09
149 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 521.14 | 32 | 2013-09-27
150 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 444.82 | 33 | 2013-10-11
151 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 371.47 | 34 | 2013-11-20
152 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 328.77 | 35 | 2013-12-19
153 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 249.49 | 36 | 2014-01-17
154 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 223.39 | 37 | 2014-02-27
155 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 212.21 | 38 | 2014-03-14
156 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 279.63 | 39 | 2014-07-22
157 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 6.6 | 39 | 2015-05-07
158 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 165 | 40 | 2014-08-20
159 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 228.08 | 41 | 2014-09-18
160 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 100.03 | 42 | 2014-11-03
161 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 59.4 | 44 | 2015-03-18
162 | Env | Caggiano, Anthony | 10-88-205.01 | [10 empty] | 116.93 | 45 | 2015-04-30
163 | Env | Caggiano, Anthony | 10-88-205.02 |  | CM BUILD FOR REMOVAL/UPGRADE/REPLACE | 2873049 | 3077522 | 0 | 0 | 2018-11-23 |  |  | 157956 |  |  |  |  | N |  | N
164 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 621.02 | 1 | 2011-01-20 | SZ12/4/19 Per Tony he has not heard back from NYCDDC regaring his proposal. He spoke with Lou & Joe and stated if he does not get a response by end of year he will put in a claim.SZ 11/8/2019 Per tony today he proposed to NYCDDC that they pay 92% of total invoice leaving the 4 sites open that are in dispute. He expects to know there decision Nov 20th.
165 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2229.83 | 1 | 2011-10-03 | SZ12/4/19 Per Tony he has not heard back from NYCDDC regaring his proposal. He spoke with Lou & Joe and stated if he does not get a response by end of year he will put in a claim.SZ 11/8/2019 Per tony today he proposed to NYCDDC that they pay 92% of total invoice leaving the 4 sites open that are in dispute. He expects to know there decision Nov 20th.
166 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 1919.27 | 2 | 2011-02-16
167 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 1640.55 | 3 | 2011-03-11
168 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 1866.92 | 4 | 2011-04-01
169 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 1968.89 | 5 | 2011-05-12
170 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2196.35 | 6 | 2011-05-27
171 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2800.61 | 7 | 2011-07-11
172 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2495.21 | 8 | 2011-08-01
173 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2936.08 | 9 | 2011-10-07
174 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 5114.36 | 10 | 2011-11-01
175 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2809.12 | 11 | 2011-11-29
176 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2842.79 | 12 | 2011-12-21
177 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2847.45 | 13 | 2012-01-16
178 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 3262.34 | 14 | 2012-02-09
179 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4437.8 | 15 | 2012-03-07
180 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4351.17 | 16 | 2012-04-02
181 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4983.65 | 17 | 2012-05-09
182 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 5243.6 | 18 | 2012-06-07
183 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4346.78 | 19 | 2012-07-12
184 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 9086.83 | 20 | 2012-08-10
185 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4684.11 | 21 | 2012-09-13
186 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4773.29 | 22 | 2012-10-08
187 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 5336.89 | 23 | 2012-11-30
188 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4533.21 | 24 | 2013-01-07
189 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 5098.46 | 25 | 2013-03-15
190 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 9677.69 | 26 | 2013-04-24
191 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 5157.89 | 27 | 2013-05-24
192 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 5956.8 | 28 | 2013-06-24
193 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4419.8 | 29 | 2013-07-16
194 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4439.33 | 30 | 2013-08-12
195 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2952.51 | 31 | 2013-09-09
196 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2635.07 | 32 | 2013-09-27
197 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 3366.14 | 33 | 2013-10-11
198 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2677.93 | 34 | 2013-11-20
199 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2277.97 | 35 | 2013-12-19
200 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2189.25 | 36 | 2014-01-17
201 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2371.56 | 37 | 2014-02-27
202 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 1704.47 | 38 | 2014-03-14
203 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 3534.94 | 39 | 2014-07-22
204 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 2775.48 | 40 | 2014-08-20
205 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 1948.91 | 41 | 2014-09-18
206 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 492.35 | 42 | 2014-11-03
207 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 239.78 | 43 | 2015-02-02
208 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 293.53 | 44 | 2015-03-18
209 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 120.5 | 45 | 2015-04-30
210 | Env | Caggiano, Anthony | 10-88-205.02 | [10 empty] | 4297.32 | 46 | 2018-12-13
211 | Env | Caggiano, Anthony | 12-149-0265.1 |  | NYCDDC City Owned Heating Oil Tank Desig | 2287947 | 1497102 | 4149 | 4149 | 2019-09-30 | 9/3/2019 - Change order is still with NYCDDC. He stated this takes months to go thru all the channels. he expects it to be done and LiRo to start invoicing mid December 2019. | [6 empty] | N |  | N
212 | Env | Caggiano, Anthony | 12-149-0265.1 | DESIGN |  |  |  |  | 4149 |  | 9/3/2019 - Change order is still with NYCDDC. He stated this takes months to go thru all the channels. he expects it to be done and LiRo to start invoicing mid December 2019.
213 | Env | Caggiano, Anthony | 12-149-0265.2 |  | NYCDDC City Owned Heating Oil Tank CM | 4954100 | 3201157 | 227710 | 227710 | 2018-08-31 | 9/3/2019 - Change order is still with NYCDDC. He stated this takes months to go thru all the channels. he expects it to be done and LiRo to start invoicing mid December 2019. | [6 empty] | N |  | N
214 | Env | Caggiano, Anthony | 12-149-0265.2 | CM |  |  |  |  | 227710
215 | Env | Caggiano, Anthony | 15-005-0265.01 |  | NYCDDC Remediation and Monitoring Tanks | 4700000 | 4700014 | 396333 | 238080 | 2019-11-30 | 11/11/19 - SZ based on call the change order is with comptrollers office and expected to take a few more weeks. 11/5/19: st for Proios -- John has a conference call set up for Friday -- Nov. 8th. Hoping to get status of Changeorder at that time. 10/24- st -- No change in status. Still waiting for changeorder to be approved.10/9/19: ST for Proios: waiting for Changeorder 5 for staffing to be approved WIP expected to be cleared November. | [6 empty] | N |  | N
216 | Env | Caggiano, Anthony | 15-005-0265.01 | DESIGN |  |  |  |  | 238080
217 | Env | Caggiano, Anthony | 15-005-0265.02 |  | NYCDDC Remediation and Monitoring Tanks | 2600000 | 2567795 | 217021 | 136086 | 2019-07-19 | 11/11/19 - SZ based on call the change order is with comptrollers office and expected to take a few more weeks.11/5/19: st for Proios -- John has a conference call set up for Friday -- Nov. 8th. Hoping to get status of Changeorder at that time.10/24/19 - no change.10/9/19: ST for Proios: waiting for Changeorder 5 for staffing to be approved WIP expected to be cleared in November | [6 empty] | N |  | N
218 | Env | Caggiano, Anthony | 15-005-0265.02 | CM |  |  |  |  | 136086
219 | Env | Caggiano, Anthony | 15-005-0265.02 | [10 empty] | -0.03 | 39 | 2019-06-27
220 | Env | Caggiano, Anthony | 15-017-0265 |  | Engine Company 293 Redesign of Diesel | 30172 | 23927 | 3349 | 3349 | 2018-11-14 | 11/15/19-This WIP is at Risk as the work was performed without a task order. 10/11/19 SZ email Bob K. on hours on WIP - Bob is call ing client and seeing if there is anything he can do for them to accept a change order. Bob was not involved in job but will give it a shot. | [6 empty] | N |  | N
221 | Env | Caggiano, Anthony | 15-017-0265 | DSGN |  |  |  |  | 3349
Total |  |  |  |  | 1884592 | 3098866 |  |  | 136339 | 852190