## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Boston Architectural | Chase, Todd | 15-376-1807 |  | Mayo Regional - Patient Floor/MEP | 749310 | 349859 | 37637 | 32439 | 2019-09-13 | 12/2/19-Todd and Kovacs are working on getting pricing for requried repairs. LiRo is at Risk for WIP of $30,332 and up to potentially $150K for the replacement of the roof top unit. 8/21/19-Brian advised that until the mechanical issue with the rooftop ERV unit is settled (Al is also assisting) the WIP cannot be billed and pending the outcome of the mechanical issue this time is at Risk. | [6 empty] | N |  | Y
2 | Boston Architectural | Chase, Todd | 15-376-1807 | ADDSVC |  |  |  |  | 1400
3 | Boston Architectural | Chase, Todd | 15-376-1807 | CONST |  |  |  |  | 24536
4 | Boston Architectural | Chase, Todd | 15-376-1807 | MEPD/C |  |  |  |  | 6928
5 | Boston Architectural | Chase, Todd | 15-376-1807 | ONSITE |  |  |  |  | -425
6 | Boston MEP | Chase, Todd | 18-106-1826 |  | Lincoln/Haney - Sara Pepper | 13300 | 10300 | 5756 | 5756 | 2019-08-31 | JP 11/7/19 - this WIP needs to be written off - project is not moving forward and was over run.JP 10/21/19 - no change on this - this project is not moving forward and was overrun and needs to be wriiten offJP 9/16/19 - same as previous note - this needs to be written off as this project was overrun and the project is not moving forward.JP 8/20/19 Voided this invoice waiting for it to be posted by LiRo - the outstanding WIP will need to be written off as this project was over run and no where to bill this time. Multiplier is approxx 2.24 with the W/o after invoice is posted.W/O will be approx $5,800.00JP 4/9 - spoke to Todd Chase - this project is just going to bid - waiting for CA to start before this can be billed | [6 empty] | N |  | N
7 | Boston MEP | Chase, Todd | 18-106-1826 | CONDOC |  |  |  |  | 5756
8 | Boston MEP | Chase, Todd | 19-112-1824 |  | UMass Burbank Campus Steam Pressure Redu | 52500 | 35265 | 2585 | 0 | 2019-08-30 |  | 6000 | [5 empty] | N |  | N
Total |  |  |  |  | 45978 | 76390 |  |  | 6000 | 0