## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Choudhury, Faisal | 12-120-0270 |  | NYCDPR 2013 Street Tree Planting CS | 483960 | 454811 | 0 | 0 | 2018-08-31 |  |  | 46756 |  |  |  |  | N |  | N
2 | CM | Choudhury, Faisal | 12-120-0270 | [10 empty] | 46755.71 | 0000000004R1 | 2018-08-07 | 11/30/19- Fais continues to follow up with the status to confirm when the funds are registered. 10/29/19: Yi-Wen and Nave Strauss are coordinating additional justification for ACCO's Office for processing the Supplemental Work Order..
3 | CM | Choudhury, Faisal | 12-120-0270.05 |  | NYCDPR Parks & Pldgs Brooklyn | 99240 | 17537 | 0 | 0 | 2015-09-30 |  |  | 17537 |  |  |  |  | N |  | Y
4 | CM | Choudhury, Faisal | 12-120-0270.05 | [10 empty] | 16078.5 | 1 | 2015-04-28 | 11/30/19-Fais is following up on the invoice and Supplemental.
5 | CM | Choudhury, Faisal | 12-120-0270.05 | [10 empty] | 1458 | 2 | 2015-08-24 | 8/1/2019FC to meet Chief P. Granitto on 8/9/19 to discuss this pending Supplental Work Order.6/5/2019 FC Funding transfer is being coordinated by Team Leader; Budget codes to follow. 4/15/19-still pending signature from ACCO after that they’ll request for budget codes, then to Comptroller's Office for registration. Budget codes take 2 - 3 months. 9/8/19: David Martin is coordnating the budget codes for the Supplemental Work Order; will receive an update this week.
6 | CM | Choudhury, Faisal | 15-036-0278 |  | NYCHA Whitman Houses | 2473989 | 2465261 | -101 | 466076 | 2019-12-31 | 10/29/19: New Task Order approved by NYCHA under IDIQ Contract for $2,699,379. Invoice to be submitted on week of 11/4/19. | [6 empty] | N |  | N
7 | CM | Choudhury, Faisal | 15-036-0278 | CONSTR |  |  |  |  | 465081
8 | CM | Choudhury, Faisal | 15-036-0278 | STAFF |  |  |  |  | 994
9 | CM | Choudhury, Faisal | 16-076-0270.17 |  | NYCPR - Reconstruct Bloomingdale Plgd | 317400 | 266629 | 17020 | 10293 | 2019-10-31 | [7 empty] | N |  | N
10 | CM | Choudhury, Faisal | 16-076-0270.17 | 1 |  |  |  |  | 10293
11 | CM | Choudhury, Faisal | 16-076-0270.18 |  | NYCPR - Reconstruct Garrison Plgd | 446200 | 221490 | 47955 | 9200 | 2019-09-27 | [7 empty] | N |  | N
12 | CM | Choudhury, Faisal | 16-076-0270.18 | 1 |  |  |  |  | 9200
13 | CM | Choudhury, Faisal | 16-076-0270.19 |  | NYCPR - CM Svcs St Mary's Greenstreets | 134132 | 99612 | 3080 | 1720 | 2019-10-11 |  |  | 6092 |  |  |  |  | N |  | N
14 | CM | Choudhury, Faisal | 16-076-0270.19 | 1 |  |  |  |  | 1720
15 | CM | Choudhury, Faisal | 16-076-0270.19 | [10 empty] | 6092 | 2 | 2019-06-14 | 11/30/19: Corrections to Invoice made on 11/27/19. Massey to resubmit with corrections.
16 | CM | Choudhury, Faisal | 16-080-0270 |  | NYCPR Reconstruct Playground 52 | 262474 | 262469 | 0 | 0 | 2018-10-08 |  |  | 3764 |  |  |  |  | N |  | N
17 | CM | Choudhury, Faisal | 16-080-0270 | [10 empty] | 3764.2 | 12 | 2018-12-18 | 11/30/19: Fais will check with Sakai Brown and Leon Fendley on this invoice. 10/29/19: Fais resubmitted Inv #12 from 12/18/18.
18 | CM | Choudhury, Faisal | 16-080-0270.02 |  | NYCPR Reconstruct Ex. Comfort Stations | 1815328 | 1750320 | 0 | 0 | 2019-01-31 |  |  | 82823 |  |  |  |  | N |  | Y
19 | CM | Choudhury, Faisal | 16-080-0270.02 | [10 empty] | 82823.4 | 00000000013R | 2018-12-18 | 11/30/19-Parks sent a letter stating they did not want to pay the remaining balance of $82K, a LiRo response was sent on 11/20/19. Fais trying to schedule a meeting to finalize.
20 | CM | Choudhury, Faisal | 16-080-0270.07 |  | NYCPR Reconstruct DeMatti Playground | 253675 | 252336 | 0 | 0 | 2018-09-30 |  |  | 1177 |  |  |  |  | N |  | N
21 | CM | Choudhury, Faisal | 16-080-0270.07 | [10 empty] | 1176.68 | 13 | 2018-10-08 | 10/29/19-Ron Woodhouse returned the invoice for corrections on 10/28/19. This will be resubmitted by 11/1/19.
22 | CM | Choudhury, Faisal | 16-080-0270.08 |  | NYCPR Reconstruct McDonald Playground | 296000 | 284622 | 8233 | 7030 | 2018-12-14 | 10/29/19-Fais advises the project is being closed out in Nov and the final invoice will be submitted in Nov. | [6 empty] | N |  | N
23 | CM | Choudhury, Faisal | 16-080-0270.08 | STAFF |  |  |  |  | 7030
24 | CM | Choudhury, Faisal | 16-080-0270.09 |  | NYCPR Reconstruct Levy Playground | 260000 | 249275 | 4753 | 4753 | 2018-11-30 | 10/29/19-Fais advises the project is being closed out in Nov and the final invoice will be submitted in Nov. | [6 empty] | N |  | N
25 | CM | Choudhury, Faisal | 16-080-0270.09 | STAFF |  |  |  |  | 4753
26 | CM | Choudhury, Faisal | 16-080-0270.11 |  | NYCPR Jesse Owens Playground & Mini Pool | 366983 | 578853 | 197834 | 167636 | 2019-02-28 | Supplemental Work Order for $215,878.60 submitted on 10/24/19. | [6 empty] | N |  | N
27 | CM | Choudhury, Faisal | 16-080-0270.11 | STAFF |  |  |  |  | 167636
28 | CM | Choudhury, Faisal | 16-080-0270.12 |  | NYCPR Ten Eyck Playground | 366983 | 297248 | 2532 | 2532 | 2019-02-28 | Supplemental Work Order for $215,878.60 submitted on 10/24/19. | [6 empty] | N |  | N
29 | CM | Choudhury, Faisal | 16-080-0270.12 | STAFF |  |  |  |  | 2532
30 | CM | Choudhury, Faisal | 18-138-0271 |  | DSNY BKLYN Community District 3 Facility | 7410613 | 333736 | 358669 | 185926 | 2019-08-02 | 10/29/19: Next Invoice being coordinated to be submitted by 11/8/19. | 158280 | 33525 |  |  |  |  | N |  | N
31 | CM | Choudhury, Faisal | 18-138-0271 | 2 |  |  |  |  | 185926
32 | CM | Choudhury, Faisal | 18-138-0271 | [10 empty] | 33524.63 | 1 | 2019-01-24 | 11/30/19: Follow up email sent from Joe Massa to Rahul Shah on 11/29/19 Re: EAO deduction. 10/29/19: Pre-Construction invoice #2 is being processed with a deduction of $25,999.06. Notice of Appeal submitted on 10/29/19.
33 | CM | Choudhury, Faisal | 19-009-0270 |  | NYCP&R CM Svcs for Battery Carousel Supp | 24870 | 1980 | 0 | 0 | 2019-09-30 |  | 1210 | [5 empty] | N |  | N
34 | CM | Choudhury, Faisal | 19-117-0278.01 |  | NYCHA-Boiler Replacemnt-Sotomayor Houses | 5549782 | 557466 | 54887 | 0 | 2019-11-30 | 9/8/19: Stephanine Castro and Art Schor are coordinating the first invoice to be submitted by 9/10/19. | 216005 | [5 empty] | N |  | N
35 | CM | Choudhury, Faisal | 19-117-0278.02 |  | NYCHA-Boiler Replacemnt-Taft Houses | 4080108 | 298764 | 224998 | 42484 | 2019-09-27 | [7 empty] | N |  | N
36 | CM | Choudhury, Faisal | 19-117-0278.02 | 1 |  |  |  |  | 42484
37 | CM | Choudhury, Faisal | 19-117-0278.04 |  | NYCHA-Ingersoll Exter Reno Contract 2 | 3826218 | 0 | 94926 | 16818 |  | Stephanie Castro will upload invoice to e-builder on 8/2/19 | [6 empty] | N |  | N
38 | CM | Choudhury, Faisal | 19-117-0278.04 | 1 |  |  |  |  | 16818
39 | CM | Choudhury, Faisal | 19-217-0271 |  | DSNY Bronx District 9, 10, 11 Facility | 14384757 | 0 | 145517 | 90932 | [8 empty] | N |  | N
40 | CM | Choudhury, Faisal | 19-217-0271 | 1 |  |  |  |  | 87522
41 | CM | Choudhury, Faisal | 19-217-0271 | 2 |  |  |  |  | 3410
Total |  |  |  |  | 1160303 | 2010799 |  |  | 375495 | 191674