## PHR WITH WIP & AR
[7 empty] | Design : WIP and AR Tracking |  |  |  | 2019-12-16 |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Project Name | Contract Amount | LiRo Billed Fee | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Capobianco, Michael | 18-297-0078 |  | Glen Cove-2018/2019 Road Improvements | 259600 | 214797 | 37296 | 70 | 2019-10-25 | 904.05.2019 CapobiancoM: Invoicing monthly, no delay in invoicing, next invoice w/o4/8/19.04/08/19-MessinaS - Inv P/E 3/29/19 sent out.05/15/2019- MessinaS-Inv P/E 05/06/19- Mike to deliver.06/28/19-MessinaS-Inv P/e 05/31/19 sent out. | [6 empty] | N |  | N
2 | Design | Capobianco, Michael | 18-297-0078 | 2 |  |  |  |  | -372
3 | Design | Capobianco, Michael | 18-297-0078 | 3 |  |  |  |  | 0
4 | Design | Capobianco, Michael | 18-297-0078 | 5 |  |  |  |  | 442
5 | Design | Castagna, Joseph | 08-100-0712 |  | PATCHOGUE CDA/RECONSTRUCT STREETS 2008 | 401700 | 240600 | 81126 | 74345 | 2019-01-04 | 12/6/19 Castagna J - no news on approval of additional fee. Joe will contact Village and inquire. Next update will be 12/6/19. Historical Info to remain:11/22/19 Castagna J - proposal ($113,400) submitted to Village on 11/6/19. I discussed status of approval with Mayor on 11/14. Said it was being reviewed for processing. Next update will be 12/6/19. | [6 empty] | N |  | N
6 | Design | Castagna, Joseph | 08-100-0712 | 440 |  |  |  |  | 74345
7 | Design | Castagna, Joseph | 09-78-0666 |  | GCPW/GARVIES PT-HERB HILL DET CSS | 236710 | 206079 | 261501 | 234803 | 2019-09-30 | 12/6/19 - Castagna J - left voicemail message with H2M on 12/4/19 requesting update on status of execution of sub agreement. Emailed GF today to request update. Awaiting response to both. Next update 12/20/19.Historical notes to remain:11/22/19 Castagna J - Disputes with GF resolved. Awaiting execution of sub agreement. Joe C again emailed H2M on 11/15 and left voicemail with PM for status update, but no response. Associate of PM said that he has been out. May be back on 11/26. I asked him to please ask PM to call me with info. Next update will be 12/6/19.10/30/19 Castagna J - Al Bereche has a tentative tel meeting with GF legal to discuss disputes in the agreement language. Joe C emailed H2M legal counsel on 10/29 to request update on status of the agreement execution (H2M PM on vacation until 11/11). Next update will be 11/8/19.10/14/19 - Castagna J - PS&S executed agreement & checklist signed by Mike S on 9/27/19. Revised agreements returned to GF on 9/17/19 and to H2M on 9/18/19. GF COI ok, H2M COI still needs correction. GF has disputed insurance requirement comments by LiRo on 9/30/19. Legal reviewing dispute. Next update will be 10/25/19.9/13/19 - Castagna J -No Cost Supplemental via transfer from three subs to LiRo fee in the amount of $274K pending sub agreement execution and client approval of transfer. PS&S agreement completed. Received comments on sub agreement from H2M and forwarded to Legal on 9/9/19. Waiting for LiRo legal to complete review of red-lined agreement from GF. Upon submission of executed subagreements to Glen Cove, Director of Public Works should be able to approve LiRo Supplemental Agreement within a day or two. Upon approval we will bill open WIP. Next update will be 9/27/19. | [6 empty] | N |  | N
8 | Design | Castagna, Joseph | 09-78-0666 | 801 |  |  |  |  | 234803
9 | Design | Castagna, Joseph | 16-430-0383 |  | SCPW/IMPROVEMENTS TO CR40 | 473538 | 37995 | 24420 | 46955 | 2019-11-22 | 12/6/19 - Castagna J - Invoice for $138,004 was submitted on December 2, 2019. Cover letter explains how PWR are calculated. Joe C will call County next week to inquire on progress of processing the invoice. The overrun of $17,543 is in preliminary survey work that was estimated very low on original Bowne proposal. Most of this work was completed in 2017, prior to the acquisition. Next update will be 12/20/19.12/2/19-Joe Castagna advised that the WIP of $17,543 is an overrun and at Risk. Joe is following up with Eisman to see if there is anything that can be done. | [6 empty] | N |  | Y
10 | Design | Castagna, Joseph | 16-430-0383 | 200 |  |  |  |  | 24014
11 | Design | Castagna, Joseph | 16-430-0383 | 201 |  |  |  |  | 22111
12 | Design | Castagna, Joseph | 16-430-0383 | 203 |  |  |  |  | 1302
13 | Design | Castagna, Joseph | 16-430-0383 | 204 |  |  |  |  | -472
14 | Design | Castagna, Joseph | 17-006-0248 |  | NCDPW Mission 17-Resurfacing various | 130000 | 130000 | 0 | 0 | 2017-10-13 | 12/6/19 Castagna J - received email response from County today that construction has been completed and we can submit for final payment. Next update will be 12/20/19.Historical info to remain:11/22/19 - Castagna J - emailed NCDPW today to request status of construction completion. Will update WIP/AR notes upon reply.10/30/19 - Castagna J - NC responded on 10/22 that there was one more road to be completed and then final construction acceptance County. Once the County has accepted the construction contract, I am told that we will need to resubmit the invoice for $26,000 because it was submitted in 2017 before it should have been. It is now too old and will require resubmission. Next update will be 11/8/19. |  | 26000 |  |  |  |  | N |  | N
15 | Design | Castagna, Joseph | 17-006-0248 | [10 empty] | 26000 | 2 | 2017-12-01 | 11-22-19 - Castagna J - emailed NCDPW today to request status of construction completion. Will update WIP/AR notes upon reply.10-14-19 - Castagna J - NC has replied that Mission 17 is still under construction and that it is anticipated to be completed by the end of this year. 9/27/19 Castagna J - Final invoice for $26,000 confirmed to be at NC, but I was informed that it will need to be resubmitted when construction is completed. NC will notify LiRo when this occurs. Follow up request on status of completion of construction sent 9/27/19. Next update will be November 1st.3.14.19 SantanaL: This payment is the 20% payment and cannot be padi until construction completion or 2 years from the approval of the final LiRo deliverable, which was submitted October 2017.
16 | Design | Castagna, Joseph | 17-117-0248 |  | NCDPW Mission 19, Resurfacing Various Rd | 97500 | 78000 | 1125 | 1125 | 2019-03-01 | 12/6/19 - Castagna J - received response on 11/25/19 that no additional info is required on payment of $39,000. County responded today that construction will not be completed until the spring of 2020. The final bill can be submitted at that point. Next update will be 12/20/19.Historical note to remain:11/22/19 Castagna J - received email from NCDPW requesting additional info, but LiRo received payment of $39,000 on 11/20/19. I emailed NCDPW today requesting clarification. Next update will be 12/6/19.9/13/19 Castagna J - Joe was informed that Claim Number 2 for $39,000 (balance of 80% payment) was processed and signed in June. County will advise where in the payment process it is. Remaining 20% will not be paid until construction is complete Joe confirmed that there is a limit of 2 years to award a construction contract after written acceptance of the design or after final construction to have the final 20% released. Next update will be 9/27/19. | [6 empty] | N |  | N
17 | Design | Castagna, Joseph | 17-117-0248 | PHSE57 |  |  |  |  | 1125
18 | Design | Castagna, Joseph | 18-006-0407 |  | Town of Babylon Geiger Pk Fence Install | 19000 | 13979 | 9193 | 9193 | 2019-03-05 | 12/6/19 - Castagna J - No new direction from Babylon has been received so project is on hold. 12/2/19 Heather and Castagna advised the WIP is not collectable.Historical info to remain:10/11/19 - Castagna J - Babylon has been advised that completion of project is dependent upon results of Babylon's meeting with cell tower owner. New anticipated completion date is now end of October. Digitized map of Geiger Park was submitted. Next update will be 10/25/19. $28K of WIP is at Risk.8/26/19-Ray Ribeiro was advised by Babylon that there was no additional scope from the original contract and requested a full plan of all projects at Geiger Park to determine possible next steps and LiRo's role in the new work.5/23/9 - Castagna J - This project is anticipated to overrun by $15,000 in labor cost. At the time, this project was an enticement to Babylon to award Wyandanch Rising 2 to Bowne. Maximum fee collectible is $19,000. Next update will be 6/7/19. | [6 empty] | N |  | Y
19 | Design | Castagna, Joseph | 18-006-0407 | DESIGN |  |  |  |  | 8945
20 | Design | Castagna, Joseph | 18-006-0407 | SURVEY |  |  |  |  | 248
21 | Design | Castagna, Joseph | 18-158-1891 |  | Town of Hemp DoE-Oceanside Drainage Impr | 262293 | 204041 | 76674 | 68002 | 2019-03-01 | 12/6/19 - Castagna J - Joe met with TOH on 11/25. Additional comments provided. Number of easement maps increased over proposal so Joe in the process of requesting an increase in fee of approximately $20,000. Next update will be 12/20/19.Historical notes to remain:11/22/19 - Castagna J - drafting changes completed. Joe meeting with TOH on 11/25 to go over final plans. Next update will be 12/6/19.11.12.19 SantanaL: Waiting on milestone (next month) to invoice a third of open WIP. Remaining WIP is at risk due to project overrun.11/7/19 _Sonnenberg - Joe met with me to complete a recovery schedule.8/1/19 - Castagna J - Billed by milestone - 60% plans submitted on 5/3/19. Rec'd verbal review comments from Town. Upon acceptance of plans, we will complete 100% design and bill remainder of fee at $34,000. The final design phase is anticipated to overrun the budget line by $80,000 in labor due to complexity of road raising design. | [6 empty] | N |  | Y
22 | Design | Castagna, Joseph | 18-158-1891 | 3 |  |  |  |  | 68002
23 | Design | Eiseman, John | 10-108-1559 |  | RACANELLI/GREYBARN -PH 3 | 88168 | 70579 | 0 | 0 | 2019-01-31 |  |  | 5368 |  |  |  |  | N |  | N
24 | Design | Eiseman, John | 10-108-1559 | [10 empty] | 5367.75 | 1010810 | 2018-10-22 | 9.17.19 SantanaL: Per Angie Bonilla "Working to set up a conference call & work out all unpaid invoices from both parties"8/26/19 - John Eiseman advised he will not deliver the final survey until this AR is paid. 07.19.2019 (AB): Per email from John Eiseman (dated 04/18/19): Racanelli claims that the $5,367.75 is the Owner’s (Rechler ) responsibility.
25 | Design | Funaro, Donna | 18-045-0424 |  | TOBDPW 2018 Pavement Assessment | 224500 | 192588 | 120 | 120 | 2019-10-11 | 04/29 MessinaS- Inv#3 for $3448.11 sent back by Town wanted two separate claims for 2018 work and 2019 work, Inv#3 was voided and two new claims were sent out.04.02.19WaltzJ - Billing based on progress last bill was 13Mar2018 for $3,448.11 |  | 648 |  |  |  |  | N |  | N
26 | Design | Funaro, Donna | 18-045-0424 | WEB |  |  |  |  | 120
27 | Design | Funaro, Donna | 18-045-0424 | [10 empty] | 648.24 | 00001804503R | 2019-04-26 | 11/12/2019 DFunaro - Unsure why this invoice was not paid at the same time as 1804504. Followed up with the Town (Nanette) as to when this will be paid.10/22/2019 - Dfunaro - after additional attempts to reach John Tassone, I received a call back today from Nanette McGeever - Administrative Assistant to John Tassone asking for me to send copies of the invoices to John again. Since I have already done that multiple times, I asked if I could send them to her instead. This way, I know they will not be lost. They have been resent and hopefully we will see payment soon.
28 | Design | Gennawey, Abla | 15-096-0383 |  | SCDPW Engineering Svcs Woodside Ave CR16 | 239359 | 138551 | 50425 | 47048 | 2019-11-08 | 9/25/2019: Invoice 15 is being prepared. Abla is working with Audrey on correcting vision input errors and also revising tasks to match cost control report in order to finalize the invoice. | [6 empty] | N |  | N
29 | Design | Gennawey, Abla | 15-096-0383 | 3 |  |  |  |  | 37558
30 | Design | Gennawey, Abla | 15-096-0383 | 8 |  |  |  |  | 1435
31 | Design | Gennawey, Abla | 15-096-0383 | 11 |  |  |  |  | 5235 |  | 8/1/19-per Bob Hutteman, Abla and him will prepare invoice once the preliminary plans to the County are submitted._rdc
32 | Design | Gennawey, Abla | 15-096-0383 | 12 |  |  |  |  | 1983 |  | 8/1/19-per Bob Hutteman, Abla and him will prepare invoice once the preliminary plans to the County are submitted._rdc
33 | Design | Gennawey, Abla | 15-096-0383 | 13 |  |  |  |  | 838 |  | 8/1/19-per Bob Hutteman, Abla and him will prepare invoice once the preliminary plans to the County are submitted._rdc
34 | Design | Gennawey, Abla | 19-206-0270 |  | NYCP&R - Eng Design Constr Davidson Park | 294264 | 0 | 21432 | 17851 | [8 empty] | N |  | N
35 | Design | Gennawey, Abla | 19-206-0270 | 1 |  |  |  |  | 17851
36 | Design | Holmstrom, Kenneth | 11-04-0383 |  | SCDPW Horseblock Rd Bridge Over LIRR | 814819 | 788820 | 3775 | 0 | 2019-11-22 |  |  | 0 |  |  |  |  | N |  | N
37 | Design | Holmstrom, Kenneth | 11-04-0383 | [10 empty] | 0.01 | 110417 | 2019-08-14
38 | Design | Holmstrom, Kenneth | 16-367-1403 |  | Stassi Land Purchase | 16573 | 23144 | 2812 | 2812 | 2019-04-08 | 11.21.19 SantanaL: Spoke with Makendy and Invoice in the amount of $2811.95 was sent to cllient and came back rejected. Client said to be unaware of the project and that invoice was sent to the wrong Stassi. Ken Holmstrong has been advised to contact client to gain additional information on who to send invoice to. Invoice #3 was never posted to vision due to it being rejected by client.8.14.19 SantanaL: Per KwaschynM invoice in the amount of $2,811.95 was processed yesterday. | [6 empty] | N |  | N
39 | Design | Holmstrom, Kenneth | 16-367-1403 | MAP/DD |  |  |  |  | 2812
40 | Design | Holmstrom, Kenneth | 18-002-0078 |  | City of Glen Cove-Brewster St Pkg Garage | 40449 | 40431 | 5073 | 5073 | 2019-08-16 | [7 empty] | N |  | N
41 | Design | Holmstrom, Kenneth | 18-002-0078 | BID |  |  |  |  | 569
42 | Design | Holmstrom, Kenneth | 18-002-0078 | DESIGN |  |  |  |  | 4466
43 | Design | Holmstrom, Kenneth | 18-002-0078 | INSPEC |  |  |  |  | 38
44 | Design | Holmstrom, Kenneth | 18-052-0270 |  | NYCPR-Civil & Structural Engineering Svc | 137456 | 128561 | 22851 | 22851 | 2019-06-21 | 12.12.19 Per Holmstrom: We were paid $83,146.50 on Invoice 2 that is for Task 3. The total LiRo fee in this invoice was $89,818.50 which was paid with the balance of the amount paid applying to Task 4 and Task 5. This is the that totaled 110,818.50 with the 21,000 difference being the GZA fee which wasn’t paid. Invoice 3 which was submitted and hasn’t been paid includes $5,836.00 which applies to Task 3. The total invoiced LiRo fee for task 3 is $88,982.50 and Task 3 was authorized with the LiRo fee being $88,840.00. | [6 empty] | N |  | Y
45 | Design | Holmstrom, Kenneth | 18-052-0270 | RET-S3 |  |  |  |  | 17878
46 | Design | Holmstrom, Kenneth | 18-052-0270 | RET-S4 |  |  |  |  | 1652
47 | Design | Holmstrom, Kenneth | 18-052-0270 | RET-S5 |  |  |  |  | 3101
48 | Design | Holmstrom, Kenneth | 18-052-0270 | RETS-2 |  |  |  |  | 34
49 | Design | Holmstrom, Kenneth | 18-052-0270 | RETS5A |  |  |  |  | 187
50 | Design | Holmstrom, Kenneth | 19-076-0462 |  | Village of Mass Park Design of Improveme | 46695 | 30166 | 19310 | 14538 | 2019-10-11 | 09/25/19 redo Inv -resent on 09/26/19 .09/19/19MessinaS - First invoice sent out thru 08/16/19. | [6 empty] | N |  | N
51 | Design | Holmstrom, Kenneth | 19-076-0462 | 1 |  |  |  |  | 3823
52 | Design | Holmstrom, Kenneth | 19-076-0462 | 2 |  |  |  |  | -434
53 | Design | Holmstrom, Kenneth | 19-076-0462 | MEP |  |  |  |  | 11149
54 | Design | Hong, Feili | 14-099-0324 |  | PANYNJ JFK Traffic Operations Engineerin | 399025 | 343495 | 0 | 0 | 2019-04-19 |  |  | 11465 |  |  |  |  | N |  | Y
55 | Design | Hong, Feili | 14-099-0324 | [10 empty] | 6782.16 | 00000000004A | 2019-04-04
56 | Design | Hong, Feili | 14-099-0324 | [10 empty] | 4682.92 | 000005-FINAL | 2019-05-02 | 11/15/19-Heather and Mike advised this AR is at risk as they cannot get an answer from the client on the status. Collection letter being drafted. 11/15/19_Sonnenberg emailed Al Meyer at Sam Schwartz inquiring on the status of the two outstanding invoices from 4/4/19 & 5/2/19 in the amount of $11,465.08.
57 | Design | Hong, Feili | 15-120-0383 |  | SCDPW CR7 Wicks Road I-495 Interchange | 158812 | 111077 | 144 | 144 | 2018-06-08 | This project is on hold by the Suffolk County. LiRo is not able to make any invoice at this time. | [6 empty] | N |  | N
58 | Design | Hong, Feili | 15-120-0383 | DSGN |  |  |  |  | 144
59 | Design | Hong, Feili | 19-181-2247 |  | Elite Prospect - TOB Site Plan Review | 1200 | 0 | 402 | 402 |  | The client deposited LiRo $600 and will bill another $600 when the initial review is finished. This is expected by 1/30/2019. | [6 empty] | N |  | N
60 | Design | Hong, Feili | 19-181-2247 | 1 |  |  |  |  | 402
61 | Design | Hurley, Daniel | 15-068-0424 |  | TOB Lake Avenue CVM Expansion | 259425 | 129230 | 85351 | 68702 | 2018-12-21 | 12/2/19-Mike Smith is drafting the final request for additional funding. Lenz feels most of the design costs are not valid. the request for funds will include the CI services as LiRo re-estimated the projects and TOB is putting out to bid Jan 2020. Commissenor Lenz feels that the majority of the additional scope was caused by LiRo errors. | [6 empty] | N |  | Y
62 | Design | Hurley, Daniel | 15-068-0424 | 1 |  |  |  |  | 55758
63 | Design | Hurley, Daniel | 15-068-0424 | STAFF |  |  |  |  | 12944
64 | Design | Hurley, Daniel | 15-068-0424 | [10 empty] | -300 | 12 | 2017-10-06
65 | Design | Hurley, Daniel | 15-068-0424 | [10 empty] | 190.44 | 13 | 2019-01-15
66 | Design | Hutteman, Robert | 13-053-0472 |  | WCDPW Palmer Road Bridge | 186886 | 143997 | 34390 | 32659 | 2017-12-31 | 9.17.19 SantanaL - Category L - Invoicing WIP amount $25,869.50 by end of month.6/11/19 PIF was update on 6/7/1905/22/19 - We received a supplemental agreement for construction support services. Ken H. is updating the PIF. PIF is expected to be completed by 6/5/19 at which time Robert Hsu's time will be moved to the new task and WIP will be invoiced. | [6 empty] | N |  | N
67 | Design | Hutteman, Robert | 13-053-0472 | CONSTR |  |  |  |  | 27720
68 | Design | Hutteman, Robert | 13-053-0472 | STAFF |  |  |  |  | 4939
69 | Design | Hutteman, Robert | 15-049-0265.03 |  | NYCDDC Stanton & Lake Court Infrastructu | 1325920 | 1574287 | 23733 | 22455 | 2019-05-29 | BIB is waiting for the entire infrastructure (all courts) to complete and signed off before we can bill the remaining 10% design fees, once the final fees are billed, these hours will be cleared. Once the amendment is approved, all Stanton work will be paid as lump sum. | [6 empty] | N |  | N
70 | Design | Hutteman, Robert | 15-049-0265.03 | CONADM |  |  |  |  | 22163
71 | Design | Hutteman, Robert | 15-049-0265.03 | DESRPZ |  |  |  |  | 291
72 | Design | Hutteman, Robert | 16-308-0305 |  | NYC-DCAS Professional Svcs Requirement | 926932 | 459715 | 79477 | 70566 | 2019-12-31 | 11.12.19 SantanaL: multi division job (C/S, MEP, ARCH)- Invoice needs to be created - categorized as further discussion needed - Hutteman needs to speak wth J Grant and M Smith to discuss invoice preparation.5.8.19 SantanaL: HuttemanR will be updatingMajority of WIP is for MEP and Architects. $333.44 is for sub (Historical Perspectives) and $3,200 in expensesI submitted a draft invoice for PV time to DCAS months ago but have not been able to get a response. |  | 43351 |  |  |  |  | N |  | N
73 | Design | Hutteman, Robert | 16-308-0305 | 2LAFAY |  |  |  |  | 12958
74 | Design | Hutteman, Robert | 16-308-0305 | BOARD |  |  |  |  | 1936
75 | Design | Hutteman, Robert | 16-308-0305 | HARLEM |  |  |  |  | 11701
76 | Design | Hutteman, Robert | 16-308-0305 | MECH |  |  |  |  | 20783
77 | Design | Hutteman, Robert | 16-308-0305 | POLICE |  |  |  |  | 1530
78 | Design | Hutteman, Robert | 16-308-0305 | READE |  |  |  |  | 1161
79 | Design | Hutteman, Robert | 16-308-0305 | SPEC |  |  |  |  | 14617
80 | Design | Hutteman, Robert | 16-308-0305 | SPEDEV |  |  |  |  | 5881
81 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 13476.08 | 000001-BOILR | 2017-07-12
82 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 24225.5 | 00000CLTWR01 | 2017-07-12
83 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 1130.4 | 001_HARLEMCO | 2019-04-11
84 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 4518.71 | 00280BDWY1R2 | 2017-08-14
85 | Design | Hutteman, Robert | 16-341-1387 |  | Breaking Ground Sites Assessment | 56000 | 0 | 13801 | 45298 | 2016-10-07 | [7 empty] | N |  | N
86 | Design | Hutteman, Robert | 16-341-1387 | STAFF |  |  |  |  | 45298
87 | Design | Hutteman, Robert | 17-046-0472 |  | Rehabilitation of Pondfield Road West Br | 196855 | 37678 | 109956 | 102188 | 2018-05-25 | 11.12.19 SantanaL: Per Hutteman contacting invoice preparer to ensure invoice goes out.9.17.19 SantanaL: Category L - Invoicing $91,378.90 by end of month.7.9.19 SantanaL: HuttemanR is working with Makendy to invoice WIP on this project" | [6 empty] | N |  | N
88 | Design | Hutteman, Robert | 17-046-0472 | CONDOC |  |  |  |  | 7722
89 | Design | Hutteman, Robert | 17-046-0472 | DESDEV |  |  |  |  | 55852
90 | Design | Hutteman, Robert | 17-046-0472 | PROP |  |  |  |  | 6674
91 | Design | Hutteman, Robert | 17-046-0472 | SCHDES |  |  |  |  | 31941
92 | Design | Hutteman, Robert | 19-045-1387 |  | Breaking Ground Property Condition Asses | 100000 | 100000 | 24457 | 0 | 2019-09-13 |  |  | 8734 |  |  |  |  | N |  | N
93 | Design | Hutteman, Robert | 19-045-1387 | [10 empty] | 8733.75 | 00001904501R | 2019-07-15 | 11.12.19 SantanaL: Received check in the amount of 43,266.25 against invoice1904501R dated 7/15/19- Balance of 12,000 remains 91-120 aging.
94 | Design | Korrow, Bruce | 17-090-0911 |  | TOHDOS Truck Wash Constr Admin | 133400 | 102611 | 14586 | 8078 | 2018-09-28 | 12/2/19-Heather has advised that the Town is issuing a new Work Order to LiRo for CI services that will be paid for by the bonding company. Heather is following up with Francesca Capitano-Counsel of the town to get an update on the new work order and getting funding in place for the previous AR and WIP not paid. 7/20/19-the town (Comm Joe Conroy) issued an NTP to the bonding company to complete the work. The town is supposedly putting a Borad Reso on the Sept docket for the LiRo funding of $103K to cover the old AR and then the bonding company is to contact LiRo to direct hire liRo to CI the balance of the work???? JM reached out to Conroy and spoke to Francesca Capitano-Counsel to the Comm for a confirmation $103,635 AR, $7,658 WIP. The former commissioner authorized this project without obtaining the resolution from the board. Mike is attempting to work with the Town to resolve and he is also working with the bonding company. This is going no where. The Town and bonding comapny to provide CI for the balance of the project. Mike was directed to forward all future requests to Joe Massa. There is no contract in place with the bonding company.$103,635 AR, $7,658 WIP. |  | 102611 |  |  |  |  | N |  | Y
95 | Design | Korrow, Bruce | 17-090-0911 | CONSTR |  |  |  |  | 8078
96 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 25383.69 | 1 | 2017-10-24 | 12/2/19-Heather has advised that the Town is issuing a new Work Order to LiRo for CI services that will be paid for by the bonding company. Heather is following up with Francesca Capitano-Counsel of the town to get an update on the new work order and getting funding in place for the previous AR and WIP not paid. 11/30/19-the Town is requesting that we move forward with the contract witht he bonding company and provide construction phase services. heather has not received a response from the Town on the open AR and WIP. 7/20/19-the town (Comm Joe Conroy) issued an NTP to the bonding company to complete the work. The town is supposedly putting a Borad Reso on the Sept docket for the LiRo funding of $103K to cover the old AR and then the bonding company is to contact LiRo to direct hire liRo to CI the balance of the work???? JM reached out to Conroy and spoke to Francesca Capitano-Counsel to the Comm for a confirmation. 4/29/2019 LS: Per HeatherS "This project has an outstanding invoice in the amount of $102,611 for work completed without the formal approval from the Town. The former commissioner authorized LiRo to proceed with work without obtaining the formal resolution from the board. Mike has met with the new commissioner to try and resolve the issue. Mike is currently working with George from the bonding company who is now involved since the Town has defaulted on the contractor. Mike submitted rates to the bonding company for Jeff Munzing with a 2.2 multiplier and a max rate of $175 for Mike. The previous GC has no interest in finishing the work so the Mike will be meeting with the new bidder next Tuesday at 1 pm to walk the site. The fees Mike has provided to the bonding company is for the current services LiRo will be providing. We still need to deal directly with the Town to resolve payment from the former work completed. Mike is communicating with the current commissioner regarding this. The bonding company will be paying for work going forward and the Town must pay for the previously completed work. Mike met with both the Commissioner and Town attorney and they advised they are working on the issue but they haven’t provided a date of resolution at this time."
97 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 6555.24 | 2 | 2017-11-14
98 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 6943.7 | 3 | 2017-12-14
99 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 940.15 | 4 | 2018-01-10
100 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 4759.58 | 5 | 2018-02-07
101 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 15103.93 | 6 | 2018-03-08
102 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 10282.4 | 7 | 2018-04-04
103 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 13312.53 | 8 | 2018-05-03
104 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 11084.99 | 9 | 2018-06-04
105 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 3935.3 | 10 | 2018-06-28
106 | Design | Korrow, Bruce | 17-090-0911 | [10 empty] | 4309.31 | 11 | 2018-10-10
107 | Design | Kuo, Lawrence | 08-101-1746 |  | WOODBURY RLTY/WCC 76 UNIT VILLAS | 404078 | 416120 | 0 | 0 | 2019-03-29 |  |  | 19688 |  |  |  |  | N |  | N
108 | Design | Kuo, Lawrence | 08-101-1746 | [10 empty] | 19688.01 | 810108 | 2019-04-08 | 6/18/19 KENNY D. SENT ANOTHER COPY OF OUTSTANDING INVOICE WITH REQUEST TO EXPEDITE PAYMENT.
109 | Design | Kuo, Lawrence | 10-106-1720 |  | RECHLER EQ/NEW FRONTIER | 586875 | 754307 | 7661 | 7699 | 2019-10-25 | 11/15/19 -Inv dated 10/14/19 for 6,368.00 has to be voided and rebilled under the new P.O.# under the new project # to be set up. 10-106-1720.01. 10-106-1720 will be left open for surveying.10-106-1720.0111/6/19 - Inv #30 for 1500.00 is for Survey - no p.o. there is no retainer.10/16/19 Inv #29 for 6000.00 is for Survey - P.O. 9195 - there is no retainer on it.09/27/19MessinaS- As per conservation between Angie and Kristen we are receiving an 125K next week to include some of the retainer we have requested.9/19/19-Larry and Eismena working on $76K in invoices for Survey that Larry say should not be billed against this contract. In addition there is a $51K change order that is with Al; Rechler will only issue the change order to Bowne and not LiRo. In addition, Rechler is refusing to change future checl to LiRo instead of Bowne. The overall project needs to be reviewed to determine which open invoices are for retainage and which are valid open AR for work perfromed. 09/19/19-On John Eiseman's Survy Task 224 Brefini I'm still waiting for certain people to transfer their time form the old task 578 to Task 224. before I can bill it. | 3400 | 84903 |  |  |  |  | N |  | N
110 | Design | Kuo, Lawrence | 10-106-1720 | 3 |  |  |  |  | 4162
111 | Design | Kuo, Lawrence | 10-106-1720 | 4 |  |  |  |  | 309
112 | Design | Kuo, Lawrence | 10-106-1720 | 558 |  |  |  |  | 2947 |  | 08-14-19 KuoL: will eventually go to CD and CA which we can request addendum when it is about to go into construction. Possibly early 2020.04-09-19 KuoL: originally Buffalo & Rochester assist on design, learning curve led to project overrun.
113 | Design | Kuo, Lawrence | 10-106-1720 | 572 |  |  |  |  | 282
114 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 3572.4 | 277358 | 2017-08-31 | 05-02-19 KuoL: This is retainer remaining.
115 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 3360 | 1010602 | 2018-07-20 | 05-02-19 KuoL: This is retainer remaining.
116 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 1800 | 1010603 | 2018-08-21 | 05-02-19 KuoL: This is retainer remaining.
117 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 510 | 1010611 | 2018-10-22 | 05-02-19 KuoL: e-mail sent to client PM and onwer on 4/11/19 to follow up on payment.
118 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 315 | 1010612 | 2018-10-23 | 05-02-19 KuoL: e-mail sent to client PM and onwer on 4/11/19 to follow up on payment.
119 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 30320.18 | 1010614 | 2018-10-23 | 08-14-19 KuoL: e-mail sent to John E. as this is survey task with different contract.
120 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 10484.62 | 1010615 | 2018-10-23 | 08-14-19 KuoL: e-mail sent to John E. as this is survey task with different contract.
121 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 30158.91 | 1010616 | 2018-10-23 | 08-14-19 KuoL: e-mail sent to John E. as this is survey task with different contract.
122 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 1052.16 | 1010617 | 2018-10-23 | 08-14-19 KuoL: e-mail sent to John E. as this is survey task with different contract.
123 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 792 | 1010624 | 2019-04-29 | 05-02-19 KuoL: e-mail sent to client PM and onwer on 4/11/19 to follow up on payment.
124 | Design | Kuo, Lawrence | 10-106-1720 | [10 empty] | 2538 | 00001010621R | 2019-03-20 | 05-02-19 KuoL: e-mail sent to client PM and onwer on 4/11/19 to follow up on payment.
125 | Design | Kuo, Lawrence | 11-172-1717 |  | R SQUARED/CANOE PL INN | 207261 | 149554 | 4483 | 710 | 2019-08-02 | 11/14/19 P.o.#6126 Goes thru Inv#1117203 dated 08/19/19 after that anything else will be P.o. #11730.11.11.19 SantanaL: Per Larry K: Waiting for change order approval to invoice WIP (1,183.07)9/19/19-The overall project needs to be reviewed to determine which open invoices are for retainage and which are valid open AR for work perfromed. |  | 26202 |  |  |  |  | N |  | N
126 | Design | Kuo, Lawrence | 11-172-1717 | 556 |  |  |  |  | 710
127 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 1216.87 | 265807 | 2012-08-08 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
128 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 960.08 | 266001 | 2012-09-04 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
129 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 72.36 | 266449 | 2012-11-07 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
130 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 19.8 | 266604 | 2012-11-28 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
131 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 189 | 267161 | 2013-02-26 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
132 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 463.14 | 267566 | 2013-05-03 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
133 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 470.25 | 267746 | 2013-05-20 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
134 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 213.75 | 268391 | 2013-08-14 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
135 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 171 | 268554 | 2013-09-04 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
136 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 83.12 | 268598 | 2013-09-06 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
137 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 171 | 268785 | 2013-10-08 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
138 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 166.73 | 269901 | 2014-03-24 | Retainage - to be collected when Rechler PO is finished
139 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 68.4 | 270128 | 2014-04-22 | Retainage - to be collected when Rechler PO is finished
140 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 435.38 | 270758 | 2014-07-16 | Retainage - to be collected when Rechler PO is finished
141 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 85.13 | 271581 | 2014-11-25 | Retainage - to be collected when Rechler PO is finished
142 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 195.6 | 271758 | 2014-12-22 | Retainage - to be collected when Rechler PO is finished
143 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 104.4 | 272543 | 2015-05-07 | Retainage - to be collected when Rechler PO is finished
144 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 84.38 | 272808 | 2015-06-12 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
145 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 28.13 | 273007 | 2015-07-13 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
146 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 28.13 | 273295 | 2015-09-08 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
147 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 225 | 273628 | 2015-11-03 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
148 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 1012.5 | 273764 | 2015-12-01 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
149 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 562.5 | 273939 | 2016-01-04 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
150 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 562.5 | 274215 | 2016-02-25 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
151 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 150 | 275381 | 2016-08-15 | 05-02-19 KuoL: Need to work with accounting to attempt to request retainer as part of site plan approval. Retainage - to be collected when Rechler PO is finished
152 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 2850 | 277533 | 2017-09-30 | 05-02-19 KuoL: This is recent retainer. 3/21/18-sent email to Kristen McCabe following up on invoice. $16,301.11 should be paid soon (invoice-retainage)
153 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 4605 | 1117201 | 2018-11-06 | 08-14-19 KuoL: Rich stated GMP was agreed with GC, project will move forward. Will follow up with Kristen on AR's.06-18-19 KuoL: Stephanie contacted Kristen, waiting for construction loan, maybe in 2 weeks plus. 05-02-19 KuoL: follow up e-mail sent to Client PM and owner on 4/11/19.
154 | Design | Kuo, Lawrence | 11-172-1717 | [10 empty] | 11008 | 1117202 | 2019-05-01 | 11.11.19 SantanaL: Per LArryK - Client waiting for construction loan to pay Outstanding AR.08-14-19 KuoL: Rich stated GMP was agreed with GC, project will move forward. Will follow up with Kristen on AR's.06-18-19 KuoL: Stephanie contacted Kristen, waiting for construction loan, maybe in 2 weeks plus.
155 | Design | Kuo, Lawrence | 11-173-1717 |  | R SQUARED/CANAL PROP | 375770 | 350799 | 27256 | 4667 | 2019-08-02 | 11/15/19 - As of 11/15 all of the outstanding balances are retainage on the old p.o. 6191. Any invoice after inv dated 08/19/19 the new p.o#11731 will apply.9/19/19-The overall project needs to be reviewed to determine which open invoices are for retainage and which are valid open AR for work perfromed.08/20/19-MessinaS - Inv thru 08/02/19 sent out.06/12/19- After my conversation with Kristen at Reichler, the Contractor Retention Invoice was revised to 27,978.10 this goes thru Inv dated 03/01/2019 with the deduction of the contruction phase of 5,640.00 which is ongoing. | 1277 | 10686 |  |  |  |  | N |  | N
156 | Design | Kuo, Lawrence | 11-173-1717 | 1 |  |  |  |  | 4667 |  | 5/2/19 KuoL: e-mail from client PM that CO is being processed. 4/11/19 KuoL: CO sent 3/27/19, waiting for PO # to bill.
157 | Design | Kuo, Lawrence | 11-173-1717 | [10 empty] | 570 | 1117301 | 2018-04-11 | 05-02-19 KuoL: this is recent retainer.
158 | Design | Kuo, Lawrence | 11-173-1717 | [10 empty] | 1905 | 1117303 | 2018-11-02 | 05-02-19 KuoL: this is recent retainer.
159 | Design | Kuo, Lawrence | 11-173-1717 | [10 empty] | 810 | 1117304 | 2019-02-22 | 05-02-19 KuoL: sent follow up e-mail to client PM and owner on 4/11/19.
160 | Design | Kuo, Lawrence | 11-173-1717 | [10 empty] | 2355 | 1117305 | 2019-03-01 | 05-02-19 KuoL: sent follow up e-mail to client PM and owner on 4/11/19.
161 | Design | Kuo, Lawrence | 11-173-1717 | [10 empty] | 5046.38 | 1117307 | 2019-05-29
162 | Design | Kuo, Lawrence | 13-169-1681 |  | ENGEL BURMAN/DOREMUS SITE DEVELOPMENT | 523201 | 516017 | 0 | 0 | 2019-06-07 |  |  | 16196 |  |  |  |  | N |  | N
163 | Design | Kuo, Lawrence | 13-169-1681 | [10 empty] | 16066.08 | 1316907 | 2018-09-28 | 11.21.19 SantanaL: Per Mesina S - who contacted client - "I just spoke with Adam in Payables, he said they cut a check on Oct 23, but it didn’t clear the bank, he said he would reissue a new check." - PM Larry Kuo will follow up with client next week to confirm check has reissued. 7.2.19 SantanaL: KennyD wrote on 6/10/19 "Check was not received - resent copy of outstanding invoices to client"5/17/19 KENNY D. EMAILED NICK MASEM 5/15/19 RE STATUS OF PAYMENT.EMAIL COMMUNICATION BETWEEN ENGEL BURMANS PROJECT MANAGER AND ACCOUNTING DEPARTMENT INDICATED THAT CHECKS WILL BE SENT OUT 5/16/19.
164 | Design | Kuo, Lawrence | 13-169-1681 | [10 empty] | 130.41 | 1316910 | 2019-07-01
165 | Design | Kuo, Lawrence | 14-194-1696 |  | LIGHTHOUSE RLTY/ISLIP PINES | 506000 | 427243 | 30221 | 16522 | 2019-08-02 |  | 30624 | [5 empty] | N |  | N
166 | Design | Kuo, Lawrence | 14-194-1696 | 200 |  |  |  |  | 4287
167 | Design | Kuo, Lawrence | 14-194-1696 | 550 |  |  |  |  | 12235
168 | Design | Kuo, Lawrence | 15-353-1725 |  | BEECHWOOD/COUNTRY POINTE AT PLAINVIEW | 1602825 | 1571810 | 1880 | 0 | 2019-10-25 | 09/13/19-Inv thru 08/30/19 sent out. $19,965.2708/27/19 INV thru 08/02/19 sent out. $6,148.83 | 19965 | 7086 |  |  |  |  | N |  | N
169 | Design | Kuo, Lawrence | 15-353-1725 | [10 empty] | 936.83 | 1535313 | 2019-05-20
170 | Design | Kuo, Lawrence | 15-353-1725 | [10 empty] | 6148.83 | 1535314 | 2019-07-01
171 | Design | Kuo, Lawrence | 15-356-1725 |  | BEECHWOOD/COUNTRY POINTE COMMERCIAL | 120782 | 140419 | 0 | 0 | 2019-10-25 |  | 282 | 23793 |  |  |  |  | N |  | N
172 | Design | Kuo, Lawrence | 15-356-1725 | [10 empty] | 3965.14 | 1535604 | 2018-09-27 | 5/16/19 KENNY D. EMAILED STEVEN DUBB (one of the owners) AT BEECHWOOD TODAY REQUESTING STATUS OF PAYMENT. PREVIOUSLY, SPOKE WITH BILL CARMAN (Project Manager) AND ADRESSED INVOICES FOR APPROVAL. STEVEN DUBB SAID HE WILL FOLLOW UP WITH PROJECT MANAGERS AND GET BACK TO ME.
173 | Design | Kuo, Lawrence | 15-356-1725 | [10 empty] | 14409.73 | 1535605 | 2019-04-10
174 | Design | Kuo, Lawrence | 15-356-1725 | [10 empty] | 1608.98 | 1535606 | 2019-05-20
175 | Design | Kuo, Lawrence | 15-356-1725 | [10 empty] | 3809.6 | 1535607 | 2019-07-01
176 | Design | Kuo, Lawrence | 16-406-1194 |  | KIMCO/MILLERIDGE INN HOTEL SITE | 179000 | 189315 | 79934 | 74120 | 2019-09-27 | 9/25/19 KennyD. Signed change order received and submitted to Kimco on 9/23/19. Invoice is being prepared for submission.9/20/19 Dane Kenny. To date, I have not received signed change order back from legal. 8/23/19 DANE K. SUBMITTED ON 8/5/19 CHANGE ORDER ($25,000 CONSTRUCTION DOCUMENTS) FOR LIRO SIGNATURE. TO DATE CHANGE ORDER NOT YET RECEIVED BACK FROM LEGAL. WIP FOR THIS TASK CANNOT BE BILLED UNTIL CHANGE ORDER SIGNED AND RETURNED TO CLIENT.08/14/19 MessinaS- Dane emailed client invoice p/e07/19/197/22/19- Dane Kenny, Approval received from Client. Change order no. 6 for $31,367.97 is being processed. Invoice for said amount will be prepared and submitted. | [6 empty] | N |  | N
177 | Design | Kuo, Lawrence | 16-406-1194 | 200 |  |  |  |  | 102
178 | Design | Kuo, Lawrence | 16-406-1194 | 201 |  |  |  |  | 30177
179 | Design | Kuo, Lawrence | 16-406-1194 | 202 |  |  |  |  | 420
180 | Design | Kuo, Lawrence | 16-406-1194 | 203 |  |  |  |  | 4128
181 | Design | Kuo, Lawrence | 16-406-1194 | 550 |  |  |  |  | 35344
182 | Design | Kuo, Lawrence | 16-406-1194 | 551 |  |  |  |  | 3950
183 | Design | Kuo, Lawrence | 16-408-0865 |  | WINTHROP/NEW LIFE EXP DESIGN & CONSTR | 72000 | 16380 | 0 | 0 | 2018-06-08 |  |  | 1980 |  |  |  |  | N |  | Y
184 | Design | Kuo, Lawrence | 16-408-0865 | [10 empty] | 720 | 1640801 | 2018-02-22 | 08-05-19 KuoL: sent Gerard Peduto a follow up e-mail. Gerard waiting for Winthrop authorization. 07-10-19 KuoL: Gerard Peduto is PM for this project. per e-mail, he will look into it. 06-17-19 KuoL: e-mail sent to Nick on 6/3/19. Nick forward to Linda & Gerald. e-mail on 6/17/19 to follow up. 05-02-19 KuoL: accounting to look up in NYU Winthrop system for status.
185 | Design | Kuo, Lawrence | 16-408-0865 | [10 empty] | 1260 | 1640802 | 2018-06-20 | 09-19-19 KuoL: sent Gerard Peduto a follow up e-mail. 08-05-19 KuoL: sent Gerard Peduto a follow up e-mail. Gerard waiting for Winthrop authorization. 07-10-19 KuoL: Gerard Peduto is PM for this project. per e-mail, he will look into it. 06-17-19 KuoL: e-mail sent to Nick on 6/3/19. Nick forward to Linda & Gerald. e-mail on 6/17/19 to follow up. 05-02-19 KuoL: accounting to look up in NYU Winthrop system for status.
186 | Design | Kuo, Lawrence | 17-241-1685 |  | HARMONY EARLY LEARNING/HARMONY DAYCARE | 31100 | 32353 | 0 | 0 | 2019-05-24 |  |  | 5067 |  |  |  |  | N |  | N
187 | Design | Kuo, Lawrence | 17-241-1685 | [10 empty] | 5066.87 | 1724103 | 2019-02-21 | 11.25.19 SantanaL: Per MikeSmith"On October 18th, Michael Smith called Sam Koshy regarding this payment when Larry Ku was asked to release final CAD. Sam commented that he couldn’t make final payment on the project until all the paperwork was completed. Sam Koshy put in writing LiRo would be paid within 30 days from the call."9/19/19 - 9/19/19 - open AR of $5,616, Larry Kuo to confirm he has spoken to the client and the project is not at Risk. If it is at risk, please send a copy of the contract and open invoices for a Legal letter to be drafted19-09-19 KuoL: e-mailed Client to follow up. 19-06-17 KuoL: Cliient stated remaining balance to be paid in about 2 weeks after closing.
188 | Design | Kuo, Lawrence | 18-159-0207 |  | Lizardos Eng-NYU Winthrop Gen Replacemen | 26700 | 3522 | 0 | 0 | 2018-10-26 |  |  | 3522 |  |  |  |  | N |  | N
189 | Design | Kuo, Lawrence | 18-159-0207 | [10 empty] | 3522.24 | 1815901 | 2018-11-05 | 09-19-19 KuoL: received PO from PM, need to put it through Unifier system to be paid. 08-16-19 KuoL: e-mailed Blitz on 8/16/19 to follow up.06-17-19 KuoL: spoke to Blitz on 6/17/19 and he stated that usually takes 90 days to process. He approved payment already. 05-02-19 KuoL: on 4/10/19 Brendan Blitz with NYU Winthrop stated he will take over, open PO and get us paid. 4-5-19 KuoL: e-mailed Dirk with Lizardos to follow up on invoice.
190 | Design | Kuo, Lawrence | 18-304-2024 |  | Domus Group - Woodbury Villas | 137280 | 73482 | 6350 | 4447 | 2019-10-25 | 11/15/19-Dane and Paul advised the client is reviewing additional services provided and the quality of the services provided. |  | 12148 |  |  |  |  | N |  | Y
191 | Design | Kuo, Lawrence | 18-304-2024 | 2 |  |  |  |  | 3460
192 | Design | Kuo, Lawrence | 18-304-2024 | 3 |  |  |  |  | 988
193 | Design | Kuo, Lawrence | 18-304-2024 | [10 empty] | 12148.02 | 1830402 | 2019-04-30 | 2019-08-02 KuoL: Dane and Paul spoke with client to discuss invoice for additional services. Client stated he will discuss with his partners and get back to us.
194 | Design | Kuo, Lawrence | 19-122-0424 |  | TOBDPW-Highway Improvements Intervale Av | 290000 | 120556 | 3688 | 612 | 2019-10-25 | [7 empty] | N |  | N
195 | Design | Kuo, Lawrence | 19-122-0424 | 1 |  |  |  |  | 0
196 | Design | Kuo, Lawrence | 19-122-0424 | 3 |  |  |  |  | 612
197 | Design | Kuo, Lawrence | 19-128-2194 |  | Alpha Capital - 475 Fulton Avenue | 5600 | 2192 | 1887 | 84 | 2019-10-25 | [7 empty] | N |  | N
198 | Design | Kuo, Lawrence | 19-128-2194 | 1 |  |  |  |  | 84
199 | Design | Kuo, Lawrence | 19-135-0407 |  | Town of Babylon Wyandanch Rising PhaseII | 1015895 | 123811 | 33132 | 13051 | 2019-09-27 | 08/12/19MessinaS - Inv sent out p/e 08/02/19. | [6 empty] | N | 2019-02-11 | N
200 | Design | Kuo, Lawrence | 19-135-0407 | 1 |  |  |  |  | 3179
201 | Design | Kuo, Lawrence | 19-135-0407 | 2 |  |  |  |  | 9872
202 | Design | Kuo, Lawrence | 19-155-0207 |  | Lizardos - NYUWH Gen #6 Replacement | 19300 | 5629 | 237 | 237 | 2019-10-25 | [7 empty] | N |  | N
203 | Design | Kuo, Lawrence | 19-155-0207 | 1 |  |  |  |  | 237
204 | Design | Kwaschyn, Michael | 15-069-0424 |  | TOB Ships Point Lane | 102580 | 101621 | 0 | 0 | 2019-06-21 |  |  | 16143 |  |  |  |  | N |  | N
205 | Design | Kwaschyn, Michael | 15-069-0424 | [10 empty] | 16142.67 | 3 | 2019-07-03
206 | Design | Mansfield, Kevin | 14-180-0424 |  | OB HWY/CON - SEABREEZE RD | 65500 | 65309 | 10925 | 10925 | 2018-04-30 | 8.15.19 SantanaL: Per SonnenbergH - In Legal - TOB refuses to pay.6/13/19- Al attempting to contact TOB Attorney-no response from TOWN. $65,309 in AR were billed prior to acquisition. CV=65,500, BTD=65,309 |  | 65309 |  |  |  |  | N |  | Y
207 | Design | Mansfield, Kevin | 14-180-0424 | 400 |  |  |  |  | 7640
208 | Design | Mansfield, Kevin | 14-180-0424 | 500 |  |  |  |  | 3285
209 | Design | Mansfield, Kevin | 14-180-0424 | [10 empty] | 17643.27 | 277509 | 2017-09-30 | 8.15.19 SantanaL: Per SonnenbergH - In Legal - TOB refuses to payRefer to email Donna Funaro sent on 11/12/18. Comptroller liquidated account and these funds are supposed to be paid. Al Bereche has attempted tocontact the Town Attorney. No contact
210 | Design | Mansfield, Kevin | 14-180-0424 | [10 empty] | 26076.33 | 277601 | 2017-10-25
211 | Design | Mansfield, Kevin | 14-180-0424 | [10 empty] | 4738.95 | 277709 | 2017-11-28
212 | Design | Mansfield, Kevin | 14-180-0424 | [10 empty] | 16850.2 | 1418001 | 2018-01-29
213 | Design | Petrie, Jeffrey | 18-241-1959 |  | Mustafa Akkaya - GSS Service Station | 750 | 0 | 282 | 282 | [8 empty] | N |  | N
214 | Design | Petrie, Jeffrey | 18-241-1959 | 1 |  |  |  |  | 282
215 | Design | Ramirez-Walton, Noris | 19-216-1891.01 |  | TOH DoE -2019 Roadway Resurfacing Part B | 143094 | 0 | 28373 | 2918 | [8 empty] | N |  | N
216 | Design | Ramirez-Walton, Noris | 19-216-1891.01 | 1 |  |  |  |  | 2918
217 | Design | Sonnenberg, Heather | 18-001-0424 |  | TOBDPW Exp of Ellsworth W. Allen Pk | 964910 | 1239371 | 18555 | 17149 | 2019-05-31 | 12/10/19_Sonnenberg - Mike Smith is negotiations with Commissioner Lenz on approval of final additional services.12/2/19-Mike Smith met with he Town and presented a request for $326K. Commissioner Lenz has pushed back and said he thinks the $ is excessive and does not agree with most of the design costs. Mike is reviewing the costs to present a final draft to the Commissioner. At Risk for $75K. | [6 empty] | N |  | Y
218 | Design | Sonnenberg, Heather | 18-001-0424 | BID |  |  |  |  | 3500
219 | Design | Sonnenberg, Heather | 18-001-0424 | CM/INS |  |  |  |  | 1925
220 | Design | Sonnenberg, Heather | 18-001-0424 | CONAD |  |  |  |  | 3325
221 | Design | Sonnenberg, Heather | 18-001-0424 | DESIGN |  |  |  |  | 8400
222 | Design | Sonnenberg, Heather | 18-357-2045 |  | Acadia - Village Commons Shopping Center | 10700 | 12244 | 0 | 0 | 2019-10-11 | 12/10/19_Sonnenberg - Emailed client today for payment status.11/11/19_Sonnenberg - Client's accounting department sent final approval for payment verification on 11/4/19. Payment should be received within the next few weeks. |  | 10374 |  |  |  |  | N |  | N
223 | Design | Sonnenberg, Heather | 18-357-2045 | [10 empty] | 10373.59 | 1835701 | 2019-08-08
224 | Design | Sonnenberg, Heather | 19-077-0248 |  | Nassau Count DPW Eisenhower Pk Spray Pk | 58000 | 27102 | 6870 | 316 | 2019-09-27 | 12/10/19_Sonnenberg - NCDPW is slower on payment requests.11/11/19_Sonnenberg - emailed additional rates requested by NCDPW to Bob LaBaw. | 5274 | 17731 |  |  |  |  | N |  | N
225 | Design | Sonnenberg, Heather | 19-077-0248 | 2 |  |  |  |  | 316
226 | Design | Sonnenberg, Heather | 19-077-0248 | [10 empty] | 17730.59 | 1907701 | 2019-06-10
227 | Design | Stevens, Paul | 12-166-1749 |  | JWD/NITRATE & VOC REMOVAL FACLTY | 733482 | 738044 | 51639 | 51639 | 2019-03-29 | 8.21.19 SantanaL: Per StevensP - WIP 80,386 should be written off6/15/19-Legal is involved with litigation between Merrick Utilities and JWD.Contractor has claim against JWD for delays, we will be required to support JWD. Another Engineer is now performing construction services on this project we designed, so there will be ongoing questions about our design. Per Paul, it is not clear what we are able to bill. Project will be open for two more years. Billed to contract max.9/20/19 Project in litagation WIP $129,243.JWD agreed to $54 K initial payment and hold remainderfor review Until after litagation.Al Bereche reviewing whether or not to accept $54 K payment at this time. |  | 129243 |  |  |  |  | N |  | Y
228 | Design | Stevens, Paul | 12-166-1749 | 200 |  |  |  |  | 1297
229 | Design | Stevens, Paul | 12-166-1749 | 800 |  |  |  |  | 36079
230 | Design | Stevens, Paul | 12-166-1749 | 801 |  |  |  |  | 3157
231 | Design | Stevens, Paul | 12-166-1749 | 802 |  |  |  |  | 11107
232 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 43063.62 | 1216605 | 2018-07-26 | 8.21.19 SantanaL: Per StevensP -theres a PO for 54,000 +/- under review by AL (LiRo legal), remaining 75k is being held by Jericho water district pending litigation outcome.5/6/19 Stevens P.Emailed Peter Logan for update on 4/12/19.He said he will review that week.Emailed Peter Logan on 4/23/19 and 5/7/19.No response.4/4/19 StevensP: Jericho water district has agreed to pay $54,000- the remaining fees are delayed until litigation is resolved. Construction is 95% complete. This note is same for the following invoice numbers (1216605,1216606,1216607,1216608,1216609,1216610). Email was sent today 4/4/19 to Commissioner Tom Abatte and Superintendent Peter Logan requesting status of our $54,000 payment.
233 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 63519.66 | 1216606 | 2018-08-07
234 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 6920.01 | 1216607 | 2018-10-08
235 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 4499.94 | 1216608 | 2018-11-09
236 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 1064.37 | 1216609 | 2018-12-26
237 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 1379.94 | 1216610 | 2019-02-19
238 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 8795.94 | 1216611 | 2019-04-17
239 | Design | Stevens, Paul | 16-425-1749 |  | JWD/WELL NO. 12 REHAB | 126800 | 113058 | 49588 | 49588 | 2019-10-25 | 12/2/19-Paul advised he has not received any update. 9/26/19-Paul Logan advised he has not yet presented our change order to the board. Hopefully, 10/16/19 meeting. 8.21.19 SantanaL: PerStevensP - Client is waiting on Peter Logan (water superintendent) to approve change order. Stevens is holding invoicing the $10,000 that can be billed currently because he wants to collect more money once change order is approved. he feels client will pay. Stevens requests updates from client every two weeks. 5/7/19 Stevens PEmailed Peter Logan on 4/12,4/23 an 5/7 for updates on status. On 4/12,Peter Logan said he would review that week.No response on 4/23 or 5/7.4/4/19 StevensP - Sent email to CommissionerTom Abatte and Superintendent Peter Logan asking for status of contract increase.Stevens P.-4/2/19 -Billed monthly ,$13,742 can be billed under present contract authorization.3.25.19 Seeking Contract increase for another $34,549.03. (Doubtful to obtain full request ). | [6 empty] | N |  | Y
240 | Design | Stevens, Paul | 16-425-1749 | 800 |  |  |  |  | 22245
241 | Design | Stevens, Paul | 16-425-1749 | 810 |  |  |  |  | 1326
242 | Design | Stevens, Paul | 16-425-1749 | 820 |  |  |  |  | 26017
243 | Design | Stevens, Paul | 18-004-0463 |  | Vill of Old Westbury-2018 | 213100 | 276749 | 2175 | 1397 | 2019-10-25 | 8/28/19 Messina- Inv p/e 08/16/19 Hastings and rds sent out.06/20/19-Inv p/e 053119 sent out-Hastings and Rds6.11.19 SantanaL: Per Stevens P - This is a write off as it exceeded authorized budget. | [6 empty] | N |  | N
244 | Design | Stevens, Paul | 18-004-0463 | ANDOVE |  |  |  |  | 1397 |  | 4/2/19 (Stevens P )Project complete ,no change orders possible.Write off.
245 | Design | Stevens, Paul | 18-004-0463 | RDS18 |  |  |  |  | 0
246 | Design | Stevens, Paul | 19-011-1686 |  | Vill of Brookville - Roads 2019 | 74600 | 60521 | 0 | 0 | 2019-08-30 | 08/28/19 MessinaS - Inv p/e 08/02/19 sent out. | [6 empty] | N |  | N
247 | Design | Stevens, Paul | 19-011-1686 | 1 |  |  |  |  | 100
248 | Design | Stevens, Paul | 19-011-1686 | 2 |  |  |  |  | -100
249 | Design | Tse, Jason | 13-170-1674 |  | CPWD/WELL 1A AND 2R TREATMENT PLT | 644450 | 850223 | 22883 | 20360 | 2019-07-19 | 12/2/19-Open WIP and AR at At Risk. Ziegler's time might be collectable. 09/20/19 Mike Smith and Al met with Tim Doyle and they advised they are currently reviewing the invoice, but feel some/most of the items are not valid. Inv 1317004 was revised to 191,808.31 reflecting the credit adj for 100 hp motor issue of $28,025.00 and sent out. Remaining time on the WIP ($34,497) is not billable. | [6 empty] | N |  | Y
250 | Design | Tse, Jason | 13-170-1674 | 800 |  |  |  |  | 20461
251 | Design | Tse, Jason | 13-170-1674 | 801 |  |  |  |  | -101
252 | Design | Tse, Jason | 17-262-1702 |  | MASS WD/LITTLE MAY BOOSTER P.S. UPGRADE | 68000 | 65899 | 598 | 598 | 2019-12-31 | 11.11.19 SantanaL: Current WIP 597.69 and AR of $780.38 – Needs to be written off per Jason Tse (1,378.07) - job completed 9.19.19 SantanaL Invoice in the amoutn of $4,220.14. was sent to client on 8/20/19.09/09/19 TseJ: Project complete. Invoices from 4/3/19 and prior should have been written off.08/26/19 TseJ: Spoke to Stan Carey/MWD and will get board approval for full amount $4,220.14. 08/20/19 Messina - Inv thru 08/02/19 emailed to client.7/25/19 - TseJ: Hold bill until 8/2/19 and bill out WIP on Phase 803 Task 003. |  | 780 |  |  |  |  | N |  | N
253 | Design | Tse, Jason | 17-262-1702 | 803 |  |  |  |  | 598
254 | Design | Tse, Jason | 17-262-1702 | [10 empty] | 540 | 277705 | 2017-11-28 | 09/09/19 TseJ: Project complete. Invoices from 4/3/19 and prior should have been written off.08/05/19 According to John Waltz's notes in the project review, Inv 277705 should be written off.
255 | Design | Tse, Jason | 17-262-1702 | [10 empty] | 240.38 | 1726205 | 2019-04-02
256 | Design | Tse, Jason | 17-263-1674 |  | CPWD/SCADA PHASE 1 | 24000 | 25747 | 0 | 0 | 2019-06-28 |  |  | 2728 |  |  |  |  | N |  | Y
257 | Design | Tse, Jason | 17-263-1674 | [10 empty] | 1772.13 | 1726302 | 2019-01-21 | 11.11.19 SantanaL: Per JasonTse - this projects links to 13-170-1674 - most likely this amount will need to be written off.9/9/19 TseJ: Spoke to Tim Doyle/CPWD on 9/3/19 on invoicing status with no update. Payment on hold without explanation.8/14/19 TseJ: Spoke to Theresa AlexandroCPWD on status update for resubmitted invoice and was advised it will be presented at tonight's board meeting with update to follow.
258 | Design | Tse, Jason | 17-263-1674 | [10 empty] | 955.38 | 1726303 | 2019-07-31 | 11.11.19 SantanaL: Per JasonTse - this projects links to 13-170-1674 - most likely this amount will need to be written off.9/9/19 TseJ: Spoke to Tim Doyle/CPWD on 9/3/19 on invoicing status with no update. Payment on hold without explanation.8/14/19 TseJ: Spoke to Theresa AlexandroCPWD on status update for invoice dated 7/31/19 and was advised it will be presented at tonight's board meeting with update to follow.
259 | Design | Tse, Jason | 18-060-1674 |  | CPWD,Design Phase Employee Break Rm | 9600 | 8318 | 0 | 0 | 2018-05-11 |  |  | 8318 |  |  |  |  | N |  | Y
260 | Design | Tse, Jason | 18-060-1674 | [10 empty] | 8318.21 | 1806001 | 2018-07-17 | 11.11.19 SantanaL: Per JasonTse - this projects links to 13-170-1674 - most likely this amount will need to be written off.9/9/19 TseJ: Spoke to Tim Doyle/CPWD on 9/3/19 on invoicing status with no update. Payment on hold without explanation.8/14/19 TseJ: Spoke to Theresa AlexandroCPWD on status update for resubmitted invoice and was advised it will be presented at tonight's board meeting with update to follow.
261 | Design | Tse, Jason | 18-319-2017 |  | Castella Imports Tank Replacements | 3200 | 3002 | 44 | 44 | 2019-08-30 | 12/11/19 TseJ: Job completed. Client should not be billed for remaining $43.89. LiRo has not received review response from SCDPW since resubmission on 4/22/19 and have no further update to provide to client.07/25/19 TseJ: As per Stephanie Trapani, 7/15/19 mail check returned and mailed again 7/24/19.07/23/19 TseJ: Castella Imports mailed out $4,077.36 on 7/15/19 as per Stephanie Trapani from Castella.07/02/19 MessinaS 2.5 hrs left on wip billed out.7/9/19 TseJ: Advised Nicole Morello LiRo does not take credit card payments, but will accept check payable to LiRo Engineers in Syosset.7/2/19 TseJ: Nicole Morello contacted her finance department and awaiting update.7/1/19 TseJ: Follow up email to Nicole Morello on Invoice 1831901R for $2,668.68. Bill WIP to date.06/03MessinaS - 2.5 hour on wip-Jason out till 06/28.5/23/19 TseJ: Nicole Morello to check with her finance department and get back.5/21/19 TseJ: Follow up email to Nicole Morello on payment status. No response.5/16/19 TseJ: Left voicemail and follow up email to Nicole Morello on payment status.041919MessinaS - First invoice voided and revised P/E0 04/12/19 and sent out..4/11/19 TseJ: Will void first invoice and invoice all work through pay period 4/12/19 next week.3/28/19 TseJ: Need to follow up with SCDHS and SCDPW for their comments on project. | [6 empty] | N |  | N
262 | Design | Tse, Jason | 18-319-2017 | 1 |  |  |  |  | 44
263 | Design | Tse, Jason | 19-179-0383 |  | SCDPW Feasibility Study Wastewater Mgmt | 194891 | 19705 | 45325 | 11001 | 2019-10-11 | 11/4/19 TseJ: Invoice No. 002 submitted for $10,539.00.09/24/19 Messina-Invoice to be emailed to client thru 08/30/19-not all of wip billed due to milestones on certain phases.9/20/19 TseJ: Invoices need to be submitted to Raftelis by 1st of each month. | [6 empty] | N | 2019-01-23 | N
264 | Design | Tse, Jason | 19-179-0383 | 1 |  |  |  |  | 0
265 | Design | Tse, Jason | 19-179-0383 | 2 |  |  |  |  | 9225
266 | Design | Tse, Jason | 19-179-0383 | 4 |  |  |  |  | 1776
267 | Design | Upadhyay, Anurag | 17-172-0272 |  | NYCDOT Total Design and CSS Cedarview Br | 246307 | 24732 | 122237 | 121848 | 2019-08-31 | 11/30/19-Anurag is working with DOT to utilize the allowances in the contract to bill for some of the overruns. At risk $25,000. 7/20/19-Hutteman-Subhash and Peter Vysotsky were managing the project. Subhash was charging excessive time to the project to get the sub-agreements in place and coordinating with NYCDOT. His rate of over $95/hr could not be supported by the project. I had to hold a significant number of hours on the first invoice to be within the budgeted amounts for the individual tasks. | [6 empty] | N |  | Y
268 | Design | Upadhyay, Anurag | 17-172-0272 | A |  |  |  |  | 22066
269 | Design | Upadhyay, Anurag | 17-172-0272 | B |  |  |  |  | 7836
270 | Design | Upadhyay, Anurag | 17-172-0272 | BUDGET |  |  |  |  | -3132
271 | Design | Upadhyay, Anurag | 17-172-0272 | C |  |  |  |  | 32655
272 | Design | Upadhyay, Anurag | 17-172-0272 | D |  |  |  |  | 5229
273 | Design | Upadhyay, Anurag | 17-172-0272 | E |  |  |  |  | 57194
274 | Design | Upadhyay, Anurag | 19-131-0272 |  | NYCDOT Total Design and CSS for Rehab o | 389839 | 0 | 144120 | 108836 |  | 12/12/19 Anurag Upadhyay: NYCDOT notified that LiRo's SI-2000 packet is approved and we are OK to submit the first invoice upto the amount of $100,000. The invoice is anticipated to be prepared in the month of December and submitted to NYCDOT.11.11.19 SantanaL: Per Anurag U. we are unable to clear WIP of 122,237.46 until January, we may be able to bill $75,000 by end of November if SI2000 submittal is approved.10-22-19 - Anurag Upadhyay : Cause of invoice delay: NYCDOT needs to approve SI-2000 packet of the consultant team (new client process), before invoicing may begin. SI-2000 process is fairly new process of NYCDOT and NYCDOT administration is still in the process of implementing it smoothly. SI-2000 packet submitted to NYCDOT on 8-7-19. Received comments on 8-30-19 on SI-2000 to be incorporated for resubmission on 9-10-19. Again received comments on SI-2000 and Resubmitted SI-2000 packet with second Rivisions on 10-10-19. It is anticipated to be approved by 11-8-19.Date invoice is expected to be issued: 11-15-19Projected amount of next invoice: $77,967 (Till November 1st Work percentage finish (20% of total project)PM Action Plan: Follow up with NYCDOT on approval of SI-2000 and start billing monthly from then onwards, as per the NYCDOT rule of billing only upto the percent complete project. | [6 empty] | N |  | N
275 | Design | Upadhyay, Anurag | 19-131-0272 | 1 |  |  |  |  | 108836
276 | Design | Weber, Anthony | 15-095-0418 |  | TOH Newbridge Road Park Shoreline Beach | 47000 | 54591 | 0 | 0 | 2019-09-13 |  |  | 21133 |  |  |  |  | N |  | N
277 | Design | Weber, Anthony | 15-095-0418 | [10 empty] | 16592.69 | 9 | 2019-02-28 | 12/11/19 Anthony Weber: Invoice is pending approval by Town. Followed up with client in Novement on payment status, waiting for their response.7/9/2019 SantanaL: KwaschynM wrote on 7/2/19 " Awaiting response from Town on the status of the AR"6/11/2019 SantanaL: Per PM "According to John L this project was cancelled. The project appears to have re-started" there is a potential Risk on this project in the amount of $17,000.
278 | Design | Weber, Anthony | 15-095-0418 | [10 empty] | 4540.47 | 10 | 2019-07-03 | 12/11/19 Anthony Weber: Invoice is pending approval by Town. Followed up with client in Novement on payment status, waiting for their response.
279 | Design | Weber, Anthony | 17-129-0248 |  | NCDPW Grand Ave Complete Sts Design Svc | 429051 | 343860 | 52607 | 49142 | 2019-09-30 | The final invoice of $49,683.3 can be billed until the final design is accepted. It is expected between 12/15 to 12/31/2019. | [6 empty] | N |  | N
280 | Design | Weber, Anthony | 17-129-0248 | IA |  |  |  |  | 350
281 | Design | Weber, Anthony | 17-129-0248 | IIB |  |  |  |  | 44337
282 | Design | Weber, Anthony | 17-129-0248 | IIE |  |  |  |  | 4456
283 | Design | Weber, Anthony | 17-164-0089 |  | City of Yonkers-Grassy Sprain Dam Ph 3 R | 57580 | 34089 | 7680 | 7437 | 2019-06-07 | 11.11.19 SantanaL: Per AnthonyW. Invoicing by end of month --Open WIP 7,436.687/9/19 SantanaL: KwaschynM wrote on 7/2/19 " Outstanding WIP is being billed $4,123" | [6 empty] | N |  | N
284 | Design | Weber, Anthony | 17-164-0089 | CONINS |  |  |  |  | 6783
285 | Design | Weber, Anthony | 17-164-0089 | CSS |  |  |  |  | 654
286 | Design | Weber, Anthony | 18-340-0270.01 |  | NYCP&R - Little Bush Playground | 47663 | 41681 | 3369 | 3369 | 2019-06-28 | 12/10/19 - Anthony Weber - No changes. See below comment.08/06/19 - Anthony Weber - Per On-Call agreement, Final 10% design fee to be held until completion of Construction. Date Invoice is expected: TBD. Amount of next invoice: $3,966.2707/22/19MessinaS - sent out invoice thru 06/28/1906/04/19 MessinaS-spoke with Anthony Weber, wait till next month.04/22/19- MessinaS - waiting for new phase to be opened and labor transfers.2/25/19 - Anthony Weber - Hold off on invoice until project completion.Date invoice is expected to be issued: 4/23/19Projected amount of next invoice: $39,662.73 | [6 empty] | N |  | N
287 | Design | Weber, Anthony | 18-340-0270.01 | 2 |  |  |  |  | 3369
288 | Design | Weber, Anthony | 18-340-0270.04 |  | NYCP&R - Recon Poor Richard's Playground | 41057 | 33217 | 317 | 317 | 2019-10-18 | 12/10/19 - Anthony Weber - Per On-Call agreement, Final 10% design fee to be held until completion of Construction. Date Invoice is expected: TBD. Amount of next invoice: $3,305.679/20/19 - Anthony Weber - Per On-Call agreement, waiting for completion of next milestone to bill 15% design fee. Date Invoice is expected: TBD. Amount of next invoice: $4,958.5108/06/19 - Anthony Weber - 75% design fee invoice plus allowances is expected to be issued at end of month. Projected amount of invoice: $38,106.3406/04MessinaS- Hold off till June Cycle. | [6 empty] | N |  | N
289 | Design | Weber, Anthony | 18-340-0270.04 | 3 |  |  |  |  | 317
290 | Design | Weber, Anthony | 18-340-0270.05 |  | NYCP&R Recon William E Sheridan Playgrou | 113063 | 0 | 29812 | 18221 |  | 12/10/19 - Anthony Weber - Per On-Call agreement, waiting for completion of next milestone to bill 25% design fee. Date Invoice is expected: TBD. Amount of next invoice: $27,123.17 | [6 empty] | N |  | N
291 | Design | Weber, Anthony | 18-340-0270.05 | 1 |  |  |  |  | 13642
292 | Design | Weber, Anthony | 18-340-0270.05 | 2 |  |  |  |  | 3571
293 | Design | Weber, Anthony | 18-340-0270.05 | 3 |  |  |  |  | 1008
294 | Design | Weber, Anthony | 18-340-0270.06 |  | NYCP&R Recon Synthetic Turf Harlem River | 49711 | 0 | 10266 | 3474 |  | 12/10/19 - Anthony Weber - Next milestone will be TBD. Amount of next invoice: 25% Design Fee | [6 empty] | N |  | N
295 | Design | Weber, Anthony | 18-340-0270.06 | 1 |  |  |  |  | 3474
296 | Design | Weber, Anthony | 18-340-0270.07 |  | NYCP&R Recon Ballfield 3 McCarren Park | 116123 | 0 | 20954 | 3898 |  | 12/10/19 - Anthony Weber - Per On-Call agreement, waiting for completion of next milestone to bill 25% design fee. Date Invoice is expected: TBD. Amount of next invoice: $29,030.63 | [6 empty] | N |  | N
297 | Design | Weber, Anthony | 18-340-0270.07 | 1 |  |  |  |  | 3898
298 | Design | Weber, Anthony | 19-198-0416.01 |  | TOH Parks - Harbor Isle Park Retaining W | 13500 | 0 | 7505 | 7375 |  | 12/10/19 - Anthony Weber - Waiting for completion of Design phase to invoice. Date Invoice is expected: End of Month. Amount of next invoice: $10,870.44 | [6 empty] | N |  | N
299 | Design | Weber, Anthony | 19-198-0416.01 | 1 |  |  |  |  | 1546
300 | Design | Weber, Anthony | 19-198-0416.01 | 2 |  |  |  |  | 5829
301 | Design | Weber, Anthony | 19-250-0248.01 |  | NCDPW-TO5 Long Beach Rd,Oceanside,Draina | 185540 | 0 | 14163 | 325 | [8 empty] | N |  | N
302 | Design | Weber, Anthony | 19-250-0248.01 | 1 |  |  |  |  | 325
303 | Design | Wendel, Thomas | 16-410-1238 |  | CORNERSTONE PROP/CORNERSTONE TOWNHOUSES | 3500 | 15540 | 0 | 0 |  |  |  | 15540 |  |  |  |  | Y | 2019-10-16 | Y
304 | Design | Wendel, Thomas | 16-410-1238 | [10 empty] | 5040 | 276316 | 2017-02-14 | 12/2/19-Claim filed, no response yet from the court on acknowledgement of the claim. contract has not been located but supposedly existed. The agreed upon fee was $3,500, however, there was $15,540 in efforts. To date, no payment has been rendered for any portion of the project.
305 | Design | Wendel, Thomas | 16-410-1238 | [10 empty] | 4200 | 276451 | 2017-03-20 | Billed through contract fee. Awaiting response from Tom Wendal and client
306 | Design | Wendel, Thomas | 16-410-1238 | [10 empty] | 1120 | 276563 | 2017-04-13 | Billed through contract fee. Awaiting response from Tom Wendal and client
307 | Design | Wendel, Thomas | 16-410-1238 | [10 empty] | 4620 | 276686 | 2017-05-08 | Billed through contract fee. Awaiting response from Tom Wendal and client
308 | Design | Wendel, Thomas | 16-410-1238 | [10 empty] | 560 | 277216 | 2017-07-31 | 04.25.2019 WendelT: Same comment as below.04.03.2019 WendelT: Client does not respond to phone or email, last attempts 07/2018. Suggest this be turned over to our collections people. Project is complete. Comment applies to all listed invoices.
309 | Design | Wijewardena, Sunil | 02-75-0463 |  | OW/JUNE | 427500 | 329715 | 6979 | 153 | 2019-10-25 | 11/18/19 (WijewardenaS) : Billed in every 3 months.07/10/19(MessinaS)-Inv p/e 6/28/19 sent out. Last Invoice - 11/5/19 ($38,770.10)Next Invoice - 2/1/20 WIP since last invoice -Completed and can be invoiced -Task797 (100%) In progress - | [6 empty] | N |  | N
310 | Design | Wijewardena, Sunil | 02-75-0463 | 600 |  |  |  |  | 153
Total | [5 empty] | 19235837 | 14918268 | 1857425 | 1508043 | [6 empty] | 60822 | 696747