## PHR WITH WIP & AR
[7 empty] | Field-REI : WIP and AR Tracking |  |  |  | 2019-12-16 |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Project Name | Contract Amount | LiRo Billed Fee | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Field-REI | Abreu, Raul | 18-184-0238 |  | TBTA Design-Build of Elec/Mech Rehab RFK | 956813 | 271330 | 99272 | 22554 | 2019-10-31 | [7 empty] | N |  | N
2 | Field-REI | Abreu, Raul | 18-184-0238 | 1 |  |  |  |  | 22554
3 | Field-REI | Bailey, Michael | 10-52-200G |  | NYCEDC-Replace Water Siphons | 9043356 | 8937484 | 44564 | 0 | 2019-10-31 | 1-17-19, We have submitted Supplemental No. 5 for $670K. This will take us through April 2020. It is in process at EDC. Will take 8-12 weeks. | 33 | [5 empty] | N |  | N
4 | Field-REI | Bailey, Michael | 10-80-100 |  | NYSDOT Slosson Avenue to Victory Bouleva | 5817889 | 5507534 | 0 | 0 | 2018-03-30 | 4/24/18, DLM - Final invoice submitted 4/13. |  | 458 |  |  |  |  | N |  | N
5 | Field-REI | Bailey, Michael | 10-80-100 | [10 empty] | 458.44 | 33 | 2017-11-30 | 2/7/18-invoice in review with DOT. this is an invoice that was reqeusted, but is a credit against Longi. _rdc
6 | Field-REI | Bailey, Michael | 13-049-0296 |  | NYSTA Construction of New Tappan Zee Br | 45534253 | 27921529 | 527228 | 175515 | 2019-09-13 | [7 empty] | N |  | N
7 | Field-REI | Bailey, Michael | 13-049-0296 | E014.4 |  |  |  |  | 180
8 | Field-REI | Bailey, Michael | 13-049-0296 | E335 |  |  |  |  | 50834
9 | Field-REI | Bailey, Michael | 13-049-0296 | HOT |  |  |  |  | 1733
10 | Field-REI | Bailey, Michael | 13-049-0296 | LANDIN |  |  |  |  | 25036
11 | Field-REI | Bailey, Michael | 13-049-0296 | MAG19 |  |  |  |  | 1080
12 | Field-REI | Bailey, Michael | 13-049-0296 | STAFF |  |  |  |  | 96653
13 | Field-REI | Bailey, Michael | 15-133-0324 |  | PANYNJ Performance of Expert Professiona | 536000 | 529771 | 209910 | 209910 | 2018-08-31 | 8-16-18, MB spoke with Angela Calabrese of P.A. Revised award letter increasing funding to be issued by 8/24.10-10-18, Supplemental being processed. Should be received by 10/12/18. | [6 empty] | N |  | N
14 | Field-REI | Bailey, Michael | 15-133-0324 | 1 |  |  |  |  | 209910
15 | Field-REI | Bailey, Michael | 16-042-0272 |  | NYCDOT REI Svcs Metropolitan Ave & Fresh | 3549869 | 2009708 | 8809 | 4305 | 2019-06-21 | [7 empty] | N |  | N
16 | Field-REI | Bailey, Michael | 16-042-0272 | STAFF |  |  |  |  | 4305
17 | Field-REI | Bailey, Michael | 16-063-0272 |  | NYCDOT REI Recon Park Ave | 3301768 | 2595006 | 176291 | 35083 | 2019-09-27 | 1-16-19, The supplemental was reviewed by DOT and submitted on 12/31/18 for $1,538,000.3-4-19, Submittals have been submitted and are currently being processed. | [6 empty] | N |  | N
18 | Field-REI | Bailey, Michael | 16-063-0272 | STAFF |  |  |  |  | 35083
19 | Field-REI | Bailey, Michael | 16-342-0275 |  | NYC EDC - On Call Civil Engineering | 108627 | 88552 | 7776 | 7533 | 2019-08-31 | [7 empty] | N |  | N
20 | Field-REI | Bailey, Michael | 16-342-0275 | 5 |  |  |  |  | 680
21 | Field-REI | Bailey, Michael | 16-342-0275 | PIER42 |  |  |  |  | 6853
22 | Field-REI | Bailey, Michael | 17-079-0272 |  | NYCDOT-REI Svcs Atlantic Ave Bridge | 5526137 | 3080976 | 104145 | 0 | 2019-11-08 |  |  | 1025 |  |  |  |  | N |  | N
23 | Field-REI | Bailey, Michael | 17-079-0272 | [10 empty] | 996.76 | 9 | 2019-02-27
24 | Field-REI | Bailey, Michael | 17-079-0272 | [10 empty] | 28.26 | 12 | 2019-08-06
25 | Field-REI | Bailey, Michael | 17-125-0275 |  | NYCEDC New Stapleton Waterfront PH2/PH3 | 6542823 | 370441 | 6831 | 693 | 2019-09-30 | [7 empty] | N |  | N
26 | Field-REI | Bailey, Michael | 17-125-0275 | P-FEMA |  |  |  |  | 266
27 | Field-REI | Bailey, Michael | 17-125-0275 | PRECON |  |  |  |  | 426
28 | Field-REI | Bailey, Michael | 18-249-0291 |  | NYSDOT CI Svcs, Arthur Sheridan Expwy | 6426868 | 1890126 | 207446 | 0 | 2019-10-25 |  | 0 | [5 empty] | N |  | N
29 | Field-REI | Bradley, Daniel | 11-66-0275 |  | NYCEDC Hudson Park Boulevard and Streets | 4255191 | 4006704 | 9796 | 4388 | 2019-06-30 | 11-22-19: Requistion 48 through 11-30-19 anticipated to be submitted 12-15-19. | [6 empty] | N |  | N
30 | Field-REI | Bradley, Daniel | 11-66-0275 | CONSTR |  |  |  |  | 3380 |  | 8-15-18 Requisition for period ending 6/30/18 was submitted to EDC on 7/13 including $37,390.31 in staffing.
31 | Field-REI | Bradley, Daniel | 11-66-0275 | PHASE2 |  |  |  |  | 1008 |  | 8-15-18 Requisition for period ending 6/30/18 was submitted to EDC on 7/13 including $37,390.31 in staffing.
32 | Field-REI | Bradley, Daniel | 11-66-0275 | [10 empty] | -60 | 40 | 2017-03-08
33 | Field-REI | Bradley, Daniel | 11-66-0275 | [10 empty] | 0.01 | 41 | 2017-07-10 | Requisition for period ending 6/30/18 was submitted to EDC on 7/13 including $37,390.21 in staffing.
34 | Field-REI | Bradley, Daniel | 11-66-0275 | [10 empty] | 0.01 | 44 | 2018-11-06
35 | Field-REI | Bradley, Daniel | 12-100-0275 |  | NYCEDC Highline Section 3 | 1798009 | 1768738 | 0 | 0 | 2019-06-30 | 11-22-19: Submitted requisition for period ending 06-30-19 on 07-10-19. EDC processing Amendment to facilitate payment anticipated 12-31-19. Job is complete. Requested accounting to write off all remaining reimbursables on WIP. Accounting replied:There is still $13K in expenses on the wip that will need to be billed, moved or approved for write off before the project can be set to dormant.I requested accounting to provide receipts for all expenses for my review. Awaiting response. |  | 1783 |  |  |  |  | N |  | N
36 | Field-REI | Bradley, Daniel | 12-100-0275 | [10 empty] | -267.58 | 24 | 2018-06-30
37 | Field-REI | Bradley, Daniel | 12-100-0275 | [10 empty] | 2050.23 | 26 | 2019-07-10
38 | Field-REI | Bradley, Daniel | 19-113-0275.01 |  | NYCEDC - On Call Civil & Res Eng Retaine | 905967 | 0 | 0 | 1274 | 2019-11-30 | 10-22-19: will submit req. through 10-31 by 11-15. | [6 empty] | N |  | N
39 | Field-REI | Bradley, Daniel | 19-113-0275.01 | 1 |  |  |  |  | 1274
40 | Field-REI | Calpin, Gerald | 15-039-0098 |  | CTDOT Rehabilitation of Bridge 00507 | 141300 | 97586 | 0 | 0 | 2016-12-23 | 9/23/19-Feb. 2019 retainage was billed (late) but once CTDOT finishes with their Audit, we should receive payment for the Retainage that was released. Per J. Calpin - The one on the WIP/AR report (Bridge 00507) is the Tectonic project and we were told we will get it when they audit it, so we can leave it for now. |  | 1331 |  |  |  |  | N |  | N
41 | Field-REI | Calpin, Gerald | 15-039-0098 | [10 empty] | 942.38 | 1 | 2015-11-18 | 4/15/19-released retainage. Informed by client that there is a CT audit in process. Retainage will be released once the audit is complete, no ETA. _rdc
42 | Field-REI | Calpin, Gerald | 15-039-0098 | [10 empty] | 248.54 | 2 | 2015-12-22
43 | Field-REI | Calpin, Gerald | 15-039-0098 | [10 empty] | 13.81 | 3 | 2016-07-21
44 | Field-REI | Calpin, Gerald | 15-039-0098 | [10 empty] | 126 | 4 | 2017-03-21
45 | Field-REI | Calpin, Gerald | 17-069-0272 |  | NYCDOT REI Protective Coating Belt | 1726974 | 917065 | 644 | 430 | 2019-11-30 | 8-17-18, Contacted client. Waiting on payment of previous invoices before we can submit invoice for this WIP. Invoice #2 being processed and should be sent to Fiscal Affairs 8/17 for payment. Likely 1-2 weeks. | [6 empty] | N |  | N
46 | Field-REI | Calpin, Gerald | 17-069-0272 | COATIN |  |  |  |  | 430
47 | Field-REI | Eckhoff, James | 13-090-0275 |  | NYCEDC Green Infrastructure | 2851812 | 2640248 | 64340 | 63668 | 2019-11-30 | [7 empty] | N |  | N
48 | Field-REI | Eckhoff, James | 13-090-0275 | STAFF |  |  |  |  | 63668
49 | Field-REI | Eckhoff, James | 18-166-0275 |  | NYCEDC Lower Concourse Improvements | 5212295 | 232027 | 22590 | 8137 | 2019-09-04 | 8-16-18, Project is Lump Sum - working w/M. Duran on Invoice #1 | [6 empty] | N |  | N
50 | Field-REI | Eckhoff, James | 18-166-0275 | 1 |  |  |  |  | 7805
51 | Field-REI | Eckhoff, James | 18-166-0275 | 4 |  |  |  |  | 332 |  | 8-16-18, Project is Lump Sum - working w/M. Duran on Invoice #1
52 | Field-REI | Gadbois, Joseph | 16-035-0816 |  | TGI Facilities Mngmt and CM Services | 11717321 | 9377372 | 264904 | 23776 | 2019-12-31 | CM020 8-16-18, Related to air monitoring testing under Chris Zanoni. The proposal for these services were lump sum and they were to be billed as a vendor to LiRo Program & Construct. Mgmt. GI staff did not charge tothis work order.CM022 8-16-18, Related to Bldg. 400 artwork installation. The proposal for these services were lump sum and they were to be billed as a vendor to LiRo Program & Construct. Mgmt. GI staff did not charge to this work.5-6-19, Phase FM001, These individuals on Open WIP should have not billed under this Project Code. They were to bill as a vendor to LiRo and TGI under their own Project Code and invoice us separately. | [6 empty] | N |  | N
53 | Field-REI | Gadbois, Joseph | 16-035-0816 | CM020 |  |  |  |  | 5972
54 | Field-REI | Gadbois, Joseph | 16-035-0816 | CM022 |  |  |  |  | 1048
55 | Field-REI | Gadbois, Joseph | 16-035-0816 | CM026 |  |  |  |  | 17788
56 | Field-REI | Gadbois, Joseph | 16-035-0816 | FM001 |  |  |  |  | -1031
57 | Field-REI | Gadbois, Joseph | 16-035-0816 | [10 empty] | -0.01 | 0OPS-34-JUNE | 2019-07-24
58 | Field-REI | Gadbois, Joseph | 16-035-0816 | [10 empty] | -14999 | CAP-19-MARCH | 2018-04-26 | 9-21-18, Related to B&G Invoice, TGI has paid LiRo for Invoice. Payment to B&G being held until B&G completes work.
59 | Field-REI | Gray, Laura | 16-059-0238 |  | TBTA As Needed CA INSP and Support Svcs | 5767475 | 1994766 | 361435 | 3306 | 2019-10-11 |  |  | 0 |  |  |  |  | N |  | N
60 | Field-REI | Gray, Laura | 16-059-0238 | TSK28T |  |  |  |  | 3306
61 | Field-REI | Gray, Laura | 16-059-0238 | [10 empty] | 0.03 | 19 | 2019-03-28
62 | Field-REI | Grubman, Jonathan | 15-012-0275 |  | NYCEDC GI CM Services Westchester Creek | 5231943 | 442890 | 165649 | 38741 | 2019-08-31 | 10-10-18, Billing being prepared through 10/12/18. | [6 empty] | N |  | N
63 | Field-REI | Grubman, Jonathan | 15-012-0275 | STAFF |  |  |  |  | 38741
64 | Field-REI | Khachmanian, John | 08-70-205 |  | HWCRQ01, Requirements Contract for REI S | 6059254 | 4961927 | 0 | 0 | 2017-05-31 |  |  | 55271 |  |  |  |  | N |  | N
65 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 2697.95 | 000010BAILEY | 2018-12-31 | 9/18/19-John K. advised that all invoices (retainage and hours) have been approved and should be paid in Oct 2019.
66 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 29921.56 | 000014BAILEY | 2014-08-19
67 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 1297.76 | 000015BAILEY | 2015-12-31
68 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 21353.72 | 000016BAILEY | 2016-12-19
69 | Field-REI | Khachmanian, John | 12-029-0265 |  | NYCDDC Trunk Water Main 48th Street | 8591185 | 6754470 | 2761 | 0 | 2019-10-25 |  |  | 3451 |  |  |  |  | N |  | N
70 | Field-REI | Khachmanian, John | 12-029-0265 | [10 empty] | 3500.01 | 28 | 2016-10-04 | 8-6-18, No issues.
71 | Field-REI | Khachmanian, John | 12-029-0265 | [10 empty] | -49.13 | 39 | 2018-09-12 | 10-4-18, No issues10-31-18, Last invoice covered 08-31-18.
72 | Field-REI | Khachmanian, John | 12-056-0265 |  | NYCDDC Requirements Contract for REI Ser | 13362946 | 8638107 | 2259069 | 2156260 | 2019-09-27 |  |  | 782502 |  |  |  |  | N |  | N
73 | Field-REI | Khachmanian, John | 12-056-0265 | 3 |  |  |  |  | 555215
74 | Field-REI | Khachmanian, John | 12-056-0265 | 4 |  |  |  |  | 1601086
75 | Field-REI | Khachmanian, John | 12-056-0265 | 5 |  |  |  |  | -42
76 | Field-REI | Khachmanian, John | 12-056-0265 | [10 empty] | 13236.4 | 12 | 2018-12-12 | 7-15-19, Last invoiced 12/8/17. Completed.8/28/19, Task 1, Last invoice covered 12/7/18.8/28/19, Task 3, Last invoice covered 8/4/17.8/28/19,Task 4, Last invoice covered 12/8/17.
77 | Field-REI | Khachmanian, John | 12-056-0265 | [10 empty] | 769265.55 | 0000000009RC | 2017-10-25 | 10-4-18, Task 1, Close out. No issues.10-4-18, Task 3, Last invoice covered 8/4/17.10-4-18, Task 4, Last invoice covered 12/8/17.10-4-18, Task 5, Completed. Final Payment submitted. Last invoice covered 8/31/18.10-31-18, Same comments as 10-4-18 (above) for all Tasks.
78 | Field-REI | Khachmanian, John | 13-012-0265 |  | NYCDDC Times Sq. Reconstruction REI | 8837264 | 7920426 | 159495 | 33171 | 2019-09-27 |  |  | 8374 |  |  |  |  | N |  | N
79 | Field-REI | Khachmanian, John | 13-012-0265 | DECLAR |  |  |  |  | 37096
80 | Field-REI | Khachmanian, John | 13-012-0265 | STAFF |  |  |  |  | -3925
81 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 1000 | 7 | 2014-08-19 | 5/15-15- Cut for $1000 is temporary and is rebilled with each invoice- SC
82 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 32.5 | 8 | 2014-06-19 | 5/15-15- Cut for $32.50 is temporary and is rebilled with each invoice- SC
83 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 6000 | 11 | 2015-07-21
84 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 1341.42 | 12 | 2015-10-09
85 | Field-REI | Khachmanian, John | 15-101-0265 |  | NYCDDC Albert Road Area Ozone Park | 5961160 | 4186918 | 190822 | 4469 | 2019-10-11 | 8-6-18, An invoice is being submitted for processing 8/31/18.10-4-18, Awaiting the check to be vouchered.10-31-18, Waiting for the check to be vouchered.2-13-19, Waiting for the check to be vouchered.4-8-19, Waiting for the check to be vouchered.7-15-19 & 8/28/19, Waiting for the check to be vouchered. | [6 empty] | N |  | N
86 | Field-REI | Khachmanian, John | 15-101-0265 | STAFF |  |  |  |  | 4469
87 | Field-REI | Khachmanian, John | 16-083-0265 |  | NYCDDC Reconstruction of Leonard Street | 4876343 | 3287923 | 224999 | 50673 | 2019-09-27 | 8-6-18, An invoice is being submitted for processing 8/31/18.10-4-18, Awaiting the check to be vouchered.10-31-18, Awaiting the check to be vouchered.2-13-19, Waiting for the check to be vouchered.4-8-19, Waiting for the check to be vouchered.7-15-19 & 8/28/19, Waiting for the check to be vouchered. | [6 empty] | N |  | N
88 | Field-REI | Khachmanian, John | 16-083-0265 | STAFF |  |  |  |  | 50673
89 | Field-REI | Khachmanian, John | 17-014-0265 |  | NYCDDC 2017 Large Requirement Contract | 19887602 | 7084315 | 1883582 | 1218453 | 2019-10-25 | 9/19/19-Waiting for the Change order of the amount $2,787,404.84 to be registered. Project was switched from Requirement Contract to Stand Alone Contract |  | 242531 |  |  |  |  | N |  | Y
90 | Field-REI | Khachmanian, John | 17-014-0265 | 2 |  |  |  |  | 95626
91 | Field-REI | Khachmanian, John | 17-014-0265 | 5 |  |  |  |  | 780286
92 | Field-REI | Khachmanian, John | 17-014-0265 | ASTORI |  |  |  |  | 342541
93 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 598.72 | 00000006WARD | 2018-09-12 | 10-4-18, Task 2, No Issues; Task 3, No issues; Task 4, No issues.10-31-18, Task 2, Last Invoice covered 8-31-18.7-15-19, Task 2, Last Invoice covered 5-10-19.
94 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 3056.19 | 000009PELHAM | 2019-05-31 | 7-15-19, Last invoice covered 5-10-19.
95 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 8882.72 | 00003ASTORIA | 2018-07-20 | 7/30/18 JK No issues8-6-18, Last invoice covered 7/6/18; Task 2, No Issues; Task 3, No issues; Task 4, No issues.10-4-18, Last Invoice covered 8/31/18.
96 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 47946.72 | 00005ASTORIA | 2019-06-03
97 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 182046.73 | 00006ASTORIA | 2019-07-31 | 8/28/19, Task 1, Last invoice covered 7/5/19.
98 | Field-REI | Khachmanian, John | 19-066-0093 |  | Columbia Univ Manhattanville Phase IV | 249588 | 134996 | 43541 | 897 | 2019-10-11 | [7 empty] | N |  | N
99 | Field-REI | Khachmanian, John | 19-066-0093 | 1 |  |  |  |  | 897
100 | Field-REI | Khachmanian, John | 19-230-0265 |  | NYCDDC- Coastal Resiliency Project | 61685993 | 0 | 44965 | 9446 | [8 empty] | N |  | N
101 | Field-REI | Khachmanian, John | 19-230-0265 | 1 |  |  |  |  | 9446
102 | Field-REI | Kreuzer, Robert | 19-158-0134 |  | ECDPW 2019 Erie Co CC & CM Program | 195000 | 68948 | 15853 | 0 | 2019-10-11 | 12/2/2019 JW - Next invoice in draft for approximately $15,000.00 to be sent on 12/6. |  | 19802 |  |  |  |  | N |  | N
103 | Field-REI | Kreuzer, Robert | 19-158-0134 | [10 empty] | 19801.59 | 1 | 2019-07-26
104 | Field-REI | Nazzaro, Dennis | 13-116-0015 |  | Amtrak NEC Gateway Improvements | 9765896 | 8536458 | 303030 | 132271 | 2019-08-31 | 09/25/19. Yadira Candelario. Phase I/MOE July 2019 invoice #54 and ESB Invoice #08 were received and applied to the HY Gateway project on 9/23/19 in the amount of $89,050.50. August 2019 invoices were requested from LIRO A/P for processing on 9/24/19 and are still pending. Amtrak payment terms is "Net 60" from Invoice date. | [6 empty] | N |  | N
105 | Field-REI | Nazzaro, Dennis | 13-116-0015 | 2 |  |  |  |  | 88941
106 | Field-REI | Nazzaro, Dennis | 13-116-0015 | 7 |  |  |  |  | 16982 |  | Invoice submitted to Amtrak in Philladelpia on November 13. Payment should be received week of November 25.
107 | Field-REI | Nazzaro, Dennis | 13-116-0015 | STAFF |  |  |  |  | 26349
108 | Field-REI | Pfister, Frank | 18-089-0291 |  | NYSDOT- QM Svcs Bruckner Blvd | 935861 | 348809 | 8902 | 0 | 2019-10-25 | test |  | 0 |  |  |  |  | N |  | N
109 | Field-REI | Pfister, Frank | 18-089-0291 | [10 empty] | 0.01 | 7 | 2019-03-06
110 | Field-REI | Pokorny, Michael | 19-059-2048 |  | OUTFRONT Media | 829464 | 180271 | 275924 | 193402 | 2019-10-31 | [7 empty] | N |  | N
111 | Field-REI | Pokorny, Michael | 19-059-2048 | 1 |  |  |  |  | 193402
112 | Field-REI | Pokorny, Michael | 19-059-2048 | 2 |  |  |  |  | 0
113 | Field-REI | Pokorny, Michael | 19-059-2048 | 3 |  |  |  |  | 0
114 | Field-REI | Valdemira, Vincent | 07-32-200K |  | MTA - No. 7 Line Extension | 20690691 | 20091746 | 155476 | 122897 | 2019-10-31 | 8/21/19-Meetings to resolve previous invoice matters continue to take place with NYCT. |  | 543288 |  |  |  |  | N |  | Y
115 | Field-REI | Valdemira, Vincent | 07-32-200K | CONSTR |  |  |  |  | 122897
116 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 24813.99 | 86 | 2015-06-30 | 9/19/19-Lu approved write off of Rafat time for rate variance and asked Vinny to revise the invoices and submit to the JV for submittal to NYCT. 6/20/19-Vinny Valdemira met with Tom McLaughlin (HDR) and John Milano (Hill) to discuss the cuts made by NYCT over the past year which for LiRo amount to more than $551k. Both JV partners are on board with mounting a challenge to recover more than $1.1M, in cuts, across our team. A letter was sent from Drygulski, on behalf of the JV team to Mark Shiffman stating in very brief terms our objections and requesting a meeting to resolve our differences; for; Project Directors Hourly Rate, Unauthorized Overtime, Unqualified Premium Overtime and Hourly Rate Differential.8/21/19, Cuts of roughly $54K to be made for OT throughout the project. Issue being resolved, and we will be able to recoup the money -it may take some time. The MTA has made another major cut, $74,406.49 (attached memo). This cut is on Premium Time, out of the $76,280.41 submitted for overtime on the bill to date $74,406.49 was disallowed. abCuts that are being disputed per memo to Mark Shillman.
117 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 26513.62 | 87 | 2015-07-13 | 8/21/19, Cuts of roughly $54K to be made for OT throughout the project. Issue being resolved, and we will be able to recoup the money -it may take some time. The MTA has made another major cut, $74,406.49 (attached memo). This cut is on Premium Time, out of the $76,280.41 submitted for overtime on the bill to date $74,406.49 was disallowed. abCuts that are being disputed per memo to Mark Shillman.
118 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 321.62 | 89 | 2015-09-22
119 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 28375.37 | 91 | 2016-08-11
120 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 21047.61 | 92 | 2016-08-11
121 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 241861.47 | 93 | 2016-08-22
122 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 139512.9 | 94 | 2016-10-31
123 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 3125.09 | 95 | 2016-12-30
124 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 12.93 | 96 | 2017-01-09 | 8/21/19, Cuts of roughly $54K to be made for OT throughout the project. Issue being resolved, and we will be able to recoup the money -it may take some time. The MTA has made another major cut, $74,406.49 (attached memo). This cut is on Premium Time, out of the $76,280.41 submitted for overtime on the bill to date $74,406.49 was disallowed. abCuts that are being disputed per memo to Mark Shillman.
125 | Field-REI | Valdemira, Vincent | 07-32-200K | [10 empty] | 57703.27 | 108 | 2019-05-07
126 | Field-REI | Valdemira, Vincent | 08-11-200K |  | East Side Access | 43139247 | 50512192 | 801835 | 0 | 2019-12-31 | 4-26-19, Invoice prepared; waiting for Jacobs. |  | 35040 |  |  |  |  | N |  | N
127 | Field-REI | Valdemira, Vincent | 08-11-200K | [10 empty] | 35039.93 | 133 | 2019-07-26
128 | Field-REI | Valdemira, Vincent | 14-135-0245.01 |  | NYCT Clark Street Tube Rehabilitation | 4347748 | 3980571 | 1215618 | 1184330 | 2019-10-31 | [7 empty] | N |  | Y
129 | Field-REI | Valdemira, Vincent | 14-135-0245.01 | CLOUT |  |  |  |  | 487980
130 | Field-REI | Valdemira, Vincent | 14-135-0245.01 | CONSTR |  |  |  |  | 693488
131 | Field-REI | Valdemira, Vincent | 14-135-0245.01 | PRECON |  |  |  |  | 2861
132 | Field-REI | Valdemira, Vincent | 14-135-0245.02 |  | NYCT CCM Bundle | 4401583 | 3754728 | 1240834 | 979632 | 2019-08-31 | 9/6/19-Waiting for PB to give us okay to submit. | [6 empty] | N |  | N
133 | Field-REI | Valdemira, Vincent | 14-135-0245.02 | A37659 |  |  |  |  | 460414
134 | Field-REI | Valdemira, Vincent | 14-135-0245.02 | A37660 |  |  |  |  | 519218
135 | Field-REI | Valdemira, Vincent | 14-135-0245.02 | [10 empty] | -183.07 | 9 | 2019-04-30 | 6/26/19-last of revisions were sent to Transit 6/25/19. They are going to try to process immediately. _rdc
136 | Field-REI | Valdemira, Vincent | 14-135-0245.03 |  | NYCT-CM for Hurricane Sandy Coney Island | 6644265 | 646198 | 692785 | 540807 | 2019-03-31 | 10/23/19-Liro submitted draft inv 8 to WSP on 10/23/19 to WSP. We are 1 of many subs. Waiting for PPF to be approved-then invoice will be finalized. Will be billed as of 9/30/19. | 203266 | [5 empty] | N |  | N
137 | Field-REI | Valdemira, Vincent | 14-135-0245.03 | C34836 |  |  |  |  | 323446
138 | Field-REI | Valdemira, Vincent | 14-135-0245.03 | P36451 |  |  |  |  | 217361
139 | Field-REI | Valdemira, Vincent | 15-063-0242 |  | MTA On Call Constr Supervision & INSP Sv | 15994443 | 11790710 | 1109310 | 442600 | 2019-11-22 | 8/21/19-Invoices being submitted week of 8/19/19.9/10/19- Nostrand on hold for possible CO. Also ESI on hold but billed up to budget 5/21/19. Waiting for approved CO. | [6 empty] | N |  | N
140 | Field-REI | Valdemira, Vincent | 15-063-0242 | B |  |  |  |  | 14474
141 | Field-REI | Valdemira, Vincent | 15-063-0242 | G |  |  |  |  | 63208
142 | Field-REI | Valdemira, Vincent | 15-063-0242 | H |  |  |  |  | 45804
143 | Field-REI | Valdemira, Vincent | 15-063-0242 | I |  |  |  |  | 15103
144 | Field-REI | Valdemira, Vincent | 15-063-0242 | O |  |  |  |  | 110081 |  | 9/20/2019 A modification for $388k has been requested and acknowledged by LIRR, to extend this task order through Sept 2020.
145 | Field-REI | Valdemira, Vincent | 15-063-0242 | Q |  |  |  |  | 23077
146 | Field-REI | Valdemira, Vincent | 15-063-0242 | R |  |  |  |  | 24757
147 | Field-REI | Valdemira, Vincent | 15-063-0242 | S |  |  |  |  | 46653
148 | Field-REI | Valdemira, Vincent | 15-063-0242 | U |  |  |  |  | 25927 |  | A modification in the amount of $27k has been requested and acknowledged by LIRR, to cover the hours in the WIP on this task.
149 | Field-REI | Valdemira, Vincent | 15-063-0242 | V |  |  |  |  | 21086
150 | Field-REI | Valdemira, Vincent | 15-063-0242 | W |  |  |  |  | 20519
151 | Field-REI | Valdemira, Vincent | 15-063-0242 | X |  |  |  |  | 14045
152 | Field-REI | Valdemira, Vincent | 15-063-0242 | Z |  |  |  |  | 17865
153 | Field-REI | Valdemira, Vincent | 19-092-0245 |  | MTA- IQ for CM - Misc Constr Projects | 150000 | 59407 | 256986 | 115389 | 2019-11-30 |  |  | 23598 |  |  |  |  | N |  | N
154 | Field-REI | Valdemira, Vincent | 19-092-0245 | 2 |  |  |  |  | 115389
155 | Field-REI | Valdemira, Vincent | 19-092-0245 | [10 empty] | 23597.76 | 2 | 2019-07-11
156 | Field-REI | Vysotsky, Pyotr | 10-55-200.1 |  | NYCDOT ESA Retaining Wall Design | 523245 | 462972 | 0 | 0 | 2017-01-20 | 4/24/18, DLM - Cut. |  | 81 |  |  |  |  | N |  | N
157 | Field-REI | Vysotsky, Pyotr | 10-55-200.1 | [10 empty] | 81.03 | 3 | 2016-10-12
158 | Field-REI | Wagh, Vikas | 10-55-200 |  | NYCDOT Engineering Service Agreement | 10508413 | 8690747 | 37397 | 11080 | 2019-10-25 | 2/7/19-This a multiple phased project. 09B is the largest amount of unbilled WIP. Supplemental has been approved and registered for 1.1M, Contract Value will be updated and the next invoice will be submitted through 2/15/19. |  | 27075 |  |  |  |  | N |  | N
159 | Field-REI | Wagh, Vikas | 10-55-200 | 149DCK |  |  |  |  | 2389
160 | Field-REI | Wagh, Vikas | 10-55-200 | SDR |  |  |  |  | 1779
161 | Field-REI | Wagh, Vikas | 10-55-200 | TASK03 |  |  |  |  | -130
162 | Field-REI | Wagh, Vikas | 10-55-200 | TASK11 |  |  |  |  | 1084
163 | Field-REI | Wagh, Vikas | 10-55-200 | TASK2 |  |  |  |  | 5958
164 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 1045.01 | 000007TASK04 | 2017-08-07
165 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 2861.73 | 00010TASK09B | 2016-09-21
166 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 14077.39 | 00014TASK09B | 2017-12-28
167 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 9091.02 | 00017TASK09B | 2019-03-19
168 | Field-REI | Wagh, Vikas | 14-001-0238 |  | MTA B&T CA and Insp. for RK 65 and RK 75 | 11176265 | 10469536 | 63742 | 1543 | 2019-09-27 | 12-4-19, CO submitted early Nov.; approval expected soon. | [6 empty] | N |  | N
169 | Field-REI | Wagh, Vikas | 14-001-0238 | 2.1.A |  |  |  |  | 1543
Total | [5 empty] | 385766146 | 237242228 | 13268556 | 7796632 | [6 empty] | 203299 | 1745610