## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Gennawey, Abla | 15-096-0383 |  | SCDPW Engineering Svcs Woodside Ave CR16 | 239359 | 138551 | 50425 | 47048 | 2019-11-08 | 9/25/2019: Invoice 15 is being prepared. Abla is working with Audrey on correcting vision input errors and also revising tasks to match cost control report in order to finalize the invoice. | [6 empty] | N |  | N
2 | Design | Gennawey, Abla | 15-096-0383 | 3 |  |  |  |  | 37558
3 | Design | Gennawey, Abla | 15-096-0383 | 8 |  |  |  |  | 1435
4 | Design | Gennawey, Abla | 15-096-0383 | 11 |  |  |  |  | 5235 |  | 8/1/19-per Bob Hutteman, Abla and him will prepare invoice once the preliminary plans to the County are submitted._rdc
5 | Design | Gennawey, Abla | 15-096-0383 | 12 |  |  |  |  | 1983 |  | 8/1/19-per Bob Hutteman, Abla and him will prepare invoice once the preliminary plans to the County are submitted._rdc
6 | Design | Gennawey, Abla | 15-096-0383 | 13 |  |  |  |  | 838 |  | 8/1/19-per Bob Hutteman, Abla and him will prepare invoice once the preliminary plans to the County are submitted._rdc
7 | Design | Gennawey, Abla | 19-206-0270 |  | NYCP&R - Eng Design Constr Davidson Park | 294264 | 0 | 21432 | 17851 | [8 empty] | N |  | N
8 | Design | Gennawey, Abla | 19-206-0270 | 1 |  |  |  |  | 17851
Total |  |  |  |  | 71857 | 129799 |  |  | 0 | 0