## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Architect | Giorgou, Argiris | 15-359-1719 |  | RB BETHPAGE REALTY/120 HICKSVILLE RD | 100000 | 91111 | 3383 | 3383 | 2018-05-25 | 12.9.19: Invoice to clear WIP will go out this month. | [6 empty] | N |  | N
2 | Architect | Giorgou, Argiris | 15-359-1719 | 102 |  |  |  |  | 1200
3 | Architect | Giorgou, Argiris | 15-359-1719 | 104 |  |  |  |  | 1626
4 | Architect | Giorgou, Argiris | 15-359-1719 | 851 |  |  |  |  | 557
5 | Architect | Giorgou, Argiris | 16-384-0425 |  | OB HSING/CCTV INSTALLATIONS | 28500 | 27525 | 4263 | 4263 | 2018-05-25 | 12.9.19: Invoice to clear balance of contract amount will go ut this month in the amount of $975. The remaining WIP balance will need to be written off $3,287.60 | [6 empty] | N |  | N
6 | Architect | Giorgou, Argiris | 16-384-0425 | 900 |  |  |  |  | 4263
7 | Architect | Giorgou, Argiris | 17-269-1089 |  | AECOM/SCC STEM BUILDING | 287550 | 45069 | 38002 | 38002 | 2018-05-25 | 12/2/19 - Project is on Hold letter being sent to AECOM for additional funding. "Final" invoice for Design in the amount of $47K may be at risk. 100% design has been submitted to AECOM, pending SCCC review and the estimate from the Architect. There is $149K in budget for the CI. Joe Grant anticipates $400K in CI will be required. In addition, if the estimate comes in over the $17M construction budget VE will be required which is also not billable (approx $20 -$25K). When we acquired this project from Bowne, we were told that they were 90% complete (billings represented milestones), were in actuality, they were 30% complete. |  | 143 |  |  |  |  | N |  | Y
8 | Architect | Giorgou, Argiris | 17-269-1089 | 102 |  |  |  |  | 33043
9 | Architect | Giorgou, Argiris | 17-269-1089 | 103 |  |  |  |  | 4959
10 | Architect | Giorgou, Argiris | 17-269-1089 | [10 empty] | 143.2 | 277612 | 2017-10-31 | Frank Lowe working on rate/contract issue SCC
11 | Architect | Giorgou, Argiris | 18-123-1855 |  | Fox Hollow TOB Permit Issues | 26169 | 26169 | 1787 | 0 | 2019-06-19 |  |  | 26169 |  |  |  |  | N |  | N
12 | Architect | Giorgou, Argiris | 18-123-1855 | [10 empty] | 26169.42 | 1 | 2019-08-13 | 12.9.19 PM in contact with Mauricio "General Manager" at Fox Hollow who requested additional work from our team; However, PM advised previous invoice paymet is required prior to providing add'l services. Mauricio is following up with his accounting team on payment status.
13 | Architect | Giorgou, Argiris | 18-237-1954 |  | LI Script - 333 Crossways-Interior Alter | 55097 | 55097 | 5124 | 4163 | 2019-04-12 | [7 empty] | N |  | N
14 | Architect | Giorgou, Argiris | 18-237-1954 | 1 |  |  |  |  | 4163
15 | Architect | Giorgou, Argiris | 18-323-0247 |  | NCC - SSC Fire Area | 23000 | 12060 | 1626 | 1060 | 2019-04-12 | [7 empty] | N |  | N
16 | Architect | Giorgou, Argiris | 18-323-0247 | 2 |  |  |  |  | 1060
Total |  |  |  |  | 54185 | 101742 |  |  | 0 | 26312