## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Hurley, Daniel | 15-068-0424 |  | TOB Lake Avenue CVM Expansion | 259425 | 129230 | 85351 | 68702 | 2018-12-21 | 12/2/19-Mike Smith is drafting the final request for additional funding. Lenz feels most of the design costs are not valid. the request for funds will include the CI services as LiRo re-estimated the projects and TOB is putting out to bid Jan 2020. Commissenor Lenz feels that the majority of the additional scope was caused by LiRo errors. | [6 empty] | N |  | Y
2 | Design | Hurley, Daniel | 15-068-0424 | 1 |  |  |  |  | 55758
3 | Design | Hurley, Daniel | 15-068-0424 | STAFF |  |  |  |  | 12944
4 | Design | Hurley, Daniel | 15-068-0424 | [10 empty] | -300 | 12 | 2017-10-06
5 | Design | Hurley, Daniel | 15-068-0424 | [10 empty] | 190.44 | 13 | 2019-01-15
Total |  |  |  |  | 85351 | 137404 |  |  | 0 | 0