## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Hurley, Joseph | 09-06-100B |  | PLA ANAYLSES FOR VARIOUS PROJECTS ASNEED | 592546 | 421494 | 26356 | 16886 | 2019-05-10 | [7 empty] | N |  | N
2 | CM | Hurley, Joseph | 09-06-100B | 24 |  |  |  |  | 16886
3 | CM | Hurley, Joseph | 12-128-0383 |  | SCDPW Bergen Point Plant Upgrade | 6732632 | 5573947 | 100954 | 19301 | 2019-09-27 | [7 empty] | N |  | N
4 | CM | Hurley, Joseph | 12-128-0383 | STAFF |  |  |  |  | 19301
5 | CM | Hurley, Joseph | 13-017-0265.04 |  | DDC- New Westchester Square Library | 18630 | 0 | 6763 | 6763 |  | 10/29/2019 LB following up on status of Executed Task Order. | [6 empty] | N |  | Y
6 | CM | Hurley, Joseph | 13-017-0265.04 | FEASI |  |  |  |  | 6763
7 | CM | Hurley, Joseph | 13-139-1165.03 |  | Cost Proposal for PLA Admin during Const | 24821 | 11007 | 1526 | 1526 | 2018-04-30 | 8-1-19- Project active. Will process invoice after 8/2/19 payroll is processed. | [6 empty] | N |  | N
8 | CM | Hurley, Joseph | 13-139-1165.03 | STAFF |  |  |  |  | 1526
9 | CM | Hurley, Joseph | 14-083-0248 |  | NCDPW Cedar Creek Influent Screenings | 1647098 | 1530764 | 10423 | 5450 | 2019-01-18 | 10/29/2019 AF checking with Mike Baranello on status of open A/R and submitting final billing for current staffing. | [6 empty] | N |  | N
10 | CM | Hurley, Joseph | 14-083-0248 | STAFF |  |  |  |  | 5450
11 | CM | Hurley, Joseph | 16-357-0248 |  | NCDPW Cedar Creek Effluent Screening & D | 1381091 | 1359210 | 182323 | 108248 | 2019-07-19 | 10-31-19- Awaiting Staffing Ammendment. Told it was approved, waiting for legislative approval.Once offical approval lettter recieved, the unbilled STaffing can be billed. $ 318,801 | [6 empty] | N |  | N
12 | CM | Hurley, Joseph | 16-357-0248 | STAFF |  |  |  |  | 108248
13 | CM | Hurley, Joseph | 18-041-1307 |  | CDM - Bergen Point Outfall Replacement | 1000000 | 515450 | 89427 | 0 | 2019-10-25 |  |  | 6564 |  |  |  |  | N |  | N
14 | CM | Hurley, Joseph | 18-041-1307 | [10 empty] | 6563.88 | 3 | 2019-02-05 | 10/29/2019 JH following up with phone calls to CDM 10-1-19- CDM had to revise the JV invoices with corrections amd were fedexed to Suffolk DPW 9/26/19. Optimistically payment should be received in about 6 weeks
15 | CM | Hurley, Joseph | 19-201-0248.01 |  | NCDPW - Mission 4 CPM Scheduler | 73000 | 0 | 9594 | 9225 | [8 empty] | N |  | N
16 | CM | Hurley, Joseph | 19-201-0248.01 | 1 |  |  |  |  | 9225
17 | CM | Hurley, Joseph | 19-238-0270 |  | NYCP&R - Highbridge Park Comfort Station | 15110 | 0 | 12022 | 2762 | [8 empty] | N |  | N
18 | CM | Hurley, Joseph | 19-238-0270 | 1 |  |  |  |  | 2762
19 | CM | Hurley, Joseph | 19-242-2292 |  | Broad Channel VFD-PLA Feasibility Study | 13573 | 0 | 14683 | 4918 | [8 empty] | N |  | N
20 | CM | Hurley, Joseph | 19-242-2292 | 1 |  |  |  |  | 4918
Total |  |  |  |  | 454071 | 350158 |  |  | 0 | 6564