## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Hutteman, Robert | 13-053-0472 |  | WCDPW Palmer Road Bridge | 186886 | 143997 | 34390 | 32659 | 2017-12-31 | 9.17.19 SantanaL - Category L - Invoicing WIP amount $25,869.50 by end of month.6/11/19 PIF was update on 6/7/1905/22/19 - We received a supplemental agreement for construction support services. Ken H. is updating the PIF. PIF is expected to be completed by 6/5/19 at which time Robert Hsu's time will be moved to the new task and WIP will be invoiced. | [6 empty] | N |  | N
2 | Design | Hutteman, Robert | 13-053-0472 | CONSTR |  |  |  |  | 27720
3 | Design | Hutteman, Robert | 13-053-0472 | STAFF |  |  |  |  | 4939
4 | Design | Hutteman, Robert | 15-049-0265.03 |  | NYCDDC Stanton & Lake Court Infrastructu | 1325920 | 1574287 | 23733 | 22455 | 2019-05-29 | BIB is waiting for the entire infrastructure (all courts) to complete and signed off before we can bill the remaining 10% design fees, once the final fees are billed, these hours will be cleared. Once the amendment is approved, all Stanton work will be paid as lump sum. | [6 empty] | N |  | N
5 | Design | Hutteman, Robert | 15-049-0265.03 | CONADM |  |  |  |  | 22163
6 | Design | Hutteman, Robert | 15-049-0265.03 | DESRPZ |  |  |  |  | 291
7 | Design | Hutteman, Robert | 16-308-0305 |  | NYC-DCAS Professional Svcs Requirement | 926932 | 459715 | 79477 | 70566 | 2019-12-31 | 11.12.19 SantanaL: multi division job (C/S, MEP, ARCH)- Invoice needs to be created - categorized as further discussion needed - Hutteman needs to speak wth J Grant and M Smith to discuss invoice preparation.5.8.19 SantanaL: HuttemanR will be updatingMajority of WIP is for MEP and Architects. $333.44 is for sub (Historical Perspectives) and $3,200 in expensesI submitted a draft invoice for PV time to DCAS months ago but have not been able to get a response. |  | 43351 |  |  |  |  | N |  | N
8 | Design | Hutteman, Robert | 16-308-0305 | 2LAFAY |  |  |  |  | 12958
9 | Design | Hutteman, Robert | 16-308-0305 | BOARD |  |  |  |  | 1936
10 | Design | Hutteman, Robert | 16-308-0305 | HARLEM |  |  |  |  | 11701
11 | Design | Hutteman, Robert | 16-308-0305 | MECH |  |  |  |  | 20783
12 | Design | Hutteman, Robert | 16-308-0305 | POLICE |  |  |  |  | 1530
13 | Design | Hutteman, Robert | 16-308-0305 | READE |  |  |  |  | 1161
14 | Design | Hutteman, Robert | 16-308-0305 | SPEC |  |  |  |  | 14617
15 | Design | Hutteman, Robert | 16-308-0305 | SPEDEV |  |  |  |  | 5881
16 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 13476.08 | 000001-BOILR | 2017-07-12
17 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 24225.5 | 00000CLTWR01 | 2017-07-12
18 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 1130.4 | 001_HARLEMCO | 2019-04-11
19 | Design | Hutteman, Robert | 16-308-0305 | [10 empty] | 4518.71 | 00280BDWY1R2 | 2017-08-14
20 | Design | Hutteman, Robert | 16-341-1387 |  | Breaking Ground Sites Assessment | 56000 | 0 | 13801 | 45298 | 2016-10-07 | [7 empty] | N |  | N
21 | Design | Hutteman, Robert | 16-341-1387 | STAFF |  |  |  |  | 45298
22 | Design | Hutteman, Robert | 17-046-0472 |  | Rehabilitation of Pondfield Road West Br | 196855 | 37678 | 109956 | 102188 | 2018-05-25 | 11.12.19 SantanaL: Per Hutteman contacting invoice preparer to ensure invoice goes out.9.17.19 SantanaL: Category L - Invoicing $91,378.90 by end of month.7.9.19 SantanaL: HuttemanR is working with Makendy to invoice WIP on this project" | [6 empty] | N |  | N
23 | Design | Hutteman, Robert | 17-046-0472 | CONDOC |  |  |  |  | 7722
24 | Design | Hutteman, Robert | 17-046-0472 | DESDEV |  |  |  |  | 55852
25 | Design | Hutteman, Robert | 17-046-0472 | PROP |  |  |  |  | 6674
26 | Design | Hutteman, Robert | 17-046-0472 | SCHDES |  |  |  |  | 31941
27 | Design | Hutteman, Robert | 19-045-1387 |  | Breaking Ground Property Condition Asses | 100000 | 100000 | 24457 | 0 | 2019-09-13 |  |  | 8734 |  |  |  |  | N |  | N
28 | Design | Hutteman, Robert | 19-045-1387 | [10 empty] | 8733.75 | 00001904501R | 2019-07-15 | 11.12.19 SantanaL: Received check in the amount of 43,266.25 against invoice1904501R dated 7/15/19- Balance of 12,000 remains 91-120 aging.
Total |  |  |  |  | 285814 | 546333 |  |  | 0 | 52085