## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Field-REI | Khachmanian, John | 08-70-205 |  | HWCRQ01, Requirements Contract for REI S | 6059254 | 4961927 | 0 | 0 | 2017-05-31 |  |  | 55271 |  |  |  |  | N |  | N
2 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 2697.95 | 000010BAILEY | 2018-12-31 | 9/18/19-John K. advised that all invoices (retainage and hours) have been approved and should be paid in Oct 2019.
3 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 29921.56 | 000014BAILEY | 2014-08-19
4 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 1297.76 | 000015BAILEY | 2015-12-31
5 | Field-REI | Khachmanian, John | 08-70-205 | [10 empty] | 21353.72 | 000016BAILEY | 2016-12-19
6 | Field-REI | Khachmanian, John | 12-029-0265 |  | NYCDDC Trunk Water Main 48th Street | 8591185 | 6754470 | 2761 | 0 | 2019-10-25 |  |  | 3451 |  |  |  |  | N |  | N
7 | Field-REI | Khachmanian, John | 12-029-0265 | [10 empty] | 3500.01 | 28 | 2016-10-04 | 8-6-18, No issues.
8 | Field-REI | Khachmanian, John | 12-029-0265 | [10 empty] | -49.13 | 39 | 2018-09-12 | 10-4-18, No issues10-31-18, Last invoice covered 08-31-18.
9 | Field-REI | Khachmanian, John | 12-056-0265 |  | NYCDDC Requirements Contract for REI Ser | 13362946 | 8638107 | 2259069 | 2156260 | 2019-09-27 |  |  | 782502 |  |  |  |  | N |  | N
10 | Field-REI | Khachmanian, John | 12-056-0265 | 3 |  |  |  |  | 555215
11 | Field-REI | Khachmanian, John | 12-056-0265 | 4 |  |  |  |  | 1601086
12 | Field-REI | Khachmanian, John | 12-056-0265 | 5 |  |  |  |  | -42
13 | Field-REI | Khachmanian, John | 12-056-0265 | [10 empty] | 13236.4 | 12 | 2018-12-12 | 7-15-19, Last invoiced 12/8/17. Completed.8/28/19, Task 1, Last invoice covered 12/7/18.8/28/19, Task 3, Last invoice covered 8/4/17.8/28/19,Task 4, Last invoice covered 12/8/17.
14 | Field-REI | Khachmanian, John | 12-056-0265 | [10 empty] | 769265.55 | 0000000009RC | 2017-10-25 | 10-4-18, Task 1, Close out. No issues.10-4-18, Task 3, Last invoice covered 8/4/17.10-4-18, Task 4, Last invoice covered 12/8/17.10-4-18, Task 5, Completed. Final Payment submitted. Last invoice covered 8/31/18.10-31-18, Same comments as 10-4-18 (above) for all Tasks.
15 | Field-REI | Khachmanian, John | 13-012-0265 |  | NYCDDC Times Sq. Reconstruction REI | 8837264 | 7920426 | 159495 | 33171 | 2019-09-27 |  |  | 8374 |  |  |  |  | N |  | N
16 | Field-REI | Khachmanian, John | 13-012-0265 | DECLAR |  |  |  |  | 37096
17 | Field-REI | Khachmanian, John | 13-012-0265 | STAFF |  |  |  |  | -3925
18 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 1000 | 7 | 2014-08-19 | 5/15-15- Cut for $1000 is temporary and is rebilled with each invoice- SC
19 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 32.5 | 8 | 2014-06-19 | 5/15-15- Cut for $32.50 is temporary and is rebilled with each invoice- SC
20 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 6000 | 11 | 2015-07-21
21 | Field-REI | Khachmanian, John | 13-012-0265 | [10 empty] | 1341.42 | 12 | 2015-10-09
22 | Field-REI | Khachmanian, John | 15-101-0265 |  | NYCDDC Albert Road Area Ozone Park | 5961160 | 4186918 | 190822 | 4469 | 2019-10-11 | 8-6-18, An invoice is being submitted for processing 8/31/18.10-4-18, Awaiting the check to be vouchered.10-31-18, Waiting for the check to be vouchered.2-13-19, Waiting for the check to be vouchered.4-8-19, Waiting for the check to be vouchered.7-15-19 & 8/28/19, Waiting for the check to be vouchered. | [6 empty] | N |  | N
23 | Field-REI | Khachmanian, John | 15-101-0265 | STAFF |  |  |  |  | 4469
24 | Field-REI | Khachmanian, John | 16-083-0265 |  | NYCDDC Reconstruction of Leonard Street | 4876343 | 3287923 | 224999 | 50673 | 2019-09-27 | 8-6-18, An invoice is being submitted for processing 8/31/18.10-4-18, Awaiting the check to be vouchered.10-31-18, Awaiting the check to be vouchered.2-13-19, Waiting for the check to be vouchered.4-8-19, Waiting for the check to be vouchered.7-15-19 & 8/28/19, Waiting for the check to be vouchered. | [6 empty] | N |  | N
25 | Field-REI | Khachmanian, John | 16-083-0265 | STAFF |  |  |  |  | 50673
26 | Field-REI | Khachmanian, John | 17-014-0265 |  | NYCDDC 2017 Large Requirement Contract | 19887602 | 7084315 | 1883582 | 1218453 | 2019-10-25 | 9/19/19-Waiting for the Change order of the amount $2,787,404.84 to be registered. Project was switched from Requirement Contract to Stand Alone Contract |  | 242531 |  |  |  |  | N |  | Y
27 | Field-REI | Khachmanian, John | 17-014-0265 | 2 |  |  |  |  | 95626
28 | Field-REI | Khachmanian, John | 17-014-0265 | 5 |  |  |  |  | 780286
29 | Field-REI | Khachmanian, John | 17-014-0265 | ASTORI |  |  |  |  | 342541
30 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 598.72 | 00000006WARD | 2018-09-12 | 10-4-18, Task 2, No Issues; Task 3, No issues; Task 4, No issues.10-31-18, Task 2, Last Invoice covered 8-31-18.7-15-19, Task 2, Last Invoice covered 5-10-19.
31 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 3056.19 | 000009PELHAM | 2019-05-31 | 7-15-19, Last invoice covered 5-10-19.
32 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 8882.72 | 00003ASTORIA | 2018-07-20 | 7/30/18 JK No issues8-6-18, Last invoice covered 7/6/18; Task 2, No Issues; Task 3, No issues; Task 4, No issues.10-4-18, Last Invoice covered 8/31/18.
33 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 47946.72 | 00005ASTORIA | 2019-06-03
34 | Field-REI | Khachmanian, John | 17-014-0265 | [10 empty] | 182046.73 | 00006ASTORIA | 2019-07-31 | 8/28/19, Task 1, Last invoice covered 7/5/19.
35 | Field-REI | Khachmanian, John | 19-066-0093 |  | Columbia Univ Manhattanville Phase IV | 249588 | 134996 | 43541 | 897 | 2019-10-11 | [7 empty] | N |  | N
36 | Field-REI | Khachmanian, John | 19-066-0093 | 1 |  |  |  |  | 897
37 | Field-REI | Khachmanian, John | 19-230-0265 |  | NYCDDC- Coastal Resiliency Project | 61685993 | 0 | 44965 | 9446 | [8 empty] | N |  | N
38 | Field-REI | Khachmanian, John | 19-230-0265 | 1 |  |  |  |  | 9446
Total |  |  |  |  | 4809234 | 6946737 |  |  | 0 | 1092129