## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Architect | Pohlsander, Dianne | 16-350-0472 |  | WCDPW - Rye Playland - Switchgear Bldg. | 9207839 | 2605868 | 163071 | 17328 | 2019-09-27 | 11.5.19 DP: Draft Invoice #12 submitted to the County 2019.10.15 | [6 empty] | N |  | N
2 | Architect | Pohlsander, Dianne | 16-350-0472 | ADDSV4 |  |  |  |  | 1024
3 | Architect | Pohlsander, Dianne | 16-350-0472 | RP006 |  |  |  |  | 1827
4 | Architect | Pohlsander, Dianne | 16-350-0472 | RP025 |  |  |  |  | 154
5 | Architect | Pohlsander, Dianne | 16-350-0472 | RP033 |  |  |  |  | 4765
6 | Architect | Pohlsander, Dianne | 16-350-0472 | RP040 |  |  |  |  | 6552
7 | Architect | Pohlsander, Dianne | 16-350-0472 | SWITCH |  |  |  |  | 3007
8 | Architect | Pohlsander, Dianne | 16-350-0472 | [10 empty] | -3611.81 | 000000007R-2 | 2018-08-17
9 | Architect | Pohlsander, Dianne | 18-042-0472 |  | WCDPW Mt Vernon District Office Reno | 423135 | 105612 | 10285 | 10285 | 2019-09-27 | [7 empty] | N |  | N
10 | Architect | Pohlsander, Dianne | 18-042-0472 | CD/CA |  |  |  |  | 10285
11 | Architect | Pohlsander, Dianne | 18-285-0265 |  | NYCDDC Capital Proj Snug Harbor Cultural | 1241979 | 704932 | 288792 | 204297 | 2019-07-31 | 12.9.19 Per Joe Grant - invoice went out to client and it was approved last week. WIP will clear when invoice is posted.11.5.19 DP: Draft invoice #5 submitted to DDC 2019.10.29. | [6 empty] | N |  | N
12 | Architect | Pohlsander, Dianne | 18-285-0265 | 1 |  |  |  |  | 13651
13 | Architect | Pohlsander, Dianne | 18-285-0265 | 2 |  |  |  |  | 126866
14 | Architect | Pohlsander, Dianne | 18-285-0265 | 3 |  |  |  |  | 63780
Total |  |  |  |  | 462148 | 463821 |  |  | 0 | 0