## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Reo, Jennifer | 16-076-0270.02 |  | NYCPR Tiffany St. Pier Special Inspec | 620 | 0 | 992 | 992 | 2018-06-30 | jr 10/31/19: Awaiting Parks approval of Invoice | [6 empty] | N |  | N
2 | CM | Reo, Jennifer | 16-076-0270.02 | INSPEC |  |  |  |  | 992
3 | CM | Reo, Jennifer | 16-076-0270.06 |  | NYCPR North 5th St Bulkhead-Spec Insp | 2480 | 263 | 3064 | 3064 | 2018-12-31 | 10/3/19: re-requested Invoicing from MTL for Permit closeout work. |  | 263 |  |  |  |  | N |  | N
4 | CM | Reo, Jennifer | 16-076-0270.06 | PM |  |  |  |  | 3064
5 | CM | Reo, Jennifer | 16-076-0270.06 | [10 empty] | 262.5 | 2 | 2019-01-16
6 | CM | Reo, Jennifer | 16-076-0270.07 |  | NYCPR Marcus Garvey Watchtower-Spec Insp | 3720 | 3375 | 1504 | 1504 | 2019-02-15 | JR 10/31/19: Awaiting Parks Approval of Invoice #02. | [6 empty] | N |  | N
7 | CM | Reo, Jennifer | 16-076-0270.07 | PM |  |  |  |  | 1504
8 | CM | Reo, Jennifer | 16-076-0270.08 |  | NYCPR Riverside South Plgd-Spec Insp | 3100 | 2590 | 14260 | 13011 | 2019-10-31 | JR 10/31/19: JR submitted Supplemental request for additional CM Staffing & additional Inspections on 3/19/19, awaiting approval. DPR requested another copy be sent on 10/18/19. Upon approval, Req #02 will be submitted. | [6 empty] | N |  | N
9 | CM | Reo, Jennifer | 16-076-0270.08 | PM |  |  |  |  | 13011
10 | CM | Reo, Jennifer | 16-076-0270.09 |  | NYCPR Astoria Diving Pool - Spec Inspec | 3000 | 465 | 1121 | 1054 | 2018-08-17 | JR 10/31/19: Awaiting approval status of Invoice #01 from DPR. I have still not received a response on both payment and project status. I have reached out to all contacts at Parks that were involved with the project over the past year to no avail, requested another update on 10/31/19. |  | 465 |  |  |  |  | N |  | N
11 | CM | Reo, Jennifer | 16-076-0270.09 | PM |  |  |  |  | 1054
12 | CM | Reo, Jennifer | 16-076-0270.09 | [10 empty] | 465 | 2 | 2018-08-27 | 10/29/2019 This invoice may need to be resubmitted , it includes $ 6500 in MTL Special Inspection invoicesalready remitted by LiRoJR 10/31/19: Awaiting approval status of Invoice #01 from DPR. I have still not received a response on both payment and project status. I have reached out to all contacts at Parks that were involved with the project over the past year to no avail, requested another update on 10/31/19.
13 | CM | Reo, Jennifer | 16-076-0270.10 |  | NYCPR Queensbridge Fld Hs- Spec Inspec | 5000 | 7073 | 304 | 304 | 2019-07-19 | JR 10/31/19: Invoice submitted on 8/1/19 to DPR, email sent to client requesting payment status. |  | 2160 |  |  |  |  | N |  | N
14 | CM | Reo, Jennifer | 16-076-0270.10 | PM |  |  |  |  | 304
15 | CM | Reo, Jennifer | 16-076-0270.10 | [10 empty] | 2160 | 2 | 2019-08-02 | JR 10/31/19: Email sent to client requesting payment status.
16 | CM | Reo, Jennifer | 16-076-0270.11 |  | NYCPR - NYS Pavillion - Spec Insp | 21600 | 135 | 169 | 101 | 2019-10-31 | JR 10/29/19: Awaiting Project Closeout Status from DPR. | [6 empty] | N |  | N
17 | CM | Reo, Jennifer | 16-076-0270.11 | 1 |  |  |  |  | 101
18 | CM | Reo, Jennifer | 16-076-0270.12 |  | NYCPR - Shore Rd Fld Hs - Spec Insp | 13500 | 0 | 5389 | 4106 |  | JR 10/1/19: Will submit Invoice upon invoicing by Consultant MTL They performed first inspection 9/1. | [6 empty] | N |  | N
19 | CM | Reo, Jennifer | 16-076-0270.12 | 1 |  |  |  |  | 4106
20 | CM | Reo, Jennifer | 16-076-0270.13 |  | NYCPR - West Plgd CS - Spec Insp | 18000 | 675 | 439 | 169 | 2018-12-31 | JR 10/1/19: Will submit Invoice upon invoicing by Consultant MTL They have not performed first inspection yet | [6 empty] | N |  | N
21 | CM | Reo, Jennifer | 16-076-0270.13 | 1 |  |  |  |  | 169
22 | CM | Reo, Jennifer | 16-076-0270.14 |  | NYCPR - Brownsville Rec Ctr - Spec Insp | 12500 | 439 | 1066 | 256 | 2018-12-31 | 10/2/2019 Awaiting response from Parks noting Project complete | [6 empty] | N |  | N
23 | CM | Reo, Jennifer | 16-076-0270.14 | 1 |  |  |  |  | 256
24 | CM | Reo, Jennifer | 16-076-0270.15 |  | NYCPR - Marine Pk Plgd - Spec Insp | 9000 | 0 | 6480 | 5728 |  | Awaiting response from Parks noting Project complete | [6 empty] | N |  | N
25 | CM | Reo, Jennifer | 16-076-0270.15 | 1 |  |  |  |  | 5728
26 | CM | Reo, Jennifer | 16-076-0270.16 |  | NYCPR - Canarsie CS - Spec Insp | 13500 | 743 | 140 | 140 | 2018-12-31 | Awaiting response from Parks noting Project complete | [6 empty] | N |  | N
27 | CM | Reo, Jennifer | 16-076-0270.16 | 1 |  |  |  |  | 140
28 | CM | Reo, Jennifer | 16-080-0270.13 |  | NYCPR Lincoln Terrace Park Special Insp | 25200 | 1530 | 1485 | 1283 | 2019-07-19 | 10/31/2019 JR: Meeting scheduled with EDC on 11/6/19 to find out what the issue with the Precon Pmt and anticipated Construction start. |  | 1530 |  |  |  |  | N |  | N
29 | CM | Reo, Jennifer | 16-080-0270.13 | 1 |  |  |  |  | 1283
30 | CM | Reo, Jennifer | 16-080-0270.13 | [10 empty] | 1530 | 1 | 2019-08-02 | JR 10/31/19: Email sent to client requesting payment status.
31 | CM | Reo, Jennifer | 17-102-0275 |  | NYCEDC Homeport Demolition | 377353 | 23753 | 12617 | 3896 | 2019-06-30 | 10/31/2019 JR: Meeting scheduled with EDC on 11/6/19 to find out what the issue with the Precon Pmt and anticipated Construction start. |  | 23753 |  |  |  |  | N |  | N
32 | CM | Reo, Jennifer | 17-102-0275 | STAFF |  |  |  |  | 3896
33 | CM | Reo, Jennifer | 17-102-0275 | [10 empty] | 16221.62 | 1 | 2019-02-11 | 10/31/2019 JR: Meeting scheduled with EDC on 11/6/19 to find out what the issue with the Precon Pmt and anticipated Construction start.
34 | CM | Reo, Jennifer | 17-102-0275 | [10 empty] | 7530.91 | 00000000002R | 2019-07-15 | 10/31/2019 JR: Meeting scheduled with EDC on 11/6/19 to find out what the issue with the Precon Pmt and anticipated Construction start.
35 | CM | Reo, Jennifer | 19-018-0276.02 |  | FDNY - EC-24 Female Firefighter Toilet U | 357390 | 351001 | 31679 | 586 | 2019-08-31 | 8/1/19 JR: Invoice #04 thru period 7/26/19 was submitted on 8/1/19, Current WIP $0.00. | [6 empty] | N |  | N
36 | CM | Reo, Jennifer | 19-018-0276.02 | 1 |  |  |  |  | 586
37 | CM | Reo, Jennifer | 19-018-0276.03 |  | FDNY- EC253 Multi-Component Reno COMM#2 | 355701 | 241440 | 17983 | 0 | 2019-10-25 | 8/1/19 JR: Invoice #02 thru period 7/26/19 was submitted on 8/1/19, Current WIP $0.00. | 121003 | [5 empty] | N |  | N
Total |  |  |  |  | 98692 | 72388 |  |  | 121003 | 28171