## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Ribeiro, Raymond | 14-058-0286.06 |  | NYPA Cumberland HPS Boiler Replacement | 181094 | 104087 | 4835 | 4835 | 2019-01-31 | )Marco & Larry discussed this project not meeting anticipated profit. Completion date now is anticipated for September/October 2019 providing no other issue arises. NYPA will only allow us to invoice to 95% completion once the chimney liner is installed and the Temp Boiler is removed from site. We are working continuosly to get this done. (MAB 8/9/2019) | [6 empty] | N |  | N
2 | CM | Ribeiro, Raymond | 14-058-0286.06 | CONSTR |  |  |  |  | 4835 |  | CV is $465,470.00 - Project is delayed for about 4-5 months so far due to Design omissions/errors by Wendel Engineers. Up to December 2018, we were able to bill 40% of our fee totaling $186,188.00; In March 2019, we will be billing up to 75% completion and an invoice will be sent to NYPA for $162,914.50 (2/26/2019 MAB)
3 | CM | Ribeiro, Raymond | 14-058-0286.07 |  | NYPA Lincoln Hospital - HVAC Upgrade | 1506098 | 854585 | 286913 | 209382 | 2019-09-13 | Milestone Billing | [6 empty] | N |  | N
4 | CM | Ribeiro, Raymond | 14-058-0286.07 | CONSTR |  |  |  |  | 117915
5 | CM | Ribeiro, Raymond | 14-058-0286.07 | PRE-1B |  |  |  |  | 10095 |  | We have billed the project up to 90% Design submission on 6/29/2018 for a total of "Billed to Date" of $452,592.90 (8/3/2018 MAB)
6 | CM | Ribeiro, Raymond | 14-058-0286.07 | PRECON |  |  |  |  | 81373
7 | CM | Ribeiro, Raymond | 14-058-0286.09 |  | NYPA Bridge Lighting | 50000 | 0 | 193 | 193 | 2017-12-18 | [7 empty] | N |  | N
8 | CM | Ribeiro, Raymond | 14-058-0286.09 | STAFF |  |  |  |  | 193
9 | CM | Ribeiro, Raymond | 14-058-0286.10 |  | NYPA Lincoln Hospital - Cooling Tower | 619920 | 529085 | 9709 | 5144 | 2018-12-31 | Catwalk change order work is scheduled to restart on 8/19/2019; as soon as this work is complete, we will be able to close out the project and invoice the remaining 5% $ 95,835 plus whatever percentage we are entitled to from the change order work. (MAB 8/9/2019) | [6 empty] | N |  | N
10 | CM | Ribeiro, Raymond | 14-058-0286.10 | PHASE2 |  |  |  |  | 5144
11 | CM | Ribeiro, Raymond | 14-058-0286.11 |  | NYPA Grand Ave. Bus Depot Gen Upgrade | 220000 | 49600 | 50169 | 46864 | 2018-08-17 | 10/15/2019 JRA: NYPA reached out last week asking to finalize the CIC. Marco had been working with NYPA on this item and now Chris Lynch will take over. I would guess we are a few weeks away | [6 empty] | N |  | N
12 | CM | Ribeiro, Raymond | 14-058-0286.11 | PHASE1 |  |  |  |  | 28695 |  | F. Awaiting Milestone - WIP is recoverable with an anticipated effective multiplier between 2.1 and 2.5. The next invoice will occur when the project is bid and the CIC is approved - tentative invoice date of July 2019. (JRA 6/3/2019)
13 | CM | Ribeiro, Raymond | 14-058-0286.11 | PHASE3 |  |  |  |  | 19670
14 | CM | Ribeiro, Raymond | 14-058-0286.11 | PHASE4 |  |  |  |  | -1501
15 | CM | Ribeiro, Raymond | 14-058-0286.12 |  | NYPA Fresh Pond Bus Depot-HVAC Upgrade | 1230197 | 494595 | 132445 | 122094 | 2019-02-15 | G. Awaiting Milestone - WIP is recoverable with an anticipated effective multiplier above 2.5.. The next invoice will occur when the project is bid and the CIC is approved - anticipated for October 2019. (JRA 8/7/2019) | [6 empty] | N |  | N
16 | CM | Ribeiro, Raymond | 14-058-0286.12 | 1 |  |  |  |  | 78548
17 | CM | Ribeiro, Raymond | 14-058-0286.12 | 2 |  |  |  |  | 1185
18 | CM | Ribeiro, Raymond | 14-058-0286.12 | PHASE1 |  |  |  |  | -59
19 | CM | Ribeiro, Raymond | 14-058-0286.12 | PHASE3 |  |  |  |  | 42420
20 | CM | Ribeiro, Raymond | 14-058-0286.13 |  | NYPA CUNY Boiler Repairs- Queens College | 114500 | 156416 | 1324 | 1324 | 2019-08-31 | Commissioning Phases 1 and 2 are being billed on milestones together with the Design firm EME Group; (MAB 6/3/2019) | [6 empty] | N |  | N
21 | CM | Ribeiro, Raymond | 14-058-0286.13 | COMM |  |  |  |  | 1324 |  | This commissioning project is a Pass-Thru and LiRo's involvement is only administrative. We hold the contract with EME Group and process payments. (MAB 8/9/2019)
22 | CM | Ribeiro, Raymond | 14-058-0286.18 |  | NYPA CUNY Boiler Repairs- Voohies Hall C | 14000 | 2240 | 5728 | 5728 | 2018-05-31 | Commissioning projects where we bill when the sub-consultants bill. | [6 empty] | N |  | N
23 | CM | Ribeiro, Raymond | 14-058-0286.18 | COMM |  |  |  |  | 5728
24 | CM | Ribeiro, Raymond | 14-058-0286.19 |  | NYPA CUNY Boiler Repairs- Bklyn College | 51020 | 15306 | 2696 | 2696 | 2018-11-12 | This project started in July 2018 and will be invoiced on milestones.LiRo has invoiced $15,306 of a total CM fee of $51,020; we will be invoicing when NYPA approves 60% Design submission from Aramark as soon as we achieve this goal, we will be able to invoice again. (MAB 8/9/2019) | [6 empty] | N |  | N
25 | CM | Ribeiro, Raymond | 14-058-0286.19 | RETCOM |  |  |  |  | 2696
26 | CM | Ribeiro, Raymond | 14-059-0113.02 |  | DASNY York College BMS Upgrade | 429899 | 235943 | 137226 | 135674 | 2018-06-22 | 10/5/2019 JRA JRA: Work is complete and we have one remaining invoice that I understand Andrew Frangas prepared. WIP should have been cleared by Andrew Frangas at the last invoice. | [6 empty] | N |  | N
27 | CM | Ribeiro, Raymond | 14-059-0113.02 | 1 |  |  |  |  | 127117
28 | CM | Ribeiro, Raymond | 14-059-0113.02 | 2 |  |  |  |  | 7782
29 | CM | Ribeiro, Raymond | 14-059-0113.02 | 3 |  |  |  |  | 732
30 | CM | Ribeiro, Raymond | 14-059-0113.02 | STAFF |  |  |  |  | 43
31 | CM | Ribeiro, Raymond | 14-059-0113.02 | [10 empty] | -7954.8 | 5-DESIGN-YOR | 2018-11-08
32 | CM | Ribeiro, Raymond | 15-124-0265 |  | NYCDDC 31 Chambers Street-Skylight | 1048375 | 1020535 | 0 | 0 | 2019-09-13 | 8/1/19 Request for add'l funds of $46.5k was sent on 12/31/18. |  | 491 |  |  |  |  | N |  | N
33 | CM | Ribeiro, Raymond | 15-124-0265 | [10 empty] | 490.78 | 6 | 2019-05-08 | 6/5/19- payment is with EAO
34 | CM | Ribeiro, Raymond | 17-040-0286.01 |  | NYPA VNB Bridge Lighting | 5120613 | 4960870 | 83796 | 72922 | 2018-09-28 | [7 empty] | N |  | N
35 | CM | Ribeiro, Raymond | 17-040-0286.01 | CM |  |  |  |  | 50598
36 | CM | Ribeiro, Raymond | 17-040-0286.01 | CMDD |  |  |  |  | 16227
37 | CM | Ribeiro, Raymond | 17-040-0286.01 | DESIGN |  |  |  |  | 6098
38 | CM | Ribeiro, Raymond | 17-040-0286.03 |  | NYPA RFK Harlem Bridge Lighting | 1175397 | 1145253 | 165 | 165 | 2019-06-07 | [7 empty] | N |  | N
39 | CM | Ribeiro, Raymond | 17-040-0286.03 | CMDD |  |  |  |  | 165
40 | CM | Ribeiro, Raymond | 17-040-0286.06 |  | NYPA TNB Bridge Lighting | 2287790 | 2244491 | 330 | 330 | 2019-09-13 |  |  | 4946 |  |  |  |  | N |  | N
41 | CM | Ribeiro, Raymond | 17-040-0286.06 | CMDD |  |  |  |  | 330
42 | CM | Ribeiro, Raymond | 17-040-0286.06 | [10 empty] | 4945.51 | FEEALLOCJV06 | 2019-07-31
43 | CM | Ribeiro, Raymond | 17-078-1387.02 |  | Breaking Ground-Prince George Sidewalk | 60000 | 0 | 69963 | 61969 | [8 empty] | N |  | N
44 | CM | Ribeiro, Raymond | 17-078-1387.02 | 1 |  |  |  |  | 61969
45 | CM | Ribeiro, Raymond | 17-078-1387.03 |  | Breaking Ground-Prince George Fire Pump | 15000 | 0 | 12002 | 12002 | [8 empty] | N |  | N
46 | CM | Ribeiro, Raymond | 17-078-1387.03 | 1 |  |  |  |  | 12002
47 | CM | Ribeiro, Raymond | 17-095-0407.01 |  | Town of Babylon Gilgo Potable Water | 21225 | 12850 | 9468 | 9468 | 2019-04-30 | [7 empty] | N |  | N
48 | CM | Ribeiro, Raymond | 17-095-0407.01 | CONSTR |  |  |  |  | -1850
49 | CM | Ribeiro, Raymond | 17-095-0407.01 | PRECON |  |  |  |  | 11318
50 | CM | Ribeiro, Raymond | 17-095-0407.02 |  | Town of Babylon America Venice Bridges | 274862 | 282449 | 51999 | 16335 | 2019-08-31 | [7 empty] | N |  | N
51 | CM | Ribeiro, Raymond | 17-095-0407.02 | CONSTR |  |  |  |  | 16335
52 | CM | Ribeiro, Raymond | 17-095-0407.04 |  | Town of Babylon Carls River Watershed | 258104 | 60571 | 654 | 654 | 2019-06-30 | [7 empty] | N |  | N
53 | CM | Ribeiro, Raymond | 17-095-0407.04 | PRECON |  |  |  |  | 654
54 | CM | Ribeiro, Raymond | 17-095-0407.05 |  | Town of Babylon Amityville Waterfront | 118781 | 120090 | 19345 | 17373 | 2019-06-30 | [7 empty] | N |  | N
55 | CM | Ribeiro, Raymond | 17-095-0407.05 | CONSTR |  |  |  |  | 17373
56 | CM | Ribeiro, Raymond | 17-095-0407.06 |  | Town of Babylon-Babylon Coastal Outfall | 94325 | 37100 | 3693 | 3693 | 2019-03-31 | [7 empty] | N |  | N
57 | CM | Ribeiro, Raymond | 17-095-0407.06 | PRECON |  |  |  |  | 3693
58 | CM | Ribeiro, Raymond | 17-095-0407.07 |  | Town of Babylon Captree Road Stabilizati | 80737 | 18600 | 436 | 436 | 2019-06-30 | [7 empty] | N |  | N
59 | CM | Ribeiro, Raymond | 17-095-0407.07 | PRECON |  |  |  |  | 436
60 | CM | Ribeiro, Raymond | 17-095-0407.08 |  | Town of Babylon Oakbeach Stabilization | 80700 | 24500 | 3826 | 3826 | 2019-03-31 | [7 empty] | N |  | N
61 | CM | Ribeiro, Raymond | 17-095-0407.08 | PRECON |  |  |  |  | 3826
62 | CM | Ribeiro, Raymond | 17-095-0407.09 |  | Town of Babylon Araca Stabilization | 80700 | 29250 | 2275 | 2275 | 2019-03-31 | [7 empty] | N |  | N
63 | CM | Ribeiro, Raymond | 17-095-0407.09 | CONSTR |  |  |  |  | 980
64 | CM | Ribeiro, Raymond | 17-095-0407.09 | PRECON |  |  |  |  | 1294
65 | CM | Ribeiro, Raymond | 17-141-0267 |  | NYCDEP Constr of Right of Way Green Infr | 1915765 | 836906 | 287956 | 235507 | 2019-05-31 | 10/29/19-Currently invoiced through 3/31/19 and continuing to invoice every 2 - 3 weeks. | 68661 | 167512 |  |  |  |  | N |  | N
66 | CM | Ribeiro, Raymond | 17-141-0267 | CLOSE |  |  |  |  | 9486
67 | CM | Ribeiro, Raymond | 17-141-0267 | CONSTR |  |  |  |  | 209116
68 | CM | Ribeiro, Raymond | 17-141-0267 | PM |  |  |  |  | 16905
69 | CM | Ribeiro, Raymond | 17-141-0267 | [10 empty] | -58.12 | 8 | 2019-05-21
70 | CM | Ribeiro, Raymond | 17-141-0267 | [10 empty] | 474.51 | 11 | 2019-05-21
71 | CM | Ribeiro, Raymond | 17-141-0267 | [10 empty] | 58702.42 | 13 | 2019-05-21
72 | CM | Ribeiro, Raymond | 17-141-0267 | [10 empty] | 55852.28 | 14 | 2019-05-21
73 | CM | Ribeiro, Raymond | 17-141-0267 | [10 empty] | 52551.03 | 15 | 2019-05-21
74 | CM | Ribeiro, Raymond | 17-141-0267 | [10 empty] | -10.56 | 000000007ADJ | 2019-05-20
75 | CM | Ribeiro, Raymond | 17-141-0267.01 |  | NYCDEP Constr of Aboveground Water Quali | 228352 | 166834 | 52419 | 51687 | 2019-11-30 | 10/29/19-Currently invoiced through 3/31/19 and continuing to invoice every 2 - 3 weeks. | 16419 | 45377 |  |  |  |  | N |  | N
76 | CM | Ribeiro, Raymond | 17-141-0267.01 | CLOSE |  |  |  |  | 35276 |  | 5/2/19 RR - Invoices #1 through #12 have been submitted to DEP Payment for invoice #1 & 2 have been made. DEP has agreed to allow LiRo to submit a monthly invoice each week to catch up on all outstanding invoices. Just sent invoice (#12 for Sept 2018 services)
77 | CM | Ribeiro, Raymond | 17-141-0267.01 | PM |  |  |  |  | 16411
78 | CM | Ribeiro, Raymond | 17-141-0267.01 | [10 empty] | 16407.96 | 13 | 2019-05-21
79 | CM | Ribeiro, Raymond | 17-141-0267.01 | [10 empty] | 14701.25 | 14 | 2019-05-21
80 | CM | Ribeiro, Raymond | 17-141-0267.01 | [10 empty] | 14267.79 | 15 | 2019-05-21
81 | CM | Ribeiro, Raymond | 17-141-0267.02 |  | NYCDEP Water Meter Installation at NYCHA | 1028883 | 1051708 | 371588 | 324999 | 2019-11-30 | 10/29/19-Currently invoiced through 3/31/19 and continuing to invoice every 2 - 3 weeks. | 110905 | 315031 |  |  |  |  | N |  | N
82 | CM | Ribeiro, Raymond | 17-141-0267.02 | CLOSE |  |  |  |  | 113473 |  | 5/2/19 RR - Invoices #1 through #12 have been submitted to DEP Payment for invoice #1 & 2 have been made. DEP has agreed to allow LiRo to submit a monthly invoice each week to catch up on all outstanding invoices. Just sent invoice (#12 for Sept 2018 services)
83 | CM | Ribeiro, Raymond | 17-141-0267.02 | PM |  |  |  |  | 211526
84 | CM | Ribeiro, Raymond | 17-141-0267.02 | [10 empty] | 1171.91 | 7 | 2019-05-20 | 9/9/19-DEP cut this invoice pending the SUB agreement to be executed (it was executed on 9/5/19 and resubmitted to DEP). VRX portion of invoice not collected with 8/29/2019 receipt.
85 | CM | Ribeiro, Raymond | 17-141-0267.02 | [10 empty] | -38.64 | 9 | 2019-05-21
86 | CM | Ribeiro, Raymond | 17-141-0267.02 | [10 empty] | 117515.41 | 13 | 2019-05-21
87 | CM | Ribeiro, Raymond | 17-141-0267.02 | [10 empty] | 101877.08 | 14 | 2019-05-21
88 | CM | Ribeiro, Raymond | 17-141-0267.02 | [10 empty] | 94505.63 | 15 | 2019-05-21
89 | CM | Ribeiro, Raymond | 17-141-0267.03 |  | NYCDEP - Amawalk Dam Ogee Spillway | 432803 | 4051 | 4871 | 4871 | 2019-03-31 | 10/29/19-Currently invoiced through 3/31/19 and continuing to invoice every 2 - 3 weeks. Cannot bill .03 & .04 until main contract, .01 and .02 are billed to the date of this WIP. This project has been cancelled. | [6 empty] | N |  | N
90 | CM | Ribeiro, Raymond | 17-141-0267.03 | 1 |  |  |  |  | 4871
91 | CM | Ribeiro, Raymond | 17-141-0267.04 |  | NYCDEP- WQMON-ENT2 Construction of Above | 327288 | 0 | 109398 | 77837 | 2019-11-30 | 10/29/19-Currently invoiced through 3/31/19 and continuing to invoice every 2 - 3 weeks. Cannot bill .03 & .04 until main contract, .01 and .02 are billed to the date of this WIP. This project has been cancelled. | [6 empty] | N |  | N
92 | CM | Ribeiro, Raymond | 17-141-0267.04 | 1 |  |  |  |  | 19692
93 | CM | Ribeiro, Raymond | 17-141-0267.04 | 2 |  |  |  |  | 58145
94 | CM | Ribeiro, Raymond | 17-141-0267.05 |  | NYCDEP- 26W-13G Elec and Special Inspect | 26899 | 0 | 21652 | 17510 |  | 9/9/19-Currently invoiced through 1/31/19 and continuing to invoice every 2 - 3 weeks. Cannot bill .03 & .04 until main contract, .01 and .02 are billed to the date of this WIP | [6 empty] | N |  | N
95 | CM | Ribeiro, Raymond | 17-141-0267.05 | 1 |  |  |  |  | 429
96 | CM | Ribeiro, Raymond | 17-141-0267.05 | 4 |  |  |  |  | 17080
Total |  |  |  |  | 1737074 | 2895586 |  |  | 195985 | 533357