## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Stevens, Paul | 12-166-1749 |  | JWD/NITRATE & VOC REMOVAL FACLTY | 733482 | 738044 | 51639 | 51639 | 2019-03-29 | 8.21.19 SantanaL: Per StevensP - WIP 80,386 should be written off6/15/19-Legal is involved with litigation between Merrick Utilities and JWD.Contractor has claim against JWD for delays, we will be required to support JWD. Another Engineer is now performing construction services on this project we designed, so there will be ongoing questions about our design. Per Paul, it is not clear what we are able to bill. Project will be open for two more years. Billed to contract max.9/20/19 Project in litagation WIP $129,243.JWD agreed to $54 K initial payment and hold remainderfor review Until after litagation.Al Bereche reviewing whether or not to accept $54 K payment at this time. |  | 129243 |  |  |  |  | N |  | Y
2 | Design | Stevens, Paul | 12-166-1749 | 200 |  |  |  |  | 1297
3 | Design | Stevens, Paul | 12-166-1749 | 800 |  |  |  |  | 36079
4 | Design | Stevens, Paul | 12-166-1749 | 801 |  |  |  |  | 3157
5 | Design | Stevens, Paul | 12-166-1749 | 802 |  |  |  |  | 11107
6 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 43063.62 | 1216605 | 2018-07-26 | 8.21.19 SantanaL: Per StevensP -theres a PO for 54,000 +/- under review by AL (LiRo legal), remaining 75k is being held by Jericho water district pending litigation outcome.5/6/19 Stevens P.Emailed Peter Logan for update on 4/12/19.He said he will review that week.Emailed Peter Logan on 4/23/19 and 5/7/19.No response.4/4/19 StevensP: Jericho water district has agreed to pay $54,000- the remaining fees are delayed until litigation is resolved. Construction is 95% complete. This note is same for the following invoice numbers (1216605,1216606,1216607,1216608,1216609,1216610). Email was sent today 4/4/19 to Commissioner Tom Abatte and Superintendent Peter Logan requesting status of our $54,000 payment.
7 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 63519.66 | 1216606 | 2018-08-07
8 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 6920.01 | 1216607 | 2018-10-08
9 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 4499.94 | 1216608 | 2018-11-09
10 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 1064.37 | 1216609 | 2018-12-26
11 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 1379.94 | 1216610 | 2019-02-19
12 | Design | Stevens, Paul | 12-166-1749 | [10 empty] | 8795.94 | 1216611 | 2019-04-17
13 | Design | Stevens, Paul | 16-425-1749 |  | JWD/WELL NO. 12 REHAB | 126800 | 113058 | 49588 | 49588 | 2019-10-25 | 12/2/19-Paul advised he has not received any update. 9/26/19-Paul Logan advised he has not yet presented our change order to the board. Hopefully, 10/16/19 meeting. 8.21.19 SantanaL: PerStevensP - Client is waiting on Peter Logan (water superintendent) to approve change order. Stevens is holding invoicing the $10,000 that can be billed currently because he wants to collect more money once change order is approved. he feels client will pay. Stevens requests updates from client every two weeks. 5/7/19 Stevens PEmailed Peter Logan on 4/12,4/23 an 5/7 for updates on status. On 4/12,Peter Logan said he would review that week.No response on 4/23 or 5/7.4/4/19 StevensP - Sent email to CommissionerTom Abatte and Superintendent Peter Logan asking for status of contract increase.Stevens P.-4/2/19 -Billed monthly ,$13,742 can be billed under present contract authorization.3.25.19 Seeking Contract increase for another $34,549.03. (Doubtful to obtain full request ). | [6 empty] | N |  | Y
14 | Design | Stevens, Paul | 16-425-1749 | 800 |  |  |  |  | 22245
15 | Design | Stevens, Paul | 16-425-1749 | 810 |  |  |  |  | 1326
16 | Design | Stevens, Paul | 16-425-1749 | 820 |  |  |  |  | 26017
17 | Design | Stevens, Paul | 18-004-0463 |  | Vill of Old Westbury-2018 | 213100 | 276749 | 2175 | 1397 | 2019-10-25 | 8/28/19 Messina- Inv p/e 08/16/19 Hastings and rds sent out.06/20/19-Inv p/e 053119 sent out-Hastings and Rds6.11.19 SantanaL: Per Stevens P - This is a write off as it exceeded authorized budget. | [6 empty] | N |  | N
18 | Design | Stevens, Paul | 18-004-0463 | ANDOVE |  |  |  |  | 1397 |  | 4/2/19 (Stevens P )Project complete ,no change orders possible.Write off.
19 | Design | Stevens, Paul | 18-004-0463 | RDS18 |  |  |  |  | 0
20 | Design | Stevens, Paul | 19-011-1686 |  | Vill of Brookville - Roads 2019 | 74600 | 60521 | 0 | 0 | 2019-08-30 | 08/28/19 MessinaS - Inv p/e 08/02/19 sent out. | [6 empty] | N |  | N
21 | Design | Stevens, Paul | 19-011-1686 | 1 |  |  |  |  | 100
22 | Design | Stevens, Paul | 19-011-1686 | 2 |  |  |  |  | -100
Total |  |  |  |  | 103402 | 205249 |  |  | 0 | 129243