## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Tse, Jason | 13-170-1674 |  | CPWD/WELL 1A AND 2R TREATMENT PLT | 644450 | 850223 | 22883 | 20360 | 2019-07-19 | 12/2/19-Open WIP and AR at At Risk. Ziegler's time might be collectable. 09/20/19 Mike Smith and Al met with Tim Doyle and they advised they are currently reviewing the invoice, but feel some/most of the items are not valid. Inv 1317004 was revised to 191,808.31 reflecting the credit adj for 100 hp motor issue of $28,025.00 and sent out. Remaining time on the WIP ($34,497) is not billable. | [6 empty] | N |  | Y
2 | Design | Tse, Jason | 13-170-1674 | 800 |  |  |  |  | 20461
3 | Design | Tse, Jason | 13-170-1674 | 801 |  |  |  |  | -101
4 | Design | Tse, Jason | 17-262-1702 |  | MASS WD/LITTLE MAY BOOSTER P.S. UPGRADE | 68000 | 65899 | 598 | 598 | 2019-12-31 | 11.11.19 SantanaL: Current WIP 597.69 and AR of $780.38 – Needs to be written off per Jason Tse (1,378.07) - job completed 9.19.19 SantanaL Invoice in the amoutn of $4,220.14. was sent to client on 8/20/19.09/09/19 TseJ: Project complete. Invoices from 4/3/19 and prior should have been written off.08/26/19 TseJ: Spoke to Stan Carey/MWD and will get board approval for full amount $4,220.14. 08/20/19 Messina - Inv thru 08/02/19 emailed to client.7/25/19 - TseJ: Hold bill until 8/2/19 and bill out WIP on Phase 803 Task 003. |  | 780 |  |  |  |  | N |  | N
5 | Design | Tse, Jason | 17-262-1702 | 803 |  |  |  |  | 598
6 | Design | Tse, Jason | 17-262-1702 | [10 empty] | 540 | 277705 | 2017-11-28 | 09/09/19 TseJ: Project complete. Invoices from 4/3/19 and prior should have been written off.08/05/19 According to John Waltz's notes in the project review, Inv 277705 should be written off.
7 | Design | Tse, Jason | 17-262-1702 | [10 empty] | 240.38 | 1726205 | 2019-04-02
8 | Design | Tse, Jason | 17-263-1674 |  | CPWD/SCADA PHASE 1 | 24000 | 25747 | 0 | 0 | 2019-06-28 |  |  | 2728 |  |  |  |  | N |  | Y
9 | Design | Tse, Jason | 17-263-1674 | [10 empty] | 1772.13 | 1726302 | 2019-01-21 | 11.11.19 SantanaL: Per JasonTse - this projects links to 13-170-1674 - most likely this amount will need to be written off.9/9/19 TseJ: Spoke to Tim Doyle/CPWD on 9/3/19 on invoicing status with no update. Payment on hold without explanation.8/14/19 TseJ: Spoke to Theresa AlexandroCPWD on status update for resubmitted invoice and was advised it will be presented at tonight's board meeting with update to follow.
10 | Design | Tse, Jason | 17-263-1674 | [10 empty] | 955.38 | 1726303 | 2019-07-31 | 11.11.19 SantanaL: Per JasonTse - this projects links to 13-170-1674 - most likely this amount will need to be written off.9/9/19 TseJ: Spoke to Tim Doyle/CPWD on 9/3/19 on invoicing status with no update. Payment on hold without explanation.8/14/19 TseJ: Spoke to Theresa AlexandroCPWD on status update for invoice dated 7/31/19 and was advised it will be presented at tonight's board meeting with update to follow.
11 | Design | Tse, Jason | 18-060-1674 |  | CPWD,Design Phase Employee Break Rm | 9600 | 8318 | 0 | 0 | 2018-05-11 |  |  | 8318 |  |  |  |  | N |  | Y
12 | Design | Tse, Jason | 18-060-1674 | [10 empty] | 8318.21 | 1806001 | 2018-07-17 | 11.11.19 SantanaL: Per JasonTse - this projects links to 13-170-1674 - most likely this amount will need to be written off.9/9/19 TseJ: Spoke to Tim Doyle/CPWD on 9/3/19 on invoicing status with no update. Payment on hold without explanation.8/14/19 TseJ: Spoke to Theresa AlexandroCPWD on status update for resubmitted invoice and was advised it will be presented at tonight's board meeting with update to follow.
13 | Design | Tse, Jason | 18-319-2017 |  | Castella Imports Tank Replacements | 3200 | 3002 | 44 | 44 | 2019-08-30 | 12/11/19 TseJ: Job completed. Client should not be billed for remaining $43.89. LiRo has not received review response from SCDPW since resubmission on 4/22/19 and have no further update to provide to client.07/25/19 TseJ: As per Stephanie Trapani, 7/15/19 mail check returned and mailed again 7/24/19.07/23/19 TseJ: Castella Imports mailed out $4,077.36 on 7/15/19 as per Stephanie Trapani from Castella.07/02/19 MessinaS 2.5 hrs left on wip billed out.7/9/19 TseJ: Advised Nicole Morello LiRo does not take credit card payments, but will accept check payable to LiRo Engineers in Syosset.7/2/19 TseJ: Nicole Morello contacted her finance department and awaiting update.7/1/19 TseJ: Follow up email to Nicole Morello on Invoice 1831901R for $2,668.68. Bill WIP to date.06/03MessinaS - 2.5 hour on wip-Jason out till 06/28.5/23/19 TseJ: Nicole Morello to check with her finance department and get back.5/21/19 TseJ: Follow up email to Nicole Morello on payment status. No response.5/16/19 TseJ: Left voicemail and follow up email to Nicole Morello on payment status.041919MessinaS - First invoice voided and revised P/E0 04/12/19 and sent out..4/11/19 TseJ: Will void first invoice and invoice all work through pay period 4/12/19 next week.3/28/19 TseJ: Need to follow up with SCDHS and SCDPW for their comments on project. | [6 empty] | N |  | N
14 | Design | Tse, Jason | 18-319-2017 | 1 |  |  |  |  | 44
15 | Design | Tse, Jason | 19-179-0383 |  | SCDPW Feasibility Study Wastewater Mgmt | 194891 | 19705 | 45325 | 11001 | 2019-10-11 | 11/4/19 TseJ: Invoice No. 002 submitted for $10,539.00.09/24/19 Messina-Invoice to be emailed to client thru 08/30/19-not all of wip billed due to milestones on certain phases.9/20/19 TseJ: Invoices need to be submitted to Raftelis by 1st of each month. | [6 empty] | N | 2019-01-23 | N
16 | Design | Tse, Jason | 19-179-0383 | 1 |  |  |  |  | 0
17 | Design | Tse, Jason | 19-179-0383 | 2 |  |  |  |  | 9225
18 | Design | Tse, Jason | 19-179-0383 | 4 |  |  |  |  | 1776
Total |  |  |  |  | 68850 | 64006 |  |  | 0 | 11826