## PHR WITH WIP & AR
[7 empty] | Utility Engineering : WIP and AR Tracking |  |  | 2019-12-13 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/10/2019 | WIP > 60 as of 12/10/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Utility Engineering | Burrus, Andre | 16-231-1366 |  | LT- Newtown Z5- Q204 36-41 28th St | 0 | 0 | 1103 | 1103 |  | PM: Andre BurrusDate: 12/2/2019A/R Delay: Proposal Issued, PO pending, emailed Crown Castle for PO status. PM: Andre Burrus 10/22/2019 Total WIP&gt;60 is as follows:- PO Waiting $1,103 (100.0%) | [6 empty] | N |  | Y
2 | Utility Engineering | Burrus, Andre | 16-231-1366 | 2 |  |  |  |  | 832
3 | Utility Engineering | Burrus, Andre | 16-231-1366 | 6 |  |  |  |  | 271
4 | Utility Engineering | Salerno, Michael | 16-346-1366 |  | Lightower Term Contract 14 Zone Planning | 565715 | 490615 | 0 | 0 | 2019-11-30 |  | 100 | [5 empty] | N |  | N
5 | Utility Engineering | Salerno, Michael | 16-346-1366 | [10 empty] | -0.1 | 00016-346-48 | 2019-05-14
6 | Utility Engineering | Stasco, Arin | 18-130-1364.A |  | AT&T ASE/NN/ADE NYC-ATT NYCT | 6293532 | 1827856 | 188686 | 72644 | 2019-11-30 | PM: A.STASCO 12/4/19 Total WIP&gt;60 is as follows; - Proposal Required $0 - 0%- PO Waiting $30,595 -58%- Invoice Submitted $16,096-31%- Other $5,638-11% | 4408 | 0 |  |  |  |  | N |  | N
7 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 76 |  |  |  |  | 1029
8 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 139 |  |  |  |  | 768
9 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 283 |  |  |  |  | 588
10 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 289 |  |  |  |  | 409
11 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 382 |  |  |  |  | 2197
12 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 383 |  |  |  |  | 1340
13 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 396 |  |  |  |  | 248
14 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 461 |  |  |  |  | 1715
15 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 467 |  |  |  |  | 1052
16 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 468 |  |  |  |  | 717
17 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 504 |  |  |  |  | 248
18 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 572 |  |  |  |  | 1365
19 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 575 |  |  |  |  | 179
20 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 583 |  |  |  |  | 579
21 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 608 |  |  |  |  | 60
22 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 631 |  |  |  |  | 179
23 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 632 |  |  |  |  | 2091
24 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 672 |  |  |  |  | 60
25 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 681 |  |  |  |  | 0
26 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 708 |  |  |  |  | 299
27 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 728 |  |  |  |  | 179
28 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 730 |  |  |  |  | 1304
29 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 746 |  |  |  |  | 3476
30 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 753 |  |  |  |  | 60
31 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 762 |  |  |  |  | 3881
32 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 763 |  |  |  |  | 644
33 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 764 |  |  |  |  | 60
34 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 766 |  |  |  |  | 748
35 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 767 |  |  |  |  | 60
36 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 768 |  |  |  |  | 90
37 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 769 |  |  |  |  | 209
38 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 770 |  |  |  |  | 209
39 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 771 |  |  |  |  | 90
40 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 772 |  |  |  |  | 90
41 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 773 |  |  |  |  | 90
42 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 774 |  |  |  |  | 351
43 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 775 |  |  |  |  | 120
44 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 776 |  |  |  |  | 90
45 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 777 |  |  |  |  | 120
46 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 778 |  |  |  |  | 90
47 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 779 |  |  |  |  | 1284
48 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 789 |  |  |  |  | 434
49 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 791 |  |  |  |  | 90
50 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 792 |  |  |  |  | 90
51 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 793 |  |  |  |  | 1049
52 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 797 |  |  |  |  | 1549
53 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 798 |  |  |  |  | 5712
54 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 799 |  |  |  |  | 90
55 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 800 |  |  |  |  | 590
56 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 801 |  |  |  |  | 1213
57 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 802 |  |  |  |  | 120
58 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 803 |  |  |  |  | 1223
59 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 804 |  |  |  |  | 90
60 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 805 |  |  |  |  | 418
61 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 806 |  |  |  |  | 1666
62 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 811 |  |  |  |  | 2593
63 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 812 |  |  |  |  | 1684
64 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 813 |  |  |  |  | 243
65 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 814 |  |  |  |  | 609
66 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 816 |  |  |  |  | 2134
67 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 817 |  |  |  |  | 411
68 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 825 |  |  |  |  | 120
69 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 828 |  |  |  |  | 2892
70 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 829 |  |  |  |  | 5628
71 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 830 |  |  |  |  | 1673
72 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 840 |  |  |  |  | 2737
73 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 845 |  |  |  |  | 837
74 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 846 |  |  |  |  | 656
75 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 848 |  |  |  |  | 404
76 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 849 |  |  |  |  | 312
77 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 850 |  |  |  |  | 445
78 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 853 |  |  |  |  | 464
79 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 854 |  |  |  |  | 60
80 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 857 |  |  |  |  | 428
81 | Utility Engineering | Stasco, Arin | 18-130-1364.A | 859 |  |  |  |  | 1710
82 | Utility Engineering | Stasco, Arin | 18-130-1364.A | FPM |  |  |  |  | 3913
83 | Utility Engineering | Stasco, Arin | 18-130-1364.A | [10 empty] | 0.01 | 18-130.A1041 | 2019-07-30
84 | Utility Engineering | Stasco, Arin | 18-130-1364.B |  | AT&T ASE/NN/ADE LI-ATT NYCT | 344760 | 113787 | 15198 | 8484 | 2019-11-30 | PM: A.STASCO 12/4/19 Total WIP&gt;60 is as follows:- Proposal Required $0 - 0%- PO Waiting $5,170-46%- Invoice Submitted $5,922-53%- Other $30-0% | [6 empty] | N |  | N
85 | Utility Engineering | Stasco, Arin | 18-130-1364.B | 35 |  |  |  |  | 30
86 | Utility Engineering | Stasco, Arin | 18-130-1364.B | 44 |  |  |  |  | 855
87 | Utility Engineering | Stasco, Arin | 18-130-1364.B | 48 |  |  |  |  | 837
88 | Utility Engineering | Stasco, Arin | 18-130-1364.B | 49 |  |  |  |  | 165
89 | Utility Engineering | Stasco, Arin | 18-130-1364.B | 50 |  |  |  |  | 6597
90 | Utility Engineering | Stasco, Arin | 18-130-1364.F |  | AT&T ROUTINE NYC - ATT NYCT | 1623746 | 956850 | 60604 | 18127 | 2019-10-31 | PM: A.STASCO 12/4/19 Total WIP&gt;60 is as follows: - Proposal Required $0 - 0%- PO Waiting $10,485-39%- Invoice Submitted $12,402-46%- Other $4,181-15% | [6 empty] | N |  | N
91 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 39 |  |  |  |  | -285
92 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 90 |  |  |  |  | 2433
93 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 109 |  |  |  |  | 747
94 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 149 |  |  |  |  | 248
95 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 155 |  |  |  |  | 285
96 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 177 |  |  |  |  | 120
97 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 189 |  |  |  |  | 192
98 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 191 |  |  |  |  | 1016
99 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 192 |  |  |  |  | 192
100 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 199 |  |  |  |  | 9978
101 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 200 |  |  |  |  | 809
102 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 201 |  |  |  |  | 179
103 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 202 |  |  |  |  | 777
104 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 203 |  |  |  |  | 179
105 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 204 |  |  |  |  | 179
106 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 205 |  |  |  |  | 657
107 | Utility Engineering | Stasco, Arin | 18-130-1364.F | 206 |  |  |  |  | 179
108 | Utility Engineering | Stasco, Arin | 18-130-1364.F | FPM |  |  |  |  | 243
109 | Utility Engineering | Stasco, Arin | 18-130-1364.G |  | AT&T ROUTINE LI - ATT NYCT | 80868 | 38131 | 14033 | 5705 | 2019-11-30 | PM: A.STASCO 12/4/19 Total WIP &gt;60 Days is as follows:- Proposal Required $0 - 0%- PO Waiting $4,240-100%- Invoice Submitted $0-0%- Other $0-0% | [6 empty] | N |  | N
110 | Utility Engineering | Stasco, Arin | 18-130-1364.G | 9 |  |  |  |  | 1195
111 | Utility Engineering | Stasco, Arin | 18-130-1364.G | 10 |  |  |  |  | 4510
112 | Utility Engineering | Stasco, Arin | 18-130-1364.H |  | AT&T MOBILITY LI - ATT NYCT | 512746 | 79475 | 38803 | 13730 | 2019-11-30 | PM: A.STASCO 12/4/19 Total WIP&gt;60 is as:- Proposal Required $0 - 0%- PO Waiting $3,993-23%- Invoice Submitted $12,216-69%- Other $1,495-8% | 4 | [5 empty] | N |  | N
113 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 7 |  |  |  |  | 938
114 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 34 |  |  |  |  | 369
115 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 47 |  |  |  |  | 190
116 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 49 |  |  |  |  | 155
117 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 51 |  |  |  |  | 250
118 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 58 |  |  |  |  | 250
119 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 68 |  |  |  |  | 440
120 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 72 |  |  |  |  | 380
121 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 77 |  |  |  |  | 209
122 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 81 |  |  |  |  | 310
123 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 88 |  |  |  |  | 215
124 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 102 |  |  |  |  | 322
125 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 107 |  |  |  |  | 274
126 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 120 |  |  |  |  | 1517
127 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 121 |  |  |  |  | 165
128 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 122 |  |  |  |  | 2801
129 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 123 |  |  |  |  | 4470
130 | Utility Engineering | Stasco, Arin | 18-130-1364.H | 124 |  |  |  |  | 478
131 | Utility Engineering | Stasco, Arin | 18-130-1364.I |  | AT&T - MOBILITY NYC - ATT NYCT | 1847918 | 396035 | 73627 | 32300 | 2019-11-30 | PM: A.STASCO 12/4/19 Total WIP&gt;60 is as follows:- Proposal Required $0 - 0%- PO Waiting $4,461-18%- Invoice Submitted $18,859-75%- Other $1,888-7% | 8678 | [5 empty] | N |  | N
132 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 11 |  |  |  |  | 956
133 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 14 |  |  |  |  | 460
134 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 34 |  |  |  |  | 1912
135 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 62 |  |  |  |  | 1288
136 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 69 |  |  |  |  | 607
137 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 86 |  |  |  |  | 2753
138 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 114 |  |  |  |  | -460
139 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 208 |  |  |  |  | 155
140 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 222 |  |  |  |  | 155
141 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 233 |  |  |  |  | 107
142 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 234 |  |  |  |  | 48
143 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 240 |  |  |  |  | 48
144 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 241 |  |  |  |  | 202
145 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 244 |  |  |  |  | 322
146 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 249 |  |  |  |  | 48
147 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 252 |  |  |  |  | 369
148 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 259 |  |  |  |  | 274
149 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 268 |  |  |  |  | 369
150 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 272 |  |  |  |  | 95
151 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 273 |  |  |  |  | 155
152 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 286 |  |  |  |  | 107
153 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 287 |  |  |  |  | 48
154 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 289 |  |  |  |  | 95
155 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 292 |  |  |  |  | 48
156 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 295 |  |  |  |  | 48
157 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 299 |  |  |  |  | 709
158 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 305 |  |  |  |  | 371
159 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 308 |  |  |  |  | 155
160 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 309 |  |  |  |  | 48
161 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 322 |  |  |  |  | 73
162 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 324 |  |  |  |  | 1046
163 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 326 |  |  |  |  | 190
164 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 328 |  |  |  |  | 165
165 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 331 |  |  |  |  | 165
166 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 332 |  |  |  |  | 95
167 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 336 |  |  |  |  | 165
168 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 344 |  |  |  |  | 0
169 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 354 |  |  |  |  | 956
170 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 359 |  |  |  |  | 2370
171 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 360 |  |  |  |  | 896
172 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 361 |  |  |  |  | 1397
173 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 362 |  |  |  |  | 404
174 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 368 |  |  |  |  | 3994
175 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 370 |  |  |  |  | 1445
176 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 372 |  |  |  |  | 954
177 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 375 |  |  |  |  | 165
178 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 377 |  |  |  |  | 128
179 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 378 |  |  |  |  | 3734
180 | Utility Engineering | Stasco, Arin | 18-130-1364.I | 379 |  |  |  |  | 2174
181 | Utility Engineering | Stasco, Arin | 18-130-1364.I | FPM |  |  |  |  | 298
182 | Utility Engineering | Stasco, Arin | 18-130-1364.I | [10 empty] | -0.01 | 018-130-I374 | 2019-08-13
183 | Utility Engineering | Totillo, Frank | 16-189-1366 |  | LT- Newtown Z1- Q610 45-30 36th St | 2300 | 0 | 9116 | 9116 |  | PM: F. Totillo 12/2/19 PO Waiting $9,116 (100.0%) Attemps have been make to contact Program Manager M. McGuire, with no response. | [6 empty] | N |  | Y
184 | Utility Engineering | Totillo, Frank | 16-189-1366 | 2 |  |  |  |  | 1619
185 | Utility Engineering | Totillo, Frank | 16-189-1366 | 4 |  |  |  |  | 743
186 | Utility Engineering | Totillo, Frank | 16-189-1366 | 6 |  |  |  |  | 4913
187 | Utility Engineering | Totillo, Frank | 16-189-1366 | 7 |  |  |  |  | 1842
188 | Utility Engineering | Totillo, Frank | 16-346-1366.01 |  | Lightower Term Contract 14 - Schools | 208695 | 165878 | 38457 | 38457 | 2019-03-12 | 11/30/19-Isaac has advised there is a potentisl risk of $40K on all five task orders for lightower. He is attempting to get work orders for as much as he can. | [6 empty] | N |  | Y
189 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | 50 |  |  |  |  | 3518
190 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | 58 |  |  |  |  | 3189
191 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | 60 |  |  |  |  | 9490
192 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | 61 |  |  |  |  | 5263
193 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | 62 |  |  |  |  | 4498
194 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | K157 |  |  |  |  | 3931
195 | Utility Engineering | Totillo, Frank | 16-346-1366.01 | Q315 |  |  |  |  | 8568
196 | Utility Engineering | Totillo, Frank | 16-346-1366.02 |  | Lightower Term Contract 14 - NYCHA | 16000 | 500 | 19514 | 19514 | 2017-12-05 | PM: F. Totillo 10/22/19 Total WIP&gt;60 is as follows:- Pending PO: $19,514 (100%)Attempts have been made to contact Project Manager Matt Cassamassino. | [6 empty] | N |  | N
197 | Utility Engineering | Totillo, Frank | 16-346-1366.02 | 2505BE |  |  |  |  | 1737
198 | Utility Engineering | Totillo, Frank | 16-346-1366.02 | 307BLA |  |  |  |  | 5828
199 | Utility Engineering | Totillo, Frank | 16-346-1366.02 | 812ASH |  |  |  |  | 11949
200 | Utility Engineering | Totillo, Frank | 16-346-1366.04 |  | Lightower Term Contract 14 - Proj Ranger | 557581 | 572342 | 16702 | 14317 | 2019-09-13 | PM: F. Totillo 12/2/19 Total WIP &gt;60 is as follows; Other $14,317 100% Client stated that a new job will be opened for this locaton & we will be able to invoice upon receipt of the new job. | [6 empty] | N |  | N
201 | Utility Engineering | Totillo, Frank | 16-346-1366.04 | 8 |  |  |  |  | 14317 |  | PM: F. Totillo 12/2/19 Total WIP &gt; 60 is as follows; Other $14,317 100% Client stated that a new job will be opened for this locaton & we will be able to invoice upon receipt of the new job.
202 | Utility Engineering | Totillo, Frank | 16-346-1366.05 |  | Lightower Term Contract 14 - Health/Hosp | 64750 | 68450 | 2757 | 2757 | 2019-05-31 | PM: F. Totillo 12/2/19 Total WIP&gt;60 is as follows:Other $2,757 (100%)Attemps have been make to contact Project Manager Michael Cassamassino. | [6 empty] | N |  | N
203 | Utility Engineering | Totillo, Frank | 16-346-1366.05 | 1 |  |  |  |  | 1408
204 | Utility Engineering | Totillo, Frank | 16-346-1366.05 | 2 |  |  |  |  | 1349
205 | Utility Engineering | Totillo, Frank | 17-072-1364 |  | At&T- Requests for Watchman | 5456 | 2068 | 321 | 321 | 2019-07-20 | PM: F. Totillo 12/2/19 Total WIP&gt;60 is as follows:Other $321 (100.0%) | [6 empty] | N |  | N
206 | Utility Engineering | Totillo, Frank | 17-072-1364 | 10 |  |  |  |  | 321 |  | 12/2/19 Hours to be transferred.
207 | Utility Engineering | Totillo, Frank | 17-072-1364 | [10 empty] | -69.2 | 000017-072-5 | 2018-09-26 | 11/12/18 Check will be sent next week per Ken O'Connor.
208 | Utility Engineering | Totillo, Frank | 17-073-1364 |  | AT&T-Requests for Watchman NYC | 14380 | 4314 | 273 | 273 | 2018-11-30 | PM: F. Totillo 12/2/19 Total WIP&gt;60 is as follows:Other $273 (100%) | [6 empty] | N |  | N
209 | Utility Engineering | Totillo, Frank | 17-073-1364 | 18 |  |  |  |  | 135 |  | 12/2/19 Hours to be rolled back to prior invoice.
210 | Utility Engineering | Totillo, Frank | 17-073-1364 | 19 |  |  |  |  | 138 |  | 12/2/19 Hours to be transferred.
211 | Utility Engineering | Totillo, Frank | 17-176-0451 |  | Verizon FIOS Block Design | 215030 | 228368 | 6299 | 224 | 2019-11-30 | PM: F. Totillo 12/2/19 Total WIP &gt;60 days is as follows: Invoice submitted $987 (100%) | [6 empty] | N |  | N
212 | Utility Engineering | Totillo, Frank | 17-176-0451 | 184 |  |  |  |  | 112
213 | Utility Engineering | Totillo, Frank | 17-176-0451 | 189 |  |  |  |  | 112
214 | Utility Engineering | Totillo, Frank | 18-016-0022 |  | AT&T - 2018 AT&T Term Contract | 743693 | 722590 | 225685 | 201343 | 2019-11-30 | PM: W.Mohr 12/2/19 Total WIP&gt;60 as follows:- Proposal Submitted: $190,271 (93%)- Waiting for Milestone $12,933 (6%) - Invoice submitted: $1,106 (0.5%)- Other: $996 (0.5%) |  | 1904 |  |  |  |  | N |  | N
215 | Utility Engineering | Totillo, Frank | 18-016-0022 | 2 |  |  |  |  | 1005 |  | BUH: Michael Smith PM: Andre BurrusDate: 12/2/2019A/R Delay: Proposal Issued, Pending PO.
216 | Utility Engineering | Totillo, Frank | 18-016-0022 | 30 |  |  |  |  | 2341 |  | BUH: Michael Smith PM: Andre BurrusDate: 12/2/2019A/R Delay: Site Cancelled, Proposal Issued on 5/9/18, PO Pending.
217 | Utility Engineering | Totillo, Frank | 18-016-0022 | 31 |  |  |  |  | 13519 |  | BUH: Michael Smith PM: Andre BurrusDate: 12/2/2019A/R Delay: Proposal Issued on 5/13/19, Susan (AT&T) has been contacted again, PO Pending..
218 | Utility Engineering | Totillo, Frank | 18-016-0022 | 44 |  |  |  |  | 11928 |  | BUH: Michael Smith PM: Andre BurrusDate: 12/2/2019A/R Delay: Site now Active.
219 | Utility Engineering | Totillo, Frank | 18-016-0022 | 52 |  |  |  |  | 8251 |  | COMPLETE
220 | Utility Engineering | Totillo, Frank | 18-016-0022 | 57 |  |  |  |  | 12459 |  | JOB STILL OPEN
221 | Utility Engineering | Totillo, Frank | 18-016-0022 | 59 |  |  |  |  | 19388 |  | COMPLETE
222 | Utility Engineering | Totillo, Frank | 18-016-0022 | 67 |  |  |  |  | 13850
223 | Utility Engineering | Totillo, Frank | 18-016-0022 | 68 |  |  |  |  | 28691
224 | Utility Engineering | Totillo, Frank | 18-016-0022 | 70 |  |  |  |  | 119
225 | Utility Engineering | Totillo, Frank | 18-016-0022 | 72 |  |  |  |  | 3826 |  | BUH: Michael Smith PM: Andre BurrusDate: 12/2/2019A/R Delay: Addtional work required, proposal to be revised.
226 | Utility Engineering | Totillo, Frank | 18-016-0022 | 74 |  |  |  |  | 6079 |  | 12/3/19 Supplemental proposal submited. Client requested additional information on charges.
227 | Utility Engineering | Totillo, Frank | 18-016-0022 | 77 |  |  |  |  | 24776
228 | Utility Engineering | Totillo, Frank | 18-016-0022 | 94 |  |  |  |  | 17468
229 | Utility Engineering | Totillo, Frank | 18-016-0022 | 101 |  |  |  |  | 10714
230 | Utility Engineering | Totillo, Frank | 18-016-0022 | 102 |  |  |  |  | 1499
231 | Utility Engineering | Totillo, Frank | 18-016-0022 | 105 |  |  |  |  | 3144 |  | 12/2/19 Additional funding request sent
232 | Utility Engineering | Totillo, Frank | 18-016-0022 | 107 |  |  |  |  | 462 |  | 12/2/19 Hours to be transferred
233 | Utility Engineering | Totillo, Frank | 18-016-0022 | 110 |  |  |  |  | 1106
234 | Utility Engineering | Totillo, Frank | 18-016-0022 | 115 |  |  |  |  | 20136
235 | Utility Engineering | Totillo, Frank | 18-016-0022 | 116 |  |  |  |  | 0
236 | Utility Engineering | Totillo, Frank | 18-016-0022 | 119 |  |  |  |  | 297 |  | Negative WIP
237 | Utility Engineering | Totillo, Frank | 18-016-0022 | 120 |  |  |  |  | 285 |  | Move 3hrs to 18-130-1364 ph373
238 | Utility Engineering | Totillo, Frank | 18-016-0022 | [10 empty] | -1000 | 00018-016-43 | 2019-03-08
239 | Utility Engineering | Totillo, Frank | 18-016-0022 | [10 empty] | 5.05 | 00018-016-83 | 2019-05-09
240 | Utility Engineering | Totillo, Frank | 18-016-0022 | [10 empty] | 2899.25 | 0018-016-101 | 2019-07-29 | Scheduled to be paid 12/16/2019- LSmythe
241 | Utility Engineering | Totillo, Frank | 18-048-1365 |  | JEMB - 2018 75 Broad St Tenant Changes | 22555 | 16380 | 4850 | 193 | 2019-04-19 | PM: F Totillo 12/2/19 Total WIP &gt;60 Days is as follows: Invoice Submitted: $3,034 100% | [6 empty] | N |  | N
242 | Utility Engineering | Totillo, Frank | 18-048-1365 | 7 |  |  |  |  | 193 |  | BUH: M.Smith PM: S. Blumberg 5/7/19 phase 5 on hold pending tenant-bldg mgnt agreement
243 | Utility Engineering | Totillo, Frank | 18-135-1865 |  | CDL Utilities Contract | 20775 | 11219 | 10374 | 2593 | 2019-04-10 | PM: Frank Totillo; Date: 12/2/19 Total WIP &gt; 60 Days is as follows: Waiting for Milestone $1,508 66%, Other $771 34% | [6 empty] | N |  | N
244 | Utility Engineering | Totillo, Frank | 18-135-1865 | 3 |  |  |  |  | 771 |  | PM: Frank Totillo; Date: 12/2/19 Total WIP &gt; 60 Days is as follows: $771 100% Hours to be transferred to the correct phase
245 | Utility Engineering | Totillo, Frank | 18-135-1865 | 4 |  |  |  |  | 705 |  | PM: Frank Totillo; Date: 12/2/19 Total WIP &gt; 60 Days is as follows: Waiting for Milestone $600 100%
246 | Utility Engineering | Totillo, Frank | 18-135-1865 | 5 |  |  |  |  | 559 |  | PM: Frank Totillo; Date: 12/2/19 Total WIP &gt; 60 Days is as follows: Waiting for Milestone $454 100%
247 | Utility Engineering | Totillo, Frank | 18-135-1865 | 6 |  |  |  |  | 559 |  | PM: Frank Totillo; Date: 12/2/19 Total WIP &gt; 60 Days is as follows: Waiting for Milestone $454 100%
248 | Utility Engineering | Totillo, Frank | 18-326-1800 |  | Altice - RR Crossing Design | 74100 | 72800 | 453 | 0 | 2019-10-25 | BUH: M. SmithPM: F. Totillo9/26/19 Total WIP&gt;60 is as follows;Invoice submitted $10,679 100% | 6100 | [5 empty] | N |  | N
249 | Utility Engineering | Totillo, Frank | 19-036-2105 |  | Crown Castle 2019 | 113325 | 68691 | 13642 | 2810 | 2019-11-30 | PM: F. Totillo 12/3/19 Total WIP &gt;60 is as follows:- Pending PO $2,389 (100%) | [6 empty] | N |  | N
250 | Utility Engineering | Totillo, Frank | 19-036-2105 | 17 |  |  |  |  | 2110
251 | Utility Engineering | Totillo, Frank | 19-036-2105 | 23 |  |  |  |  | 699
252 | Utility Engineering | Totillo, Frank | 19-048-2014 |  | Cyient - 2019 | 46236 | 20765 | 20552 | 3346 | 2019-11-30 | PM: F. Totillo 12/2/19 Total WIP &gt;60 Days is as follows:- Waiting for Milestone: $52 (16%)- Invoiced: $89 (28%)- Other: $178 (56%) | [6 empty] | N |  | N
253 | Utility Engineering | Totillo, Frank | 19-048-2014 | 71 |  |  |  |  | 178 |  | 12/2/19 Hours to be transferred to correct Phase
254 | Utility Engineering | Totillo, Frank | 19-048-2014 | 96 |  |  |  |  | 52 |  | 12/2/19 Pending Bldg Mgt approval
255 | Utility Engineering | Totillo, Frank | 19-048-2014 | 101 |  |  |  |  | 356 |  | 12/2/19 Invoiced
256 | Utility Engineering | Totillo, Frank | 19-048-2014 | 108 |  |  |  |  | 89
257 | Utility Engineering | Totillo, Frank | 19-048-2014 | 109 |  |  |  |  | 534
258 | Utility Engineering | Totillo, Frank | 19-048-2014 | 110 |  |  |  |  | 89
259 | Utility Engineering | Totillo, Frank | 19-048-2014 | 111 |  |  |  |  | 579
260 | Utility Engineering | Totillo, Frank | 19-048-2014 | 112 |  |  |  |  | 401
261 | Utility Engineering | Totillo, Frank | 19-048-2014 | 113 |  |  |  |  | 401
262 | Utility Engineering | Totillo, Frank | 19-048-2014 | 114 |  |  |  |  | 223
263 | Utility Engineering | Totillo, Frank | 19-048-2014 | 116 |  |  |  |  | 178
264 | Utility Engineering | Totillo, Frank | 19-048-2014 | 117 |  |  |  |  | 89
265 | Utility Engineering | Totillo, Frank | 19-048-2014 | 118 |  |  |  |  | 89
266 | Utility Engineering | Totillo, Frank | 19-048-2014 | 119 |  |  |  |  | 89
Total |  |  |  |  | 761049 | 894737 |  |  | 19290 | 1904