## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Wong, David | 15-121-0278.02 |  | NYCHA Cypress Hills Houses | 2089795 | 1503160 | 65382 | 28846 | 2019-09-27 | DW 6/2/2019 All 5 Liro staffing requisitions were submitted to NYCHA for payment on Friday, May 24, 2019 as follows: Cypress req #5: $262,877.57 (ebuilder),Tilden req #4: $244,331.95,. Melrose req #2: $ 87,183.15 (ebuilder) Eastchester req#1: $ 23,685.61 Webster req#1: $ 44,797.11 Total invoices due: $662,875.39 | [6 empty] | N |  | N
2 | CM | Wong, David | 15-121-0278.02 | CONSTR |  |  |  |  | 28846
3 | CM | Wong, David | 15-121-0278.03 |  | NYCHA Tilden Houses | 1249132 | 919025 | 102908 | 83573 | 2019-06-07 | 10/29/19- Submiting request for a supplemental approx $115K (transfer of funds from OOP to Staffing) within next two weeks. | [6 empty] | N |  | N
4 | CM | Wong, David | 15-121-0278.03 | CONSTR |  |  |  |  | 83573
5 | CM | Wong, David | 15-121-0278.04 |  | NYCHA Roofing Restoration/Rooftop Repair | 72354 | 72134 | 16215 | 16215 | 2019-03-31 | 12/2/19-Wong advised CJ does not want to pay the $16K, submitting a formal request for the additional funding required for pre-con cost over-runs. 10/29/2019 DW Submitting Supplemental for Pre-Const Cost overrun $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. | [6 empty] | N |  | Y
6 | CM | Wong, David | 15-121-0278.04 | CONSTR |  |  |  |  | 0
7 | CM | Wong, David | 15-121-0278.04 | PRECON |  |  |  |  | 16215
8 | CM | Wong, David | 15-121-0278.05 |  | NYCHA Melrose Houses Roofing Restoration | 931897 | 460817 | 312716 | 131888 | 2019-08-30 | Pre-Construction contract is paid 100% and closed out. Pre-Const Cost overrun of $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. $16,215.00 to be recovered once the Construction staffing T.O. is approved. Task orders for Melrose, Eastchester & Webster not expected until Dec/Jan 2019. | 86073 | 243606 |  |  |  |  | N |  | N
9 | CM | Wong, David | 15-121-0278.05 | 1 |  |  |  |  | 131888 |  | Pre-Construction contract is paid 100% and closed out. Pre-Const Cost overrun of $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. $16,215.00 to be recovered once the Construction staffing T.O. is approved. Task orders for Melrose, Eastchester & Webster not expected until Dec/Jan 2019.
10 | CM | Wong, David | 15-121-0278.05 | [10 empty] | 243606.49 | 3 | 2019-08-14
11 | CM | Wong, David | 15-121-0278.06 |  | NYCHA Webster Houses Roofing Restoration | 634580 | 236305 | 220377 | 83327 | 2019-08-30 | Pre-Construction contract is paid 100% and closed out. Pre-Const Cost overrun of $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. $16,215.00 to be recovered once the Construction staffing T.O. is approved. Task orders for Melrose, Eastchester & Webster not expected until Dec/Jan 2019. | 108887 | [5 empty] | N |  | N
12 | CM | Wong, David | 15-121-0278.06 | 1 |  |  |  |  | 83327 |  | Pre-Construction contract is paid 100% and closed out. Pre-Const Cost overrun of $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. $16,215.00 to be recovered once the Construction staffing T.O. is approved. Task orders for Melrose, Eastchester & Webster not expected until Dec/Jan 2019.
13 | CM | Wong, David | 15-121-0278.07 |  | NYCHA Eastchester Houses Roofing Restor | 1079068 | 253921 | 262370 | 98697 | 2019-08-30 | Pre-Construction contract is paid 100% and closed out. Pre-Const Cost overrun of $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. $16,215.00 to be recovered once the Construction staffing T.O. is approved. Task orders for Melrose, Eastchester & Webster not expected until Dec/Jan 2019. | 122326 | [5 empty] | N |  | N
14 | CM | Wong, David | 15-121-0278.07 | 1 |  |  |  |  | 98697 |  | Pre-Construction contract is paid 100% and closed out. Pre-Const Cost overrun of $16,215.00 b/w Melrose and Eastchester due to extensive design reviews. $16,215.00 to be recovered once the Construction staffing T.O. is approved. Task orders for Melrose, Eastchester & Webster not expected until Dec/Jan 2019.
Total |  |  |  |  | 979968 | 885092 |  |  | 317286 | 243606