## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Env | Zanoni, Christopher | 07-17-200E |  | CM1319 ASBTS & Lead Monitoring | 8721596 | 5356736 | 36340 | 36340 | 2016-11-30 | 10/30 SZ - Submitted all requests to audit dept. Ball is now in their court. Waiting to see if this audit will be complete and then LiRo can go to second phase of collecting retainage and invoicing for shortages. |  | 19120 |  |  |  |  | N |  | Y
2 | Env | Zanoni, Christopher | 07-17-200E | 92 |  |  |  |  | 32150
3 | Env | Zanoni, Christopher | 07-17-200E | 156 |  |  |  |  | 3088
4 | Env | Zanoni, Christopher | 07-17-200E | 184 |  |  |  |  | 140
5 | Env | Zanoni, Christopher | 07-17-200E | TEMP |  |  |  |  | 962
6 | Env | Zanoni, Christopher | 07-17-200E | [10 empty] | 11297.5 | 34 | 2014-08-14 | 12/2019 - SZ everything has been submitted to auditor, her house burnt down so she stated it is taking longer. i have emailed to rec any status update but no reply yet.
7 | Env | Zanoni, Christopher | 07-17-200E | [10 empty] | 1143.37 | 36 | 2014-11-14 | 12/2019 - SZ everything has been submitted to auditor, her house burnt down so she stated it is taking longer. i have emailed to rec any status update but no reply yet.
8 | Env | Zanoni, Christopher | 07-17-200E | [10 empty] | 4520.64 | 38 | 2015-05-20 | 10/30 SZ - Submitted all requests to audit dept. Ball is now in their court. Waiting to see if this audit will be complete and then LiRo can go to second phase of collecting retainage and invoicing for shortages.
9 | Env | Zanoni, Christopher | 07-17-200E | [10 empty] | 17.67 | 40 | 2015-07-28 | 12/2019 - SZ everything has been submitted to auditor, her house burnt down so she stated it is taking longer. i have emailed to rec any status update but no reply yet.
10 | Env | Zanoni, Christopher | 07-17-200E | [10 empty] | 2148.33 | 41 | 2015-12-24 | 12/2019 - SZ everything has been submitted to auditor, her house burnt down so she stated it is taking longer. i have emailed to rec any status update but no reply yet.
11 | Env | Zanoni, Christopher | 07-17-200E | [10 empty] | -7.2 | 00000000037B | 2015-03-11 | 12/2019 - SZ everything has been submitted to auditor, her house burnt down so she stated it is taking longer. i have emailed to rec any status update but no reply yet.
12 | Env | Zanoni, Christopher | 08-40-200F |  | Health & Hospital Corp, System Wide Env | 829199 | 581596 | 0 | 0 | 2017-11-30 |  |  | 38115 |  |  |  |  | N |  | Y
13 | Env | Zanoni, Christopher | 08-40-200F | [10 empty] | 177.75 | 00000GMHPM01 | 2012-10-10 | 12/2019 - Liro is sending open status reports to HHC mgmt. however, if it is not capital we must direct our emails to PM's. Al Pistone is the PM
14 | Env | Zanoni, Christopher | 08-40-200F | [10 empty] | 8494.63 | 00000GMHTVOI | 2012-10-10 | 12/2019 - Liro is sending open status reports to HHC mgmt. however, if it is not capital we must direct our emails to PM's. Al Pistone is the PM
15 | Env | Zanoni, Christopher | 08-40-200F | [10 empty] | 13914 | 000KINGSBLDB | 2012-02-27 | 9/13/2019 Sz Per Chris & Peter they have been working with Daniel Gadioma on three outstanding invoices. LAst correspondence was 6/2019
16 | Env | Zanoni, Christopher | 08-40-200F | [10 empty] | 8567.74 | 0GOLD026-038 | 2011-11-29
17 | Env | Zanoni, Christopher | 08-40-200F | [10 empty] | 6961.03 | COOLER030-35 | 2011-11-30 | 12/2019 - Liro is sending open status reports to HHC mgmt. however, if it is not capital we must direct our emails to PM's. Al Pistone is the PM
18 | Env | Zanoni, Christopher | 11-22-0113 |  | DASNY Term Contract 157548 | 3623824 | 3925683 | 169318 | 168693 | 2019-12-31 |  | 19656 | 362722 |  |  |  |  | N |  | Y
19 | Env | Zanoni, Christopher | 11-22-0113 | 15 |  |  |  |  | 9575
20 | Env | Zanoni, Christopher | 11-22-0113 | 16 |  |  |  |  | 1598
21 | Env | Zanoni, Christopher | 11-22-0113 | 21 |  |  |  |  | 965
22 | Env | Zanoni, Christopher | 11-22-0113 | 42 |  |  |  |  | 187
23 | Env | Zanoni, Christopher | 11-22-0113 | 74 |  |  |  |  | 9538
24 | Env | Zanoni, Christopher | 11-22-0113 | 107 |  |  |  |  | 10899
25 | Env | Zanoni, Christopher | 11-22-0113 | 134 |  |  |  |  | 127
26 | Env | Zanoni, Christopher | 11-22-0113 | 136 |  |  |  |  | 4400
27 | Env | Zanoni, Christopher | 11-22-0113 | 138 |  |  |  |  | 3735
28 | Env | Zanoni, Christopher | 11-22-0113 | 141 |  |  |  |  | 5965
29 | Env | Zanoni, Christopher | 11-22-0113 | 146 |  |  |  |  | 3473
30 | Env | Zanoni, Christopher | 11-22-0113 | 149 |  |  |  |  | 2317
31 | Env | Zanoni, Christopher | 11-22-0113 | 151 |  |  |  |  | 1956
32 | Env | Zanoni, Christopher | 11-22-0113 | 153 |  |  |  |  | 7034
33 | Env | Zanoni, Christopher | 11-22-0113 | 155 |  |  |  |  | 5835
34 | Env | Zanoni, Christopher | 11-22-0113 | 156 |  |  |  |  | 2644
35 | Env | Zanoni, Christopher | 11-22-0113 | 158 |  |  |  |  | 5169
36 | Env | Zanoni, Christopher | 11-22-0113 | 159 |  |  |  |  | 3218
37 | Env | Zanoni, Christopher | 11-22-0113 | 161 |  |  |  |  | 2047
38 | Env | Zanoni, Christopher | 11-22-0113 | 162 |  |  |  |  | 1834
39 | Env | Zanoni, Christopher | 11-22-0113 | 165 |  |  |  |  | 1404
40 | Env | Zanoni, Christopher | 11-22-0113 | 168 |  |  |  |  | 5118
41 | Env | Zanoni, Christopher | 11-22-0113 | 170 |  |  |  |  | 8095
42 | Env | Zanoni, Christopher | 11-22-0113 | 172 |  |  |  |  | 3283
43 | Env | Zanoni, Christopher | 11-22-0113 | 174 |  |  |  |  | -235
44 | Env | Zanoni, Christopher | 11-22-0113 | 176 |  |  |  |  | 32644
45 | Env | Zanoni, Christopher | 11-22-0113 | 178 |  |  |  |  | 3028
46 | Env | Zanoni, Christopher | 11-22-0113 | 181 |  |  |  |  | 6496
47 | Env | Zanoni, Christopher | 11-22-0113 | 185 |  |  |  |  | 3278
48 | Env | Zanoni, Christopher | 11-22-0113 | BRONXF |  |  |  |  | -1605
49 | Env | Zanoni, Christopher | 11-22-0113 | CUNY |  |  |  |  | 5743
50 | Env | Zanoni, Christopher | 11-22-0113 | OOP |  |  |  |  | -3768
51 | Env | Zanoni, Christopher | 11-22-0113 | TEMP |  |  |  |  | 22697
52 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 7742.31 | 0000000003-1 | 2016-05-02 | SZ 11/20/19 I found backup for this invoice and provided for Chris. He stated he would handle with Raphael.
53 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 5886.02 | 0000000010-1 | 2018-11-28 | 12/9/19 SZ never rec'd info from Raphael. Waiting on Chris to give me contact information to contact DASNY PM.9/5/19 SZ - Based on our meeting with Raphael. This project has a work authorization. Rapheal will prepare a Application for payment for it. Expecation of payment 2 months.
54 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 9538.34 | 0000000011-1 | 2018-06-14 | SZ 12/9/19 Partial payment made. need to address with Chris on who is PM9/5/19 SZ $14,363.43 partial application of payment was received and sent to Albany, remaining amount will be sent on a another application. Work authorization was sent for entire amount. Expect to invoice remaining amount end of October
55 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 17218.66 | 0000000058-1 | 2019-01-16 | 1SZ 12/9/19 Chris will handle with Raphael.9/2019 - Recently Chris prepared SCP for Client to get work authorizations and processing of payment- Need to reach back out to Ed Wagner to set up a meeting tto discuss
56 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 17680.09 | 0000000085-1 | 2019-01-30 | 10/7/19 - SZ received application for payment from Rapahel today.
57 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 1364.51 | 0000000095-1 | 2019-01-15 | SZ 12/9/19 - Chris will handle with Raphael9/5/19 - No work authorizations- Must go back to PM to obtain. Hopefully setting up a meeting with PM to discuss. DASNY PO needs to be figured out before we resubmit
58 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 4972.76 | 0000000104-3 | 2019-08-14 | SZ 12/9/19 emailed Chris today for explanation of invoice and if he would like to prosue with DASNY PMMay 2019 - remaining fees are for subcontratcor roofing work - we discussed issue with DASNY - the subcontractor (NAFEES) was notified: we converted their LS requisition in AE as required by DASNY and they paid $25k of $29 (approx) - remaining balance wil not be paid
59 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 5710.47 | 0000000119-1 | 2019-01-11 | SZ 12/9/19 Chris handling with Raphael9/2019 - Recently Chris prepared SCP for Client to get work authorizations and processing of payment- Need to reach back out to Ed Wagner to discuss. We ask Chris when we can set a meetiing.
60 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 2838.94 | 0000000127-2 | 2019-01-24 | SZ 12/9/2019 - Chris handling with Raphael9/5/19 - No work authorizations- Must go back to PM to obtain. Hopefully setting up a meeting with PM to discuss. DASNY PO needs to be figured out before we resubmit
61 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 2205.44 | 0000000129-1 | 2016-10-14 | SZ 11/16/19 DASNY reached out with a open pencil copy. Sent back to receive application of payment.
62 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 6971.7 | 0000000129-2 | 2019-01-11 | 9/5/19 - SZ Based on our meeting with Raphael. The SCP needs a cover letter and resubmitted to Raphael to obtain a work authorization. New submittal will be sent 9/11/19 when Raphael gets back from vacation.
63 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 25232.45 | 0000000133-1 | 2019-07-29 | 9/3/19 Application for payment sent to DASNY
64 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 9236.55 | 0000000136-1 | 2019-01-23 | Sz 12/9/19 - emailed Chris on PM contact infor. and see if he would like for me to contact DASNY PM9/5/19 - No work authorizations- Must go back to PM to obtain. Hopefully setting up a meeting with PM to discuss.
65 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 6237.2 | 0000000142-1 | 2019-01-15 | SZ 12/9/19 Email Peter Jackson from DASNY back in November. He is reviewing9/5/19 - SZ Based on our meeting with Raphael. The SCP needs to be revised and resubmitted to Raphael to obtain a work authorization. New submittal will be sent 9/11/19 when Raphael gets back from vacation.
66 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 2031.08 | 0000000147-1 | 2019-01-11 | SZ 12/9/19 Chris handling with Raphael9/5/19 work needs to be discussed with PM - trying to arrange a meeting.
67 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 22085.11 | 0000000158-1 | 2019-08-06 | SZ 12/9/19 - Chris HandlingSZ 10/22/19 per chris zanoni - dasny will be providing a lump sump work authorization - being processed now.
68 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 47474.26 | 0000000158-2 | 2019-08-13 | SZ 12/9/19 Chris HandlingSZ 10/22/19 per chris zanoni - dasny will be providing a lump sump work authorization - being processed now.
69 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 1993.87 | 0000000183-1 | 2019-01-30 | SZ 12/9/19 Chris Handling with Raphael9/5/19 - SZ Based on our meeting with Raphael. Raphael needs additional back up to obtain a work authorization. New submittal will be sent 9/11/19 when Raphael gets back from vacation.
70 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 16483.17 | 0000000185-3 | 2019-06-21 | 12/9/19 SZ emailed Chris asking for DASNY contact info. and if he would like for me to pursue.
71 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 16573.87 | 0000000185-3 | 2019-06-20 | 12/9/19 SZ emailed Chris asking for DASNY contact info. and if he would like for me to pursue.
72 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 24927.97 | 0000000208-1 | 2016-10-10 | 8/14/19 - SZ Application for Payment was submitted to DASNY 7/12/2019 - Payment should be made very shortly.
73 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 16144.57 | 0000000232-2 | 2018-10-02 | SZ 12/9/19 - emailed Bruce Suffern for an uodate. 9/5/2019 SZ for MB - application for payment wa doen for approx 13,400.00 remaining $ 40,000 still need authorization from PM Bruse Suffern. Matt will get further update in his 9/19 meeting.
74 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 30988.51 | 0000000286-2 | 2019-08-06 | SZ 12/9/19 rec'd AP 11/18/19
75 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 1801.75 | 0000330150-1 | 2016-10-25 | 9/5/19 No back up found - Need to discuss with Chris on next step
76 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 1526.25 | 000231-1DDSO | 2018-05-15 | SZ 12/9/19 we thought email was sent regarding allocation but cannot find it, David Peters doing the email to client now.11/18/19 Rec'd pencil copy however nees allocation of funds8/14/19 prepared spresheet and package for Chris mto take to DASNY - Inspection portion of work - Need work authorization / PO
77 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 3792.89 | 000CCNY201-2 | 2018-07-13 | SZ 21/9 rec'd WA today, submiited it to Bruce for the APSZ 12/4/19 Bruce sent a quick application to ALbany for WA, once rec'd he can do the AP.
78 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 2035.89 | 002-1.LIDDSO | 2018-06-08 | SZ 12/9/2019 - nothing happen with Raphael - I emailed Chris today to find out DASNY contact info and if he would like for me to pursue.9/5/19 SZ - Based on our meeting with Raphael. This project has a work authorization. Rapheal will prepare a Application for payment for it. Expecation of payment 2 months.
79 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 1019.47 | 00373-2BRONX | 2018-06-11 | SZ 12/9/19 Matt responded with clarificaton, waiting on DASNY to respon what changes are needed to get paid now.SZ 12/9/19 - Email chain sent to Chris & Matt asking that Samir's (DASNY) request for clarification be made for payment.SZ 12/9/19 - when i spoke with Mr. Brooks regarding, he stated it was paid. I will contact PM to follow up. 8/7/19 client reached out to LiRo for documents to close project and make final payment. Matt Brooks send requested documents (ACP15 & ACP 21) to Samir 8/8/19.
80 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 6827.19 | 00CCNY.177-1 | 2015-11-16 | SZ 12/9 per Bruce issue with invoice, need to have a conversation with him and find out status.
81 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 20264.67 | 00CCNY.201-1 | 2015-12-17 | SZ 12/4/19 Rec'd and submitted AP.
82 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 4189.47 | 00METRO231-1 | 2018-06-15 | SZ 12/9/19 contected Terrance ONeal architects he stated today he is in agreement with this invoice but it is very old, needs time to arrange payment expects by end of Jan 2020.
83 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 4675.25 | 0265.2.NYCHA | 2018-03-07
84 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 1469.45 | 0BMCC.116-01 | 2016-05-03 | 9/5/19 SZ - Based on our meeting with Raphael. This project has a work authorization. Rapheal will prepare a Application for payment for it. Expecation of payment 2 months.
85 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 2567.85 | 0SHEP015-023 | 2013-02-22 | SZ 12/9/19 - Bruce sent a quick application to Albany 12/5 for WA once rec'd he can do the AP.
86 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 6258.04 | 186-1.LIDDSO | 2016-11-02 | SZ 12/9/19 Nothing happen with raphael, I emailed Chris for DASNY contact info. and if he would like for me to pursue. 9/5/19 SZ - Based on our meeting with Raphael. This project has a work authorization. Rapheal will prepare a Application for payment for it. Expecation of payment 2 months.
87 | Env | Zanoni, Christopher | 11-22-0113 | [10 empty] | 4755.62 | JJCMONIT-001 | 2014-05-28 | SZ 12/2/19 rec'd application for payment and submitted 12/2/19
88 | Env | Zanoni, Christopher | 13-126-0277 |  | NYCHHC Fire Sprinkler System (Hurcules) | 4747 | 3097 | 0 | 0 | 2015-11-30 |  |  | 3097 |  |  |  |  | Y | 2018-05-09 | Y
89 | Env | Zanoni, Christopher | 13-126-0277 | [10 empty] | 3096.5 | 1 | 2015-10-22 | 9/10/2019 - At Risk Client - with Alison Ford and Legal.
90 | Env | Zanoni, Christopher | 14-092-0277.02 |  | HHC Harlem Hospital | 120537 | 112089 | 0 | 0 | 2019-09-30 |  |  | 9961 |  |  |  |  | N |  | N
91 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 757.82 | 0000000H-091 | 2016-11-15 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
92 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 1207.62 | 0000000H-104 | 2018-07-16 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
93 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 814.93 | 0000000H-105 | 2018-06-29 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
94 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 1412.47 | 0000000H-108 | 2018-06-26 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
95 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 911.97 | 0000000H-111 | 2018-06-15 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
96 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 1085.96 | 0000000H-112 | 2018-04-05 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
97 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 1047.5 | 0000000H-120 | 2018-11-13 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
98 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 729 | 0000000H-121 | 2018-11-13 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
99 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 891.23 | 0000000H-134 | 2019-04-08 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
100 | Env | Zanoni, Christopher | 14-092-0277.02 | [10 empty] | 1102.5 | 00000OFD-003 | 2019-06-26 | 12/11/19 - SZ at Gerards (HHC) suggestion I have asked Pauline Harding (HHC) the VP name that she advised had the invoices awaitng for his approval.
101 | Env | Zanoni, Christopher | 14-092-0277.03 |  | HHC Lincoln Hospital | 58968 | 58132 | 0 | 0 | 2019-09-30 |  |  | 4433 |  |  |  |  | N |  | N
102 | Env | Zanoni, Christopher | 14-092-0277.03 | [10 empty] | 3029.77 | 0000000L-016 | 2018-07-30 | 11/1 SZ email Mr. Smalls and Luis on open invoices again - asking for payment status. 9/26/19 Sz Luis heard back from Keith Smalls that this was before his time and it msut be expeditied by other. Noted Po was old GHX sysytem # 1-2221717144. Hopefully we can find someone to take responsiblitiy for this invoice.
103 | Env | Zanoni, Christopher | 14-092-0277.03 | [10 empty] | 1403.13 | 0000000L-021 | 2018-07-30 | 11/1 SZ email Mr. Smalls and Luis on open invoices again - asking for payment status.9/30/19 SZ Luis emailed me and advised invocie was processed this week.9/26/19 SZ - Luis received confirmation from Keith Smalls that when Alicia gets back from vacation 10/15 he will have her prepare the appropriate FPO documents for this invoice and must be signed by CFO COO and CEO for approval. Expectation of payment must likely November.
104 | Env | Zanoni, Christopher | 14-092-0277.04 |  | HHC Elmhurst Hospital | 119240 | 75210 | 1487 | 685 | 2019-09-24 | [7 empty] | N |  | N
105 | Env | Zanoni, Christopher | 14-092-0277.04 | 22 |  |  |  |  | 356
106 | Env | Zanoni, Christopher | 14-092-0277.04 | 23 |  |  |  |  | 329
107 | Env | Zanoni, Christopher | 14-092-0277.05 |  | HHC Gouverneur Hospital | 17310 | 16677 | 9035 | 9035 | 2019-11-30 | WIP goes back to 2017. HHC PM will not process the Supplemental until MEP group provides a C of O on a separate project. Change order is approved and its being held up from MPV group and summons. Request that HHC start to process the Supplemental while CO is obtained was rejected. |  | 5718 |  |  |  |  | N |  | Y
108 | Env | Zanoni, Christopher | 14-092-0277.05 | 2 |  |  |  |  | 9035
109 | Env | Zanoni, Christopher | 14-092-0277.05 | [10 empty] | 2509.33 | 0000000GV-06 | 2016-04-29 | 11/1/19 - SZ emailed Mr. Sanchez and Ahmad Jawwad on status of open invoices. 9/10/19 - Mr Sanchez confirmed today he approved invoice 9/4. Waiting on signature from CFO. Once obtained he will send a copy to let me know AP will be sending payment. His expectation is payment by end of month.
110 | Env | Zanoni, Christopher | 14-092-0277.05 | [10 empty] | 2221.45 | 0000000GV-07 | 2016-05-18 | 11/1/19 - SZ emailed Mr. Sanchez and Ahmad Jawwad on status of open invoices.9/10/19 - Mr Sanchez confirmed today he approved invoice 9/4. Waiting on signature from CFO. Once obtained he will send a copy to let me know AP will be sending payment. His expectation is payment by end of month.
111 | Env | Zanoni, Christopher | 14-092-0277.05 | [10 empty] | 987 | 000000GV-010 | 2019-03-26 | 11/1/19 - SZ emailed Mr. Sanchez and Ahmad Jawwad on status of open invoices.
112 | Env | Zanoni, Christopher | 14-092-0277.06 |  | HHC Queens Hospital Center | 62197 | 28947 | 0 | 0 | 2019-04-01 |  |  | 3738 |  |  |  |  | N |  | N
113 | Env | Zanoni, Christopher | 14-092-0277.06 | [10 empty] | 3738.25 | 0000000Q-016 | 2018-06-08 | 11/1 SZ - Mr. Wilson had to resend invoices again, Central office claimed they didnt have them. He is pushing to get them paid Wed 11/6/19
114 | Env | Zanoni, Christopher | 14-092-0277.07 |  | HHC Metropolitan Hospital | 10440 | 10440 | 0 | 0 | 2019-02-28 |  |  | 2791 |  |  |  |  | N |  | N
115 | Env | Zanoni, Christopher | 14-092-0277.07 | [10 empty] | 2790.84 | 0000000M-007 | 2015-04-29 | 11/1 - SZ followed up with Tamika Campbell and Amhad Jawwad for status
116 | Env | Zanoni, Christopher | 14-092-0277.08 |  | HHC Jacobi Hospital | 18990 | 59070 | 774 | 774 | 2019-09-13 | 9/18-/2019 -SZ per Bret - final report needs to be done once this is completed invocie will be done. Expectation for completion is Mid October. |  | 9446 |  |  |  |  | N |  | N
117 | Env | Zanoni, Christopher | 14-092-0277.08 | 3 |  |  |  |  | 774
118 | Env | Zanoni, Christopher | 14-092-0277.08 | [10 empty] | 6053.8 | 000000HO-024 | 2018-12-10 | 9/26/19 -SZ spoke with tamika today. This invoice Tamika stated she approved and being processed. She did mention it will take some time. Expectation at least 8 weeks
119 | Env | Zanoni, Christopher | 14-092-0277.08 | [10 empty] | 3391.77 | 000000HO-032 | 2018-12-13 | 11/1 - SZ followed up with Tamika Campbell and Amhad Jawwad for status
120 | Env | Zanoni, Christopher | 14-092-0277.09 |  | HHC 155 Water Construction and Maintenan | 109419 | 84279 | 0 | 0 | 2019-12-31 |  |  | 5635 |  |  |  |  | N |  | N
121 | Env | Zanoni, Christopher | 14-092-0277.09 | [10 empty] | 2589.4 | 000000HO-022 | 2019-02-22 | 11/1/19 SZ - followed up with Marcia Highley & Ahmad Jawwad for payment status.
122 | Env | Zanoni, Christopher | 14-092-0277.09 | [10 empty] | 3045.35 | 000000HO-023 | 2018-12-10 | 11/1/19 SZ - followed up with Marcia Highley & Ahmad Jawwad for payment status.
123 | Env | Zanoni, Christopher | 15-023-0113.03 |  | DASNY City University INSP. for Elevator | 2470 | 2470 | 0 | 0 | 2015-11-30 |  |  | 2470 |  |  |  |  | N |  | N
124 | Env | Zanoni, Christopher | 15-023-0113.03 | [10 empty] | 2469.83 | 00000INV-001 | 2015-07-30 | 11/26 SZ - I spoke with Mr. Casey and he stated upon investigating the acct. Ronaldo noted this would not be paid by DASNY, Ronaldo is no longer with company. Mr Casey is going to go back to DASNY and figure out how to get this paid. Need to give him 2 weeks before I follow-up.
125 | Env | Zanoni, Christopher | 16-056-0089 |  | YPS 2016 AHERA Re-Inspection Triennual | 278850 | 233928 | 713 | 713 | 2019-12-31 |  | 15166 | 18186 |  |  |  |  | N |  | N
126 | Env | Zanoni, Christopher | 16-056-0089 | 2 |  |  |  |  | 0
127 | Env | Zanoni, Christopher | 16-056-0089 | 17 |  |  |  |  | 0
128 | Env | Zanoni, Christopher | 16-056-0089 | 20 |  |  |  |  | 543
129 | Env | Zanoni, Christopher | 16-056-0089 | 21 |  |  |  |  | 0
130 | Env | Zanoni, Christopher | 16-056-0089 | 22 |  |  |  |  | 170
131 | Env | Zanoni, Christopher | 16-056-0089 | 23 |  |  |  |  | 0
132 | Env | Zanoni, Christopher | 16-056-0089 | [10 empty] | 620.5 | 00000000HP-1 | 2018-05-17 | SZ 12/5 - Per my conversation with Bella, she will look into getting money - may be at risk11/6/19 = SZ money was unencumbered, Chris advise Lee was trying to get these paid
133 | Env | Zanoni, Christopher | 16-056-0089 | [10 empty] | 666.25 | 0000000CHA-1 | 2019-07-02 | SZ 12/5 - Per my conversation with Bella, she will look into getting money - may be at risk11/6/19 = SZ money was unencumbered, Chris was advised to speak to Desmond Barnett - chief acct. for City of Yonkers
134 | Env | Zanoni, Christopher | 16-056-0089 | [10 empty] | 671 | 0000000RHS-2 | 2018-06-13 | SZ 12/5/19 - Per Bella money was encumbered but she found PO still be open, she will put thru an amendment for payment.11/6/19 = SZ money was unencumbered, Chris advise Lee was trying to get these paid
135 | Env | Zanoni, Christopher | 16-056-0089 | [10 empty] | 13899.95 | 000000PS25-3 | 2019-08-09 | SZ - 12/5/19 - Bella asked for invocies again, she is following up on payments.11/6/19 SZ - Chris advised Bela stated invoice was approved, pending proecessing
136 | Env | Zanoni, Christopher | 16-056-0089 | [10 empty] | 2328 | SAUNDERS22-1 | 2019-06-28 | SZ 12/5/19 this is new work and may be under new contract but per Bella I sent her the invocie she wants to see if they want to open PO to get this paid, acct. has crtitized to her invoices are submitted fater a long time of work rendered. Need to get status in a couple of weeks. 10/31/2019 - SZ CZ met with Yonkers 10/30. Found out PO's are issued thru City of Yonkers Porcurement. Chris to call Alex to get PO's and re-invoice for payment.
137 | Env | Zanoni, Christopher | 18-148-0282 |  | NYCSCA Prof Contingent Staffing 2018 | 4000000 | 447973 | 29247 | 8372 | 2019-11-30 | [7 empty] | N |  | N
138 | Env | Zanoni, Christopher | 18-148-0282 | 1 |  |  |  |  | 8372
139 | Env | Zanoni, Christopher | 18-317-0816 |  | Trust for Gover Isl - Bldg 20 Reno Insp | 4000 | 2990 | 0 | 0 | 2018-12-03 |  |  | 2990 |  |  |  |  | N |  | N
140 | Env | Zanoni, Christopher | 18-317-0816 | [10 empty] | 2990.25 | 1 | 2019-04-01 | SZ 12/2019 - I learned this was a LIRO job acct. - not to follow up on.SZ 11/12/19 - emailed CZ and Rosie for status and if they wanted me to follow up on payment.
141 | Env | Zanoni, Christopher | 18-324-0286.02 |  | NYPA DOWNSTATE Asbestos & Lead Mgmt | 155500 | 31308 | 39627 | 28284 | 2019-11-30 | [7 empty] | N |  | N
142 | Env | Zanoni, Christopher | 18-324-0286.02 | 2 |  |  |  |  | 1689 |  | Robert Soldano 12/10/2019: Abatement completed on 11/23/19. Waiting for NYPA to email contractor's cost as LiRo's invoice is a percentage of the abatement cost
143 | Env | Zanoni, Christopher | 18-324-0286.02 | 4 |  |  |  |  | 3465 |  | Robert Soldano 12/10/2019: Going to abatement. Abatement to occur siometime in 2020. Approximate length: 1 week
144 | Env | Zanoni, Christopher | 18-324-0286.02 | 6 |  |  |  |  | 18273 |  | Robert Soldano 12/10/2019: Invoiced NYPA for all abatement charges (Invoice #ESN-0619-4 on 12/6/2019)
145 | Env | Zanoni, Christopher | 18-324-0286.02 | 10 |  |  |  |  | 1847 |  | Robert Soldano 12/10/2019: Project is going to abatement. Unable to invoice. Abatement to occur sometime early spring of 2020. Approximate length of abatement: 3 days
146 | Env | Zanoni, Christopher | 18-324-0286.02 | 11 |  |  |  |  | 3011 |  | Robert Soldano 12/10/2019: Abatement completed on 12/6/19. Waiting on NYPA to email contractor's cost as LiRo invoice is based on a percentage of the abatement cost
147 | Env | Zanoni, Christopher | 19-017-0277.10 |  | HHC- Henry J. Carter Hospital Env Svcs | 3000 | 0 | 881 | 881 | [8 empty] | N |  | N
148 | Env | Zanoni, Christopher | 19-017-0277.10 | 1 |  |  |  |  | 881
149 | Env | Zanoni, Christopher | 19-017-0277.11 |  | HHC- Kings County Hospital Env Svcs | 62000 | 0 | 16972 | 5803 | [8 empty] | N |  | N
150 | Env | Zanoni, Christopher | 19-017-0277.11 | 1 |  |  |  |  | 5803
151 | Env | Zanoni, Christopher | 19-054-0816 |  | Trust for GI - Lead Paint Abate - 19 Hou | 51420 | 39130 | 0 | 0 | 2019-09-30 |  | 34482 | [5 empty] | N |  | N
152 | Env | Zanoni, Christopher | 19-100-0113 |  | DASNY-Heritage Arch Environ Eng | 6000 | 3040 | 141 | 71 | 2019-06-11 | [7 empty] | N |  | N
153 | Env | Zanoni, Christopher | 19-100-0113 | 1 |  |  |  |  | 71
154 | Env | Zanoni, Christopher | 19-136-0816 |  | Governors Is - Bldg 699 Abatement Monit | 14000 | 3901 | 0 | 0 | 2019-07-03 |  |  | 3901 |  |  |  |  | N |  | N
155 | Env | Zanoni, Christopher | 19-136-0816 | [10 empty] | 3901 | 0191360816-1 | 2019-08-09
156 | Env | Zanoni, Christopher | 19-232-0816 |  | Trust for GI- Bldg 108 Facade Inspection | 1200 | 0 | 2696 | 1074 | [8 empty] | N |  | N
157 | Env | Zanoni, Christopher | 19-232-0816 | 1 |  |  |  |  | 1074
158 | Env | Zanoni, Christopher | 19-233-0801 |  | Yonkers PS-Saunders HS Eng/Env Design | 42950 | 0 | 44974 | 7491 | [8 empty] | N |  | N
159 | Env | Zanoni, Christopher | 19-233-0801 | 1 |  |  |  |  | 1915
160 | Env | Zanoni, Christopher | 19-233-0801 | 2 |  |  |  |  | 5576
Total |  |  |  |  | 352205 | 536434 |  |  | 69304 | 492323