## PHR WITH WIP & AR
LiRo Financial Tracking Sheet:
Project Info |  | Baseline Data | [6 empty] | Previous Pay Period Data |  |  |  | Current Pay Period Data | [5 empty] | Projected Financial Outcome
Project # | Project Name | Project Manager Name | (A) BU Min. Multiplier | (B) Project (Target) Multiplier | (C) Contract Value ($) | (D) Direct Labor Budget ($) (D = C/B) | (E) Planning Direct Labor Rate/Hr. ($) | (F) Planned Hours (Hrs) (F=D/E) | Previous Est. Comp. Date | Previous Estimated Hours to Complete | (G) Previous Total Hours Required (Prev. N) | (H) Total Hours Expended To Date (Hrs) | (I) Direct Labor Cost to Date ($) | (J) Current Average Direct Labor Rate ($/Hr) ( J = I/H) | (K) Current Estimated Hours to Complete (Hrs) (K = G-H) | (L) Estimated Cost to Complete in Dollars ($) (L = K*J) | (M) Current Project Level Estimated Completion Date | (N) Total Projected Hours (N = H+K) | (O) Percentage Completed (Hours) (O = H/N) | (P) Total Direct Labor to Completion ($) (P = N*J) | (Q) Projected Multiplier (Q = C/P) | (R) Direct Labor Variance ($) R=C(1/Min(A,B)-1/Q) | (Z) Last Pay Period Hours Charged