## PHR WITH WIP & AR
|  | LiRo Financial Tracking Sheet: | [5 empty] | CM | [12 empty] | 2019-12-12
Project Info |  | Baseline Data | [6 empty] | Previous Pay Period Data |  |  |  | Current Pay Period Data | [5 empty] | Projected Financial Outcome
Project # | Project Name | Project Manager Name | (A) BU Min. Multiplier | (B) Project (Target) Multiplier | (C) Contract Value ($) | (D) Direct Labor Budget ($) (D = C/B) | (E) Planning Direct Labor Rate/Hr. ($) | (F) Planned Hours (Hrs) (F=D/E) | Previous Est. Comp. Date | Previous Estimated Hours to Complete | (G) Previous Total Hours Required (Prev. N) | (H) Total Hours Expended To Date (Hrs) | (I) Direct Labor Cost to Date ($) | (J) Current Average Direct Labor Rate ($/Hr) ( J = I/H) | (K) Current Estimated Hours to Complete (Hrs) (K = G-H) | (L) Estimated Cost to Complete in Dollars ($) (L = K*J) | (M) Current Project Level Estimated Completion Date | (N) Total Projected Hours (N = H+K) | (O) Percentage Completed (Hours) (O = H/N) | (P) Total Direct Labor to Completion ($) (P = N*J) | (Q) Projected Multiplier (Q = C/P) | (R) Direct Labor Variance ($) R=C(1/Min(A,B)-1/Q) | (Z) Last Pay Period Hours Charged
07-31-200B | NYCDOS Marine Transfer St LIRO-URS 50-50 | Blond, Lawrence | 2.04 | 0 | 7064982.5 | 0 | 0 | 0 | 2019-09-30 | 4.07 | 56158.69 | 56425.62 | 3091682.32 | 54.79 | -266.93 | -16000.84 | 2019-09-30 | 56158.69 | 100.48 | 3075681.25 | 2.3 | 375535.61 | 0
09-06-100B | PLA ANAYLSES FOR VARIOUS PROJECTS ASNEED | Hurley, Joseph | 2.04 | 2.57 | 89127.64 | 34680.02 | 40 | 867 |  | 594.2 | 719.2 | 125 | 11110.04 | 88.88 | 594.2 | 48058.58 |  | 719.2 | 17.38 | 59168.62 | 1.51 | -15478.93 | 28
10-58-515 | CUNY - Baruch College - Field Bld | Gaspari, James | 2.04 | 2.5 | 9897934 | 3959173.6 | 61 | 64907.85 | 2010-07-30 | 34541.24 | 71339.29 | 39195.74 | 2795666.58 | 71.33 | 32143.55 | 1621216.24 | 2010-07-30 | 71339.29 | 54.94 | 4417042.6 | 2.24 | 429088.28 | 283
11-68-0533 | Hudson River Park Trust Pier 40 Construc | Franco, Frank | 2.04 | 1.96 | 6363852.47 | 3246863.48 | 42.69 | 76049.43 | 2019-03-30 | 19580.88 | 71715.74 | 55282.75 | 2663240.1 | 48.17 | 16432.99 | 401406.39 | 2019-03-30 | 71715.74 | 77.09 | 3063713.56 | 2.08 | 155458.56 | 0
11-82-0265 | NYCDDC - MCC Theater Fit Outs | Franco, Frank | 2.04 | 1.35 | 1458138 | 1080102.22 | 48.73 | 22167.2 | 2019-04-01 | 3099.71 | 34189.21 | 31089.5 | 1546489.91 | 49.74 | 3099.71 | 145228.21 | 2019-04-01 | 34189.21 | 90.93 | 1691718 | 0.86 | -610194.6 | 3.5
12-147-0278.04 | NYCHA CCTV | Nazzaro, Dennis | 2.04 | 2 | 2696540.23 | 1348270.17 | 39.17 | 34422.46 | 2018-12-31 | 14173.83 | 34466.05 | 20975.5 | 834663.7 | 39.79 | 13490.55 | 515454.71 | 2018-12-31 | 34466.05 | 60.86 | 1350118.39 | 2 | -15945.03 | 0
12-147-0278.11 | NYCHA Exterior Lighting | Mo, Thomas | 2.04 | 2.1 | 1685020 | 802390.47 | 42.7 | 18791.6 | 2016-01-31 | 1008.19 | 20503.78 | 19590 | 835845.68 | 42.67 | 913.78 | 36640.35 | 2016-01-31 | 20503.78 | 95.54 | 872486.06 | 1.93 | -45930.36 | 0
13-011-0376 | SUCF New Medical and Research Bldg CM | Burke, Stephen | 2.04 | 1.85 | 9599999 | 5189188.64 | 59.89 | 86638.93 | 2019-06-01 | 41749.56 | 86638.95 | 82637.3 | 5427929.46 | 65.68 | 4001.65 | -244079.72 | 2019-06-01 | 86638.95 | 95.38 | 5183849.68 | 1.85 | 5196.58 | 245.5
13-017-0265 | NYCDDC PLA Study & Implementation Projec | Bendetti, Michael | 2.04 | 2.15 | 5000 | 2325.58 | 81.89 | 28.4 | 2013-03-31 | 8.4 | 28.4 | 20 | 1637.56 | 81.88 | 8.4 | 687.78 | 2013-03-31 | 28.4 | 70.42 | 2325.34 | 2.15 | 125.4 | 0
13-017-0265.04 | DDC- New Westchester Square Library | Hurley, Joseph | 2.04 | 2.2 | 18630.48 | 8468.4 | 84.54 | 100.17 | 2017-08-31 | 60.17 | 100.17 | 40 | 3381.4 | 84.54 | 60.17 | 5086.47 | 2017-08-31 | 100.17 | 39.93 | 8467.87 | 2.2 | 664.19 | 0
13-045-0248 | NCDPW Nassau Family & Matrimonial Court | Bendetti, Michael | 2.04 | 2.25 | 50000 | 22222.22 | 62.73 | 354.25 | 2013-07-03 | 0.03 | 701.03 | 701 | 43975.3 | 62.73 | 0.03 | 1.88 | 2013-07-03 | 701.03 | 100 | 43977.18 | 1.14 | -19349.85 | 0
13-050-0265 | NYCDDC Reno and Rehab West 59th CM | Bendetti, Michael | 2.04 | 1.95 | 5635778 | 2890142.56 | 64.96 | 44491.11 | 2016-04-01 | 32634.02 | 44491.77 | 57998.8 | 3483811.33 | 60.07 | -13507.03 | -637636.87 | 2016-04-01 | 44491.77 | 130.36 | 2846174.57 | 1.98 | -2681471.43 | 358
13-064-0113 | DASNY Term On-Call CM | Franco, Frank | 2.04 | 2.15 | 5174507.34 | 2412206.96 | 45.61 | 52891.86 | 2017-12-31 | 19645.51 | 58990.76 | 46019.5 | 2178584.5 | 47.34 | 12971.26 | 510995.08 | 2017-12-31 | 58990.76 | 78.01 | 2689652.67 | 1.92 | -365548.07 | 18
13-068-0113.09 | DASNY CCTV & LAC Analysis at NYCHA Locat | Mo, Thomas | 2.04 | 2.15 | 235063.5 | 109331.86 | 65.05 | 1680.73 | 2016-02-03 | 943.6 | 1680.73 | 1129.5 | 59883.5 | 53.02 | 551.23 | 49446.18 | 2016-02-03 | 1680.73 | 67.2 | 109329.68 | 2.15 | 5895.35 | 0
13-068-0113.10 | DASNY Conjunction Design & Security Svcs | Mo, Thomas | 2.04 | 2.15 | 1210135.8 | 562853.87 | 49.45 | 11383.32 | 2016-06-30 | 5436.13 | 12056.32 | 8592 | 428233.31 | 49.84 | 3464.32 | 164814.96 | 2016-06-30 | 12056.32 | 71.27 | 593224.2 | 2.04 | -103617.29 | 0
13-115-0090 | CUNY Macaulay Honors College Roof Top Re | Gaspari, James | 2.04 | 2 | 685359.94 | 342679.97 | 79.98 | 4284.38 | 2014-08-29 | 1020.91 | 4284.25 | 3292 | 262131.69 | 79.63 | 992.25 | 80050.64 | 2014-08-29 | 4284.25 | 76.84 | 342182.32 | 2 | 0 | 0
13-124-0113 | DASNY Energy Performance Design and CM | Ribeiro, Raymond | 2.04 | 2.27 | 828338 | 365104.05 | 41.5 | 8798.68 | 2020-03-31 | 3498.52 | 8411.17 | 5240.25 | 264106.43 | 50.4 | 3170.92 | 185562.09 | 2020-03-31 | 8411.17 | 62.3 | 449668.51 | 1.84 | -53202.66 | 70.5
13-142-0275 | NYCEDC On Call Facilities Management Con | Bradley, Daniel | 2.04 | 2.1 | 861014.32 | 410006.82 | 53.96 | 7597.86 | 2014-08-29 | 0.04 | 8021.63 | 8363 | 453651.43 | 54.25 | -341.37 | -18664.56 | 2014-08-29 | 8021.63 | 104.26 | 434986.85 | 1.98 | -13446.05 | 0.5
14-012-0282.Q | NYCSCA Emergency Program 2013 Queens | Radafshar, Bijan | 2.04 | 0 | 0 | 0 | 0 | 0 | 2016-01-16 | 0 | 0 | 135 | 5681.87 | 42.09 | -135 | -5681.87 | 2016-01-16 | 0 | 0 | 0 | 0 | -5681.87 | 0
14-058-0286.06 | NYPA Cumberland HPS Boiler Replacement | Ribeiro, Raymond | 2.04 | 2.2 | 181094 | 82315.46 | 74.66 | 1102.47 | 2018-01-01 | 218.11 | 1536.61 | 1318.5 | 97837.71 | 74.2 | 218.11 | 16437.37 | 2018-01-01 | 1536.61 | 85.81 | 114275.07 | 1.58 | -25518.68 | 0
14-058-0286.07 | NYPA Lincoln Hospital - HVAC Upgrade | Ribeiro, Raymond | 2.04 | 2.59 | 1476098 | 570076.79 | 44.78 | 12731.79 | 2018-12-31 | 6310.13 | 13371.49 | 7130.93 | 375909.69 | 52.72 | 6240.56 | 388994.03 | 2018-12-31 | 13371.49 | 53.33 | 764903.71 | 1.93 | -14687.97 | 99.5
14-058-0286.08 | NYPA CUNY Boiler Repair Services-ASRC | Ribeiro, Raymond | 2.04 | 2.2 | 106400 | 48363.63 | 49.96 | 968.08 | 2018-01-01 | 890.08 | 968.08 | 78 | 6389.38 | 81.92 | 890.08 | 41665.39 | 2018-01-01 | 968.08 | 8.06 | 48054.77 | 2.21 | 4124.39 | 0
14-058-0286.09 | NYPA Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.2 | 50000 | 22727.27 | 40 | 568.18 | 2018-06-01 | 550.68 | 568.18 | 17.5 | -25388.4 | -1450.77 | 550.68 | 22027.2 | 2018-06-01 | 568.18 | 3.08 | 22727.2 | 2.2 | 1782.53 | 0
14-058-0286.10 | NYPA Lincoln Hospital - Cooling Tower | Ribeiro, Raymond | 2.04 | 2.2 | 619920 | 281781.81 | 71.41 | 3945.8 | 2018-01-01 | 566.95 | 3936.95 | 3370 | 241310.74 | 71.61 | 566.95 | 40365.09 | 2018-01-01 | 3936.95 | 85.6 | 281675.83 | 2.2 | 22100.53 | 3
14-058-0286.11 | NYPA Grand Ave. Bus Depot Gen Upgrade | Ribeiro, Raymond | 2.04 | 2.4 | 220000 | 91515.15 | 40 | 2287.87 |  | 473.19 | 1204.69 | 731.5 | 45246.62 | 61.85 | 473.19 | 32285.82 |  | 1204.69 | 60.72 | 77854.9 | 2.83 | 29934.58 | 0
14-058-0286.12 | NYPA Fresh Pond Bus Depot-HVAC Upgrade | Ribeiro, Raymond | 2.04 | 2.51 | 1230197 | 489376.7 | 43.04 | 11371.42 | 2018-01-01 | 6658.53 | 11224.71 | 4605 | 230715.76 | 50.1 | 6619.71 | 268008.88 | 2018-01-01 | 11224.71 | 41.03 | 498724.65 | 2.47 | 102951.99 | 10.25
14-058-0286.13 | NYPA CUNY Boiler Repairs- Queens College | Ribeiro, Raymond | 2.04 | 2.2 | 114500 | 52045.45 | 82.19 | 633.2 | 2018-01-01 | 278.04 | 847.04 | 569 | 46541.92 | 81.8 | 278.04 | 21765.47 | 2018-01-01 | 847.04 | 67.18 | 68307.39 | 1.68 | -12296.16 | 0
14-058-0286.14 | NYPA Bronx Community College Utility | Gaspari, James | 2.04 | 2.27 | 2483769.89 | 1096048.51 | 42.48 | 25802.94 | 2022-07-01 | 17888.75 | 24401 | 6512.25 | 347261.84 | 53.32 | 17888.75 | 1201074.77 | 2022-07-01 | 24401 | 26.69 | 1548336.62 | 1.6 | -334750.01 | 121.75
14-058-0286.17 | NYPA CUNY Boiler Repairs- Hunter College | Ribeiro, Raymond | 2.04 | 2.1 | 13200 | 6285.71 | 84.24 | 74.62 | 2018-12-31 | 27.13 | 79.13 | 52 | 4130.98 | 79.44 | 27.13 | 2155.26 | 2018-12-31 | 79.13 | 65.71 | 6286.24 | 2.1 | 184.87 | 0
14-058-0286.18 | NYPA CUNY Boiler Repairs- Voohies Hall C | Ribeiro, Raymond | 2.04 | 2.1 | 14000 | 6666.67 | 84.24 | 79.14 | 2018-12-31 | 45.14 | 79.14 | 34 | 2864.16 | 84.24 | 45.14 | 3802.59 | 2018-12-31 | 79.14 | 42.96 | 6666.75 | 2.1 | 196.08 | 0
14-058-0286.19 | NYPA CUNY Boiler Repairs- Bklyn College | Ribeiro, Raymond | 2.04 | 2.1 | 51020 | 24295.24 | 46.78 | 519.4 | 2018-12-31 | 477.6 | 513.6 | 36 | 2833.04 | 78.7 | 477.6 | 21461.72 | 2018-12-31 | 513.6 | 7.01 | 24294.76 | 2.1 | 714.57 | 0
14-058-0286.21 | NYPA CUNY Bronx CC Piping Upgrade | White, William | 2.04 | 2.1 | 196658 | 93646.67 | 73.22 | 1278.98 | 2019-08-01 | 252.94 | 1278.98 | 2031.5 | 131743.81 | 64.85 | -752.52 | -48801.31 | 2019-08-01 | 1278.98 | 158.84 | 82942.51 | 2.37 | 13422.92 | 19
14-059-0113 | DASNY Hostos Community College WR | Ribeiro, Raymond | 2.04 | 2.14 | 235817 | 109998.29 | 64.87 | 1695.66 | 2019-11-15 | 608.24 | 1955.51 | 1397.75 | 88423.36 | 63.26 | 557.76 | 41795.21 | 2019-11-15 | 1955.51 | 71.48 | 130218.56 | 1.81 | -14625.62 | 21.5
14-059-0113.01 | DASNY JV Hostos CC Variable Freq. Drives | Barbosa, Marco | 2.04 | 2.1 | 346746 | 165117.14 | 56.48 | 2923.25 | 2015-10-31 | 615.87 | 2921.87 | 2306 | 140110.93 | 60.76 | 615.87 | 26088.66 | 2015-10-31 | 2921.87 | 78.92 | 166199.6 | 2.09 | 3782.19 | 0
14-059-0113.02 | DASNY York College BMS Upgrade | Ribeiro, Raymond | 2.04 | 2.54 | 402878.54 | 158613.6 | 48.24 | 3288.27 | 2018-12-30 | 566.82 | 3242.82 | 2676 | 130491.28 | 48.76 | 566.82 | 30064.7 | 2018-12-30 | 3242.82 | 82.52 | 160555.97 | 2.51 | 36956.24 | 0
14-088-0290.01 | NYSPRHP Upper Plaza Term Contract 2014 | Franco, Frank | 2.04 | 2.12 | 96342.13 | 45444.4 | 40 | 1136.11 | 2018-12-30 | 1136.11 | 1136.11 | 0 | 0 | 0 | 1136.11 | 45444.4 | 2018-12-30 | 1136.11 | 0 | 45444.4 | 2.12 | 1782.13 | 0
14-088-0290.14 | NYSPRHP RCSP - Electrical Upgrade | Franco, Frank | 2.04 | 2.1 | 130520 | 62152.38 | 55.42 | 1121.46 | 2019-09-01 | 537.48 | 1130.46 | 2037.25 | 128149.55 | 62.9 | -906.79 | -64007.14 | 2019-09-01 | 1130.46 | 180.21 | 64142.41 | 2.03 | -188.47 | 74
14-088-0290.15 | NYSPRHP E. River State Park Classroom Bl | Franco, Frank | 2.04 | 2.1 | 30000 | 14285.71 | 69.98 | 204.14 | 2019-09-01 | 43.26 | 43.26 | 0 | -79.45 | 0 | 43.26 | 3027.33 | 2019-09-01 | 43.26 | 0 | 3027.33 | 9.91 | 11678.64 | 0
14-094-0275 | NYCEDC Box Street Newtown Barge Parks CM | Bradley, Daniel | 2.04 | 2.4 | 2600190.8 | 1083412.83 | 62.06 | 17457.41 | 2019-12-31 | 5142.28 | 22661.88 | 18886.25 | 1027616.8 | 54.41 | 3775.63 | 251120.63 | 2019-12-31 | 22661.88 | 83.34 | 1278737.41 | 2.03 | -68617.24 | 23
14-121-0090 | CUNY Brooklyn College Ingersoll Hall Ext | Gaspari, James | 2.04 | 2.15 | 3389527.87 | 1576524.59 | 70.27 | 22435.75 | 2017-07-13 | 2603.75 | 19900.63 | 17359 | 1270743.76 | 73.2 | 2541.63 | 149728.97 | 2017-07-13 | 19900.63 | 87.23 | 1420472.7 | 2.39 | 241987.46 | 133
15-016-0276 | FDNY CM Services | Blond, Lawrence | 2.04 | 2.1 | 7564504 | 3602144.85 | 51.84 | 69486.31 | 2018-08-01 | 8406.65 | 70866.48 | 62848.75 | 3290620.32 | 52.36 | 8017.73 | 384039.66 | 2018-08-01 | 70866.48 | 88.69 | 3674659.99 | 2.06 | 33319.19 | 0
15-034-0113 | DASNY OMH South Beach Psychiatric | Barbosa, Marco | 2.04 | 2.1 | 2404751.89 | 1145119.95 | 41.04 | 27902.6 | 2015-10-31 | 17348.68 | 25998.04 | 8650.6 | 446418.57 | 51.61 | 17347.44 | 1244133.78 | 2015-10-31 | 25998.04 | 33.27 | 1690552.36 | 1.42 | -510355 | 119.5
15-035-0278 | NYCHA Ingersoll Houses | Nazzaro, Dennis | 2.04 | 2 | 3078197 | 1539098.5 | 40 | 38477.47 | 2017-03-11 | 38477.47 | 38477.47 | 0 | 0 | 0 | 38477.47 | 1539098.8 | 2017-03-11 | 38477.47 | 0 | 1539098.8 | 2 | 0 | 0
15-036-0278 | NYCHA Whitman Houses | Choudhury, Faisal | 2.04 | 2.1 | 2428126 | 1156250.47 | 49.62 | 23302.21 | 2017-03-11 | 8205.72 | 34315.47 | 26109.75 | 1296496.32 | 49.66 | 8205.72 | 405043.33 | 2017-03-11 | 34315.47 | 76.09 | 1701539.75 | 1.43 | -383217.4 | 0
15-049-0265 | NYCDDC Hurricane Sandy-Affected Resident | Pavlakos, Giannoula | 2.05 | 3.75 | 49976066 | 13326950.93 | 54.07 | 246475.88 | 2020-04-28 | 188697.56 | 256038.06 | 193366.65 | 10106803.54 | 52.27 | 62671.41 | 3783088.59 | 2020-04-28 | 256038.06 | 75.52 | 13889892.44 | 3.6 | 4125019.54 | 563.5
15-049-0265.01 | NYCDDC Hurricane Sandy-Affected | Pavlakos, Giannoula | 2.04 | 3 | 398217 | 132739 | 57.05 | 2326.74 | 2017-08-31 | 732.76 | 11476.17 | 24509.2 | 1175678.41 | 47.97 | -13033.03 | -646378.69 | 2017-08-31 | 11476.17 | 213.57 | 529299.72 | 0.75 | -967273.4 | 16.25
15-092-0282.Q | NYCSCA Emergency Program 2015 Queens | Radafshar, Bijan | 2.04 | 2.4 | 29970.34 | 12487.64 | 46.72 | 267.29 | 2017-07-23 | 0 | 267.29 | 394.5 | 18431.24 | 46.72 | -127.21 | -5943.32 | 2017-07-23 | 267.29 | 147.59 | 12487.93 | 2.4 | 2203.7 | 0
15-116-0278 | NYCHA CM Sandy Recovery at Red Hook E&W | Nazzaro, Dennis | 2.04 | 2 | 12714236 | 6357118.04 | 46.83 | 135745.09 | 2018-03-30 | 94359.85 | 140906.4 | 47865.75 | 2291431.34 | 47.87 | 93040.65 | 4256711.68 | 2018-03-30 | 140906.4 | 33.97 | 6548143.01 | 1.94 | -193025.94 | 721
15-121-0278.04 | NYCHA Roofing Restoration/Rooftop Repair | Wong, David | 2.04 | 2.2 | 72354 | 32888.19 | 76.26 | 431.26 | 2020-03-01 | 6 | 437.26 | 554.5 | 42745.2 | 77.09 | -117.24 | -9617.72 | 2020-03-01 | 437.26 | 126.81 | 33127.49 | 2.18 | -76.31 | 0
15-121-0278.05 | NYCHA Melrose Houses Roofing Restoration | Wong, David | 2.04 | 2.2 | 931896.79 | 423589.45 | 45.35 | 9340.62 | 2020-07-10 | 4049.63 | 10849.2 | 7514.8 | 352875.15 | 46.96 | 3334.4 | 171935.05 | 2020-07-10 | 10849.2 | 69.27 | 524810.18 | 1.78 | -68575.99 | 335.5
15-121-0278.06 | NYCHA Webster Houses Roofing Restoration | Wong, David | 2.04 | 2.2 | 634580.08 | 288445.49 | 40 | 7211.14 | 2020-07-10 | 3531.56 | 7996.56 | 4465 | 209511.58 | 46.92 | 3531.56 | 173402.99 | 2020-07-10 | 7996.56 | 55.84 | 382914.57 | 1.66 | -72451.71 | 224
15-121-0278.07 | NYCHA Eastchester Houses Roofing Restor | Wong, David | 2.04 | 2.2 | 1079068.02 | 490485.47 | 40 | 12262.13 | 2020-07-10 | 7764.9 | 12953.9 | 5189 | 235175.44 | 45.32 | 7764.9 | 353007.17 | 2020-07-10 | 12953.9 | 40.06 | 588182.62 | 1.83 | -59814.81 | 368
16-018-0271 | NYCDOS On-Call Services Reno & Rehab | Caggiano, Anthony | 2.04 | 2.1 | 5275045.6 | 2511926.48 | 53.13 | 47283.09 | 2019-01-06 | 37235.93 | 69683.07 | 34133.25 | 1918615.01 | 56.21 | 35549.82 | 1934418.37 | 2019-01-06 | 69683.07 | 48.98 | 3853033.41 | 1.37 | -1117310.33 | 105
16-024-0090.01 | CUNY On Call Lehman College Labs Rounds | Fitzpatrick, Lawrence | 2.04 | 2.3 | 634432 | 275840 | 46.04 | 5991.55 | 2019-05-31 | 346.55 | 6137.33 | 6827 | 315481.99 | 46.21 | -689.67 | -30752.19 | 2019-05-31 | 6137.33 | 111.24 | 284729.8 | 2.23 | 26399.65 | 3
16-025-1256.10 | HTFC APMS MCM - Construction Management | Massa, Joseph | 2.04 | 2.38 | 6782871.48 | 2849946 | 40 | 71248.65 | 2020-03-31 | 11096.79 | 61774.54 | 50677.75 | 2907866.18 | 57.38 | 11096.79 | 595220.11 | 2020-03-31 | 61774.54 | 82.04 | 3503086.09 | 1.94 | -184920.15 | 376
16-052-0290.02 | NYSDPR Penn Fountain Park | Franco, Frank | 2.04 | 2.2 | 127051.27 | 57750.58 | 74.15 | 778.83 | 2019-12-31 | 0.03 | 848.53 | 848.5 | 62689.43 | 73.88 | 0.03 | 2.22 | 2019-12-31 | 848.53 | 100 | 62691.65 | 2.03 | -306.8 | 0
16-069-0278.01 | NYCHA CM Svcs Lincoln Houses Minor Elect | Nazzaro, Dennis | 2.04 | 2.2 | 451510.59 | 205232.09 | 40.85 | 5024.06 | 2018-12-30 | 4883.85 | 5024.06 | 267.5 | 19034.77 | 71.16 | 4756.56 | 186321.15 | 2018-12-30 | 5024.06 | 5.32 | 205355.92 | 2.2 | 15981.1 | 0
16-069-0278.02 | NYCHA Playgrounds CM Svcs | Nazzaro, Dennis | 2.04 | 2.1 | 49219.6 | 23437.9 | 40 | 585.94 |  | 371.44 | 585.94 | 214.5 | 7605.39 | 35.46 | 371.44 | 13415.04 |  | 585.94 | 36.61 | 21020.43 | 2.34 | 3124.53 | 12
16-076-0270.02 | NYCPR Tiffany St. Pier Special Inspec | Reo, Jennifer | 2.04 | 2.1 | 620 | 295.24 | 75.51 | 3.91 | 2019-01-18 | 1.91 | 3.91 | 7 | 547.97 | 78.28 | -3.09 | -241.89 | 2019-01-18 | 3.91 | 179.03 | 306.08 | 2.03 | -1.5 | 0
16-076-0270.04 | NYCPR Brookville Park Spec Insp-Tennis | Reo, Jennifer | 2.04 | 2.1 | 620 | 295.24 | 76.69 | 3.85 | 2019-01-18 | 0 | 3.85 | 27 | 2069.04 | 76.63 | -23.15 | -1774.01 | 2019-01-18 | 3.85 | 701.3 | 295.03 | 2.1 | 8.68 | 0
16-076-0270.11 | NYCPR - NYS Pavillion - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 21600 | 10285.71 | 76.93 | 133.7 | 2019-11-12 | 131.95 | 134.2 | 2.25 | 174.18 | 77.41 | 131.95 | 10214.69 | 2019-11-12 | 134.2 | 1.68 | 10388.87 | 2.08 | 203.62 | 0
16-076-0270.12 | NYCPR - Shore Rd Fld Hs - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 13500 | 6428.57 | 76.93 | 83.56 | 2019-11-12 | 49.31 | 87.81 | 38.5 | 3027.24 | 78.63 | 49.31 | 3877.23 | 2019-11-12 | 87.81 | 43.84 | 6904.47 | 1.96 | -270.11 | 2.5
16-076-0270.13 | NYCPR - West Plgd CS - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 18000 | 8571.43 | 76.93 | 111.42 | 2019-11-12 | 103.17 | 111.42 | 8.25 | 640.12 | 77.59 | 103.17 | 8004.99 | 2019-11-12 | 111.42 | 7.4 | 8645.11 | 2.08 | 169.68 | 0
16-076-0270.14 | NYCPR - Brownsville Rec Ctr - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 12500 | 5952.38 | 76.93 | 77.37 | 2019-11-12 | 67.37 | 78.37 | 11 | 861.49 | 78.32 | 67.37 | 5276.23 | 2019-11-12 | 78.37 | 14.04 | 6137.72 | 2.04 | 0 | 0.25
16-076-0270.15 | NYCPR - Marine Pk Plgd - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 9000 | 4285.71 | 76.93 | 55.71 | 2019-11-12 | 21.21 | 62.46 | 41.25 | 3239.88 | 78.54 | 21.21 | 1665.89 | 2019-11-12 | 62.46 | 66.04 | 4905.77 | 1.83 | -506.27 | 0
16-076-0270.16 | NYCPR - Canarsie CS - Spec Insp | Reo, Jennifer | 2.04 | 2.1 | 13500 | 6428.57 | 76.93 | 83.56 | 2019-11-12 | 77.31 | 83.81 | 6.5 | 500.58 | 77.01 | 77.31 | 5953.82 | 2019-11-12 | 83.81 | 7.76 | 6454.4 | 2.09 | 158.32 | 0
16-076-0270.17 | NYCPR - Reconstruct Bloomingdale Plgd | Choudhury, Faisal | 2.04 | 2.1 | 317400 | 151142.86 | 44.1 | 3427.28 | 2020-01-15 | 1108.27 | 3804.02 | 2695.75 | 132053.24 | 48.99 | 1108.27 | 54289.39 | 2020-01-15 | 3804.02 | 70.87 | 186342.62 | 1.7 | -31117.65 | 0
16-076-0270.18 | NYCPR - Reconstruct Garrison Plgd | Choudhury, Faisal | 2.04 | 2.1 | 446200 | 212476.19 | 46 | 4619.05 | 2020-01-15 | 2787 | 5130 | 2343 | 107928.4 | 46.06 | 2787 | 128380.9 | 2020-01-15 | 5130 | 45.67 | 236309.29 | 1.89 | -17359.17 | 74
16-076-0270.19 | NYCPR - CM Svcs St Mary's Greenstreets | Choudhury, Faisal | 2.04 | 2.1 | 134132 | 63872.38 | 51.96 | 1229.26 | 2019-11-01 | 719.89 | 1742.89 | 1023 | 47920.79 | 46.84 | 719.89 | 33722.09 | 2019-11-01 | 1742.89 | 58.7 | 81642.88 | 1.64 | -16036.82 | 13
16-080-0270.01 | NYCPR Reconstruct New Comfort Stations | Massa, Joseph | 2.04 | 2.05 | 2695321 | 1314790.72 | 55.01 | 23901.76 | 2019-01-18 | 1902.34 | 23293.59 | 22403.25 | 1245560.07 | 55.6 | 890.34 | 59927.4 | 2019-01-18 | 23293.59 | 96.18 | 1305487.49 | 2.06 | 16370.2 | 128
16-080-0270.13 | NYCPR Lincoln Terrace Park Special Insp | Reo, Jennifer | 2.04 | 2.1 | 25200 | 12000 | 76.15 | 157.58 | 2019-11-16 | 138.58 | 159.58 | 21 | 1632.92 | 77.76 | 138.58 | 10775.72 | 2019-11-16 | 159.58 | 13.16 | 12408.64 | 2.03 | -60.85 | 0
16-080-0270.14 | NYCPR CM Svcs for St. Mary's Ballfields | Choudhury, Faisal | 2.04 | 2.1 | 358000 | 170476.19 | 40.68 | 4190.66 | 2020-04-01 | 2843.71 | 4789.21 | 1945.5 | 95470.02 | 49.07 | 2843.71 | 139547.19 | 2020-04-01 | 4789.21 | 40.62 | 235017.21 | 1.52 | -60036.12 | 64
16-080-0270.15 | NYCPR Recon of Elizabeth H. Berger Plaza | Choudhury, Faisal | 2.04 | 2.2 | 325600 | 148000 | 40 | 3700 |  | 2846 | 3700 | 854 | 35868 | 42 | 2846 | 119532 |  | 3700 | 23.08 | 155400 | 2.1 | 4560.22 | 66
16-342-0275.01 | EDC Estimating Svcs Willoughby Square Pk | Frysztacki, Edward | 2.04 | 2.3 | 19000 | 8260.87 | 68.97 | 119.77 |  | 6.78 | 124.78 | 118 | 8247.4 | 69.89 | 6.78 | 473.88 |  | 124.78 | 94.57 | 8721.28 | 2.18 | 598.13 | 0
16-379-0275 | NYCEDC NYPD JFK Site A - Closeout | Reo, Jennifer | 2.04 | 2 | 223104 | 111552 | 52.31 | 2132.4 | 2019-06-30 | 293.02 | 2134.52 | 1841.5 | 109070.77 | 59.23 | 293.02 | 16303.14 | 2019-06-30 | 2134.52 | 86.27 | 125373.91 | 1.78 | -14056.14 | 14
17-040-0286.01 | NYPA VNB Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 5120613 | 1862041.09 | 110.07 | 16916.88 | 2018-07-01 | 16359.31 | 17793.29 | 6071 | 488080.43 | 80.4 | 11722.29 | 1181304.34 | 2018-07-01 | 17793.29 | 34.12 | 1669384.77 | 3.07 | 480113.29 | 10
17-040-0286.02 | NYPA RFK Queens Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 1804774 | 656281.45 | 42.11 | 15584.93 | 2018-07-01 | 14814.77 | 21293.52 | 6799.75 | 375567.63 | 55.23 | 14493.77 | 654796.28 | 2018-07-01 | 21293.52 | 31.93 | 1030363.88 | 1.75 | -161460.37 | 0
17-040-0286.03 | NYPA RFK Harlem Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 1175397 | 427417.09 | 44.51 | 9602.72 | 2018-07-01 | 9091.77 | 10910.27 | 5733.75 | 315051.01 | 54.95 | 5176.52 | 158743.25 | 2018-07-01 | 10910.27 | 52.55 | 473794.24 | 2.48 | -129280.71 | 0
17-040-0286.04 | NYPA RFK Bronx Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 645525 | 234736.36 | 41.24 | 5691.96 | 2018-07-01 | 5105.52 | 5692.02 | 5524.25 | 306125.78 | 55.41 | 167.77 | -72545.49 | 2018-07-01 | 5692.02 | 97.05 | 233580.29 | 2.76 | -199509.95 | 0
17-040-0286.06 | NYPA TNB Bridge Lighting | Ribeiro, Raymond | 2.04 | 2.75 | 2287790 | 831923.64 | 57.69 | 14420.59 | 2018-07-01 | 13981.29 | 14242.79 | 4861.75 | 305255.82 | 62.79 | 9381.04 | 591166.89 | 2018-07-01 | 14242.79 | 34.13 | 896422.69 | 2.55 | -64504.21 | 0
17-078-1387 | Breaking Ground Prince George Rehab | Ribeiro, Raymond | 2.04 | 1 | 856268 | 856268 | 57.19 | 14972.34 | 2017-12-31 | 4645.23 | 11408.73 | 6763.5 | 387788.48 | 57.34 | 4645.23 | 266336.45 | 2017-12-31 | 11408.73 | 59.28 | 654124.9 | 1.31 | 202628.31 | 0
17-078-1387.02 | Breaking Ground-Prince George Sidewalk | Ribeiro, Raymond | 2.04 | 2.5 | 60000 | 24000 | 40 | 600 |  | 23 | 600 | 577 | 34981.49 | 60.63 | 23 | 1394.41 |  | 600 | 96.17 | 36375.9 | 1.65 | -6951.87 | 0
17-078-1387.03 | Breaking Ground-Prince George Fire Pump | Ribeiro, Raymond | 2.04 | 2.1 | 15000 | 7142.86 | 40 | 178.57 |  | 115.57 | 178.57 | 63 | 5715.36 | 90.72 | 115.57 | 10484.51 |  | 178.57 | 35.28 | 16199.87 | 0.93 | -8776.09 | 0
17-080-0282 | SCA Mentor Program-Administration | Fotopoulos, Georgia | 2.04 | 1.73 | 8893688.16 | 5140860.21 | 45.29 | 113509.83 | 2019-06-02 | 74287.79 | 114217.99 | 39930.2 | 1755122.45 | 43.95 | 74287.79 | 3265301.98 | 2019-06-02 | 114217.99 | 34.96 | 5020424.34 | 1.77 | 116177.63 | 482
17-080-0282.M | SCA Mentor Program-MANHATTAN | Fotopoulos, Georgia | 2.04 | 1.73 | 989078.58 | 571721.72 | 40.24 | 14207.09 | 2019-06-02 | 8417.26 | 15359.1 | 7422 | 303817.99 | 40.93 | 7937.1 | 323496.81 | 2019-06-02 | 15359.1 | 48.32 | 627314.82 | 1.58 | -55892.58 | 279
17-080-0282.X | SCA Mentor Program-BRONX | Fotopoulos, Georgia | 2.04 | 1.73 | 1197536.82 | 692217.82 | 41.67 | 16613.87 | 2019-06-02 | 9440.44 | 15551.19 | 7243 | 310952.8 | 42.93 | 8308.19 | 346319.56 | 2019-06-02 | 15551.19 | 46.58 | 657272.33 | 1.82 | 34963.73 | 188
17-082-0290 | OPRHP-Jones Beach State Park | Franco, Frank | 2.04 | 2.07 | 967137 | 467215.94 | 63.67 | 7338.09 | 2018-09-30 | 192.84 | 7383.09 | 7190.25 | 459832.29 | 63.95 | 192.84 | 12332.54 | 2018-09-30 | 7383.09 | 97.39 | 472164.85 | 2.05 | 2312.62 | 0
17-082-0290.01 | OPRHP Jones Beach Basketball Courts | Franco, Frank | 2.04 | 2.07 | 235134 | 113591.3 | 105.2 | 1079.81 | 2019-10-01 | 1463.52 | 2686.52 | 1223 | 63327.46 | 51.78 | 1463.52 | 73981.88 | 2019-10-01 | 2686.52 | 45.52 | 137309.35 | 1.71 | -21722.29 | 2
17-082-0290.02 | OPRHP - Jones Beach Central Mall | Franco, Frank | 2.04 | 2.07 | 257010 | 124159.42 | 40 | 3103.99 |  | 0.03 | 305.78 | 305.75 | 15912.66 | 52.04 | 0.03 | 1.56 |  | 305.78 | 99.99 | 15914.22 | 16.15 | 110071.36 | 0
17-086-0265 | NYCDDC Disaster Recovery: On-Call | Aidikoff, Brant | 2.04 | 2 | 200000 | 100000 | 61.18 | 1634.64 | 2019-06-08 | 716.15 | 848.65 | 132.5 | 12852.98 | 97 | 716.15 | 52603.91 | 2019-06-08 | 848.65 | 15.61 | 65456.89 | 3.06 | 34425.18 | 0
17-095-0407.01 | Town of Babylon Gilgo Potable Water | Ribeiro, Raymond | 2.04 | 2.5 | 21225 | 8490 | 79.07 | 107.37 | 2019-09-01 | 220.73 | 264.42 | 194.6 | 16182.43 | 83.16 | 69.82 | -3085.77 | 2019-09-01 | 264.42 | 73.6 | 13096.67 | 1.62 | -2708.28 | 0
17-095-0407.02 | Town of Babylon America Venice Bridges | Ribeiro, Raymond | 2.04 | 2.5 | 274862.2 | 109944.88 | 90.92 | 1209.29 | 2019-09-01 | 1134.1 | 2242.31 | 1268.7 | 109068.66 | 85.97 | 973.61 | 50515.2 | 2019-09-01 | 2242.31 | 56.58 | 159583.86 | 1.72 | -13831.26 | 39
17-095-0407.03 | Town of Babylon Captree Emerg Generators | Ribeiro, Raymond | 2.04 | 2.5 | 40791.38 | 16316.55 | 85.37 | 191.12 | 2019-09-01 | 204.16 | 444.36 | 240.2 | 20898.73 | 87.01 | 204.16 | 11180.72 | 2019-09-01 | 444.36 | 54.06 | 32079.44 | 1.27 | -12014.08 | 0
17-095-0407.04 | Town of Babylon Carls River Watershed | Ribeiro, Raymond | 2.04 | 2.5 | 258104 | 103241.6 | 46.02 | 2243.42 | 2019-09-01 | 1653.52 | 1930.22 | 276.7 | 23787.03 | 85.97 | 1653.52 | 81686.57 | 2019-09-01 | 1930.22 | 14.34 | 105473.6 | 2.45 | 20931.56 | 0
17-095-0407.05 | Town of Babylon Amityville Waterfront | Ribeiro, Raymond | 2.04 | 2.5 | 118781.09 | 47512.44 | 82.55 | 575.55 | 2019-09-01 | 492.76 | 1057.61 | 601.8 | 50104.25 | 83.26 | 455.81 | 24451.92 | 2019-09-01 | 1057.61 | 56.9 | 74556.17 | 1.59 | -9614.47 | 2
17-095-0407.06 | Town of Babylon-Babylon Coastal Outfall | Ribeiro, Raymond | 2.04 | 2.5 | 94325 | 37730 | 49.27 | 765.85 | 2019-09-01 | 422.79 | 624.83 | 224 | 16643 | 74.3 | 400.83 | 17044.56 | 2019-09-01 | 624.83 | 35.85 | 33687.56 | 2.8 | 12574.16 | 0
17-095-0407.07 | Town of Babylon Captree Road Stabilizati | Ribeiro, Raymond | 2.04 | 2.5 | 80737 | 32294.8 | 50.54 | 639.05 | 2019-09-01 | 543.01 | 653.11 | 115.45 | 9826.48 | 85.11 | 537.66 | 23675.94 | 2019-09-01 | 653.11 | 17.68 | 33502.41 | 2.41 | 6083.08 | 0
17-095-0407.08 | Town of Babylon Oakbeach Stabilization | Ribeiro, Raymond | 2.04 | 2.5 | 80700 | 32280 | 54.35 | 593.92 | 2019-09-01 | 495.9 | 605.35 | 109.45 | 9459.99 | 86.43 | 495.9 | 24177.05 | 2019-09-01 | 605.35 | 18.08 | 33637.04 | 2.4 | 5908.02 | 0
17-095-0407.09 | Town of Babylon Araca Stabilization | Ribeiro, Raymond | 2.04 | 2.5 | 80700 | 32280 | 51.32 | 629 | 2019-09-01 | 480.95 | 678.21 | 214.45 | 18864.49 | 87.97 | 463.76 | 36500.99 | 2019-09-01 | 678.21 | 31.62 | 55365.48 | 1.46 | -15761.15 | 0
17-095-0407.10 | Town of Babylon Little East Neck Road | Ribeiro, Raymond | 2.04 | 2.5 | 23767.48 | 9506.99 | 53.36 | 178.18 | 2019-09-01 | 254.09 | 367.88 | 126.8 | 10891.77 | 85.9 | 241.08 | 20143.54 | 2019-09-01 | 367.88 | 34.47 | 31035.3 | 0.77 | -19386.45 | 0
17-120-0113.01 | DASNY Security Enhancement Project NYCHA | Mo, Thomas | 2.04 | 2.1 | 789344 | 375878.11 | 47.19 | 7965.03 | 2018-06-30 | 1855.6 | 5549.6 | 3694 | 177887.05 | 48.16 | 1855.6 | 85069.79 | 2018-06-30 | 5549.6 | 66.56 | 262956.84 | 3 | 123881.31 | 0
17-120-0113.02 | DASNY Site Lighting Replacement Project | Mo, Thomas | 2.04 | 2.1 | 519206.91 | 247241.38 | 52.12 | 4743.52 | 2018-12-31 | 1616.17 | 5117.42 | 3501.25 | 183865.08 | 52.51 | 1616.17 | 79255.23 | 2018-12-31 | 5117.42 | 68.42 | 263120.3 | 1.97 | -8664.23 | 0
17-120-0113.03 | DASNY Security Projects at Various NYCHA | Mo, Thomas | 2.04 | 2.1 | 44474.33 | 21178.22 | 40 | 529.46 | 2018-12-31 | 529.46 | 529.46 | 0 | 0 | 0 | 529.46 | 21178.4 | 2018-12-31 | 529.46 | 0 | 21178.4 | 2.1 | 622.92 | 0
17-120-0113.05 | DASNY BMCC - Feeder Project | Franco, Frank | 2.04 | 2.1 | 170811.68 | 81338.9 | 82.34 | 987.84 | 2019-11-09 | 540.84 | 996.84 | 456 | 37547.04 | 82.34 | 540.84 | 44532.77 | 2019-11-09 | 996.84 | 45.74 | 82079.81 | 2.08 | 1610.22 | 0
17-120-0113.08 | DASNY BMCC - Generator Project | Franco, Frank | 2.04 | 2.1 | 293956.47 | 139979.27 | 81.34 | 1720.92 | 2019-11-09 | 288.98 | 2047.48 | 1758.5 | 146439.02 | 83.27 | 288.98 | 24064.8 | 2019-11-09 | 2047.48 | 85.89 | 170503.82 | 1.72 | -26808.62 | 13
17-120-0113.09 | DASNY BMCC - GYM AHU | Franco, Frank | 2.04 | 2.1 | 172538.05 | 82160.98 | 81.87 | 1003.55 | 2019-11-09 | 307.2 | 1072.2 | 765 | 62722.74 | 81.99 | 307.2 | 25187.48 | 2019-11-09 | 1072.2 | 71.35 | 87910.22 | 1.96 | -3452.14 | 0
17-120-0113.10 | DASNY Minnewaska State Park Phase 1 | Franco, Frank | 2.04 | 2.1 | 1804604 | 859335.24 | 59.62 | 14413.54 | 2019-11-09 | 9432.04 | 14413.54 | 4981.5 | 300269.77 | 60.28 | 9432.04 | 568534.89 | 2019-11-09 | 14413.54 | 34.56 | 868804.66 | 2.08 | 17011.73 | 131.5
17-120-0113.12 | DASNY- NYCHA Quality of Life | Mo, Thomas | 2.04 | 2.1 | 1522554 | 725025.7 | 61.12 | 11861.63 | 2019-04-30 | 6543.05 | 13770.68 | 7349.75 | 398456.61 | 54.21 | 6420.93 | 404419.41 | 2019-04-30 | 13770.68 | 53.37 | 802876.02 | 1.9 | -56047.6 | 192
17-120-0113.13 | DASNY Fahnestock State Park | Franco, Frank | 2.04 | 2.1 | 265000 | 126190.48 | 33.74 | 3739.58 | 2019-11-09 | 3600.72 | 3757.58 | 1451.5 | 85747.57 | 59.08 | 2306.08 | 100614.29 | 2019-11-09 | 3757.58 | 38.63 | 186361.88 | 1.42 | -56087.92 | 204.75
17-120-0113.14 | DASNY - BMCC Plaza Restoration | Franco, Frank | 2.04 | 2.1 | 530300 | 252523.81 | 65.45 | 3858.27 | 2019-12-01 | 1205.72 | 4805.72 | 3600 | 239585.8 | 66.55 | 1205.72 | 80242.61 | 2019-12-01 | 4805.72 | 74.91 | 319828.4 | 1.66 | -59506.85 | 91
17-120-0113.15 | DASNY - Harriman State Park | Franco, Frank | 2.04 | 1.92 | 302680 | 157542.86 | 54.41 | 2895.51 | 2020-01-01 | 1378.47 | 2249.77 | 871.3 | 58065.17 | 66.64 | 1378.47 | 63855.08 | 2020-01-01 | 2249.77 | 38.73 | 121920.25 | 2.48 | 39509.06 | 12
17-120-0113.17 | DASNY - York College | Franco, Frank | 2.04 | 2.1 | 417845 | 198973.81 | 40 | 4974.35 |  | 4540.35 | 4974.35 | 434 | 35654.99 | 82.15 | 4540.35 | 373009.5 |  | 4974.35 | 8.72 | 408664.49 | 1.02 | -204825.98 | 56
17-120-0113.20 | DASNY- York College BMS Controls | Ribeiro, Raymond | 2.15 | 2.1 | 497233 | 236777.62 | 40 | 5919.44 |  | 5297.44 | 5919.44 | 622 | 40904.51 | 65.76 | 5297.44 | 348374.91 |  | 5919.44 | 10.51 | 389279.42 | 1.28 | -151685.66 | 85
17-122-0275 | NYCEDC Andrew Haswell Green Pk - PH 2 | Bradley, Daniel | 2.04 | 2.1 | 2187728 | 1041775.24 | 42.31 | 24622.73 | 2021-07-01 | 23591.32 | 24785.57 | 1194.25 | 85490.67 | 71.59 | 23591.32 | 972798.08 | 2021-07-01 | 24785.57 | 4.82 | 1058288.75 | 2.07 | 14032.19 | 0
17-126-0376 | SUCF Downstate Medical-Upgrade UHB Elec | Burke, Stephen | 2.04 | 2 | 1875079.5 | 937539.75 | 101.75 | 9214.04 | 2025-05-01 | 8560.66 | 9224.04 | 2256 | 159645.82 | 70.76 | 6968.04 | 648130.32 | 2025-05-01 | 9224.04 | 24.46 | 807776.14 | 2.32 | 128546.89 | 68
17-132-0275 | NYCEDC Bushwick Inlet Demolition | Reo, Jennifer | 2.04 | 2.08 | 1166557 | 560844.71 | 47.04 | 11922.1 | 2019-09-01 | 5164 | 12293 | 7129 | 386851.03 | 54.26 | 5164 | 269490.87 | 2019-09-01 | 12293 | 57.99 | 656341.92 | 1.78 | -83862.68 | 18
17-134-0136 | Erie County Med Emerg Dept Modernization | Kreuzer, Robert | 2.08 | 2.1 | 1058282.59 | 503944.1 | 45.16 | 11159.36 | 2019-03-01 | 3947.48 | 11683.48 | 7773 | 356815.42 | 45.9 | 3910.48 | 180470.64 | 2019-03-01 | 11683.48 | 66.53 | 537286.02 | 1.97 | -18916.22 | 158
17-141-0267 | NYCDEP Constr of Right of Way Green Infr | Ribeiro, Raymond | 2.04 | 2.05 | 1915764.72 | 936355.26 | 57.09 | 16401.84 | 2020-06-01 | 1825.34 | 10490.34 | 8665 | 556901.4 | 64.27 | 1825.34 | 121324.97 | 2020-06-01 | 10490.34 | 82.6 | 678226.33 | 2.82 | 260755.36 | 72
17-141-0267.02 | NYCDEP Water Meter Installation at NYCHA | Ribeiro, Raymond | 2.04 | 2.1 | 1028883 | 489944.29 | 50.99 | 9609.31 | 2020-03-31 | 5817.98 | 19461.48 | 13643.5 | 712825.04 | 52.25 | 5817.98 | 300811.72 | 2020-03-31 | 19461.48 | 70.11 | 1013636.7 | 1.02 | -506315.19 | 61
17-141-0267.03 | NYCDEP - Amawalk Dam Ogee Spillway | Ribeiro, Raymond | 2.04 | 2.1 | 432802.63 | 206096.49 | 71.46 | 2884.15 |  | 2675.09 | 2729.09 | 54 | 4425.89 | 81.96 | 2675.09 | 188252.32 |  | 2729.09 | 1.98 | 192678.21 | 2.25 | 19480.62 | 0
17-141-0267.04 | NYCDEP- WQMON-ENT2 Construction of Above | Ribeiro, Raymond | 2.04 | 2.06 | 327288.16 | 158553.59 | 40 | 3963.85 |  | 2855.85 | 3963.85 | 1108 | 55101.04 | 49.73 | 2855.85 | 131182.31 |  | 3963.85 | 27.95 | 186283.35 | 1.76 | -25940.12 | 74
17-141-0267.05 | NYCDEP- 26W-13G Elec and Special Inspect | Ribeiro, Raymond | 2.07 | 2.12 | 26898.73 | 12667.54 | 40 | 316.69 |  | 116.44 | 316.69 | 200.25 | 10826.08 | 54.06 | 116.44 | 7875.72 |  | 316.69 | 63.23 | 18701.8 | 1.44 | -5832.72 | 6.5
17-146-0265.01 | NYCDDC Crossroads Renovations-CJCREN | Bendetti, Michael | 2.04 | 2.25 | 6498560 | 2888248.89 | 73.36 | 39370.67 | 2020-12-31 | 7175.45 | 27969.95 | 20794.5 | 1419664.88 | 68.27 | 7175.45 | 489904.22 | 2020-12-31 | 27969.95 | 74.35 | 1909569.04 | 3.4 | 1276286.68 | 226.5
17-146-0265.02 | NYCDDC - Horizon Renovations | Bendetti, Michael | 2.04 | 2.15 | 5844976 | 2718593.49 | 64.34 | 42253.55 | 2020-12-31 | 10169.94 | 27187.69 | 17017.75 | 1056291.38 | 62.07 | 10169.94 | 631247.97 | 2020-12-31 | 27187.69 | 62.59 | 1687539.37 | 3.46 | 1175884.89 | 149
17-146-0265.03 | NYCDDC Recon Harper St Asphalt Plant | Reo, Jennifer | 2.04 | 1.69 | 2154040 | 1277020 | 59.55 | 21444.62 | 2022-09-15 | 21205.73 | 21469.98 | 264.25 | 20617.86 | 78.02 | 21205.73 | 1264348.71 | 2022-09-15 | 21469.98 | 1.23 | 1284966.58 | 1.68 | -8201.78 | 6
17-153-0113 | DASNY-at-Risk Tower 3 Renov Buffalo S | Kreuzer, Robert | 2.04 | 2.35 | 769397.59 | 327403.23 | 49.24 | 6648.96 | 2019-10-09 | 992.78 | 7663.81 | 6764.5 | 338402.24 | 50.03 | 899.31 | 43350.98 | 2019-10-09 | 7663.81 | 88.27 | 381753.23 | 2.02 | -4017.78 | 77
17-159-0865 | NYU Winthrop Hosp - Program Management | Franco, Frank | 2.04 | 2.05 | 1104778 | 538916.08 | 59.37 | 9077.61 | 2018-07-01 | 6129.57 | 9743.66 | 4076 | 292591.31 | 71.78 | 5667.66 | 297950.36 | 2018-07-01 | 9743.66 | 41.83 | 590541.69 | 1.87 | -49190.68 | 0
17-169-0112 | Diocese Of Rockville Centre - On Call | Pfister, Frank | 2.04 | 2.37 | 277949.9 | 117340.07 | 53.31 | 2201.06 | 2018-11-14 | 246.79 | 2259.11 | 2149.75 | 114670.21 | 53.34 | 109.36 | 6272.02 | 2018-11-14 | 2259.11 | 95.16 | 120942.22 | 2.3 | 15296.76 | 0
18-007-0248.01 | NCDPW On-Call Building Design | Bendetti, Michael | 2.44 | 2.1 | 52828.6 | 25156.48 | 63.8 | 394.33 | 2018-07-03 | 69.63 | 511.85 | 465 | 29040.71 | 62.45 | 46.85 | 2727.57 | 2018-07-03 | 511.85 | 90.85 | 31768.27 | 1.66 | -6607.03 | 0
18-024-0132 | ECHDC Canalside Interpretive Structures | Kreuzer, Robert | 2.04 | 2 | 738515.56 | 369257.78 | 41.44 | 8910.96 | 2019-08-01 | 7727.25 | 9521 | 1793.75 | 112445.74 | 62.69 | 7727.25 | 389251.87 | 2019-08-01 | 9521 | 18.84 | 501697.61 | 1.47 | -132680.19 | 44
18-138-0271 | DSNY BKLYN Community District 3 Facility | Choudhury, Faisal | 2.04 | 2.1 | 7410613 | 3528863.34 | 80.43 | 43876.64 | 2024-05-31 | 39290.52 | 44626.97 | 5404 | 337524.1 | 62.46 | 39222.97 | 2241971.36 | 2024-05-31 | 44626.97 | 12.11 | 2579495.47 | 2.87 | 1054493.14 | 279
18-213-0283 | NYIT PM Svcs Campus Commons & Wisser Lib | Burke, Stephen | 2.04 | 2.2 | 2425000 | 1102272.73 | 42.99 | 25638.74 | 2022-07-15 | 25123.74 | 25705.74 | 693 | 71789.57 | 103.59 | 25012.74 | 1037449.55 | 2022-07-15 | 25705.74 | 2.7 | 1109239.12 | 2.19 | 68012.05 | 0
18-272-0282.Q | NYCSCA Emergency Program 2018 Queens | Radafshar, Bijan | 2.04 | 1.16 | 305318.96 | 263206 | 38.19 | 6892.88 | 2021-09-01 | 4851.88 | 6892.88 | 2219 | 89575.84 | 40.37 | 4673.88 | 186924.26 | 2021-09-01 | 6892.88 | 32.19 | 276500.11 | 1.1 | -20044.65 | 8
18-281-0136 | ECMC-Owners's Rep-Multiple Construction | Kreuzer, Robert | 2.04 | 2 | 327000 | 163500 | 44.05 | 3711.73 | 2018-12-31 | 234.29 | 2821.04 | 2586.75 | 117309.06 | 45.35 | 234.29 | 10033.65 | 2018-12-31 | 2821.04 | 91.69 | 127342.7 | 2.57 | 36044.53 | 64
18-339-0380 | SUNY Stony Brook-OR Svcs W. Apts- Bldg K | Burke, Stephen | 2.04 | 2.1 | 789891 | 376138.57 | 42.47 | 8857.44 | 2021-08-03 | 6743.62 | 9047.37 | 2303.75 | 158320.75 | 68.72 | 6743.62 | 454658.44 | 2021-08-03 | 9047.37 | 25.46 | 612979.19 | 1.29 | -224932.87 | 125
18-360-0315.02 | WSP - E. River State Park Classroom Bldg | Franco, Frank | 2.27 | 2.2 | 56000 | 25454.54 | 40 | 636.36 | 2019-04-01 | 619.71 | 785.21 | 165.5 | 11661.27 | 70.46 | 619.71 | 43640.2 | 2019-04-01 | 785.21 | 21.08 | 55301.47 | 1.01 | -28901.29 | 0
18-360-0315.03 | WSP - RCSP Shoreline | Franco, Frank | 2.04 | 2.2 | 204707 | 93048.64 | 40 | 2326.22 |  | 0.01 | 385.01 | 385 | 23974.31 | 62.27 | 0.01 | 0.62 |  | 385.01 | 100 | 23974.93 | 8.54 | 76376.19 | 0
18-360-0315.04 | WSP - RCSP Upper Plaza | Franco, Frank | 2.04 | 2.2 | 204707 | 93048.64 | 40 | 2326.22 |  | 180.09 | 1391.09 | 1211 | 78866.01 | 65.12 | 180.09 | 11728.31 |  | 1391.09 | 87.05 | 90594.32 | 2.26 | 9768.25 | 0
19-009-0270 | NYCP&R CM Svcs for Battery Carousel Supp | Choudhury, Faisal | 2.04 | 1 | 24870 | 24870 | 59.92 | 415.05 | 2019-01-01 | 397.05 | 415.05 | 18 | 1091.44 | 60.64 | 397.05 | 24075.35 | 2019-01-01 | 415.05 | 4.34 | 25166.79 | 0.99 | -251.21 | 0
19-013-0031 | BPCA - CM Svcs for Community Ctr Leak Re | Franco, Frank | 2.04 | 2.1 | 352800 | 168000 | 40 | 4200 | 2020-03-15 | 3226.93 | 4293.93 | 1067 | 69702.05 | 65.33 | 3226.93 | 203499.93 | 2020-03-15 | 4293.93 | 24.85 | 273201.97 | 1.29 | -99915.99 | 42
19-015-0376.01 | SUNY Downstate Med Ctr Isolation/Oper Rm | Burke, Stephen | 2.04 | 2.1 | 763400 | 363523.81 | 40 | 9088.09 |  | 8857.1 | 9114.1 | 257 | 23972.44 | 93.28 | 8857.1 | 377445 |  | 9114.1 | 2.82 | 401417.44 | 1.9 | -26955.42 | 17
19-015-0376.02 | SUNY Purchase HVAC Reno-Dance Bldg 29 | Burke, Stephen | 2.04 | 2.1 | 203000 | 96666.67 | 103.57 | 933.35 |  | 77.35 | 933.35 | 856 | 54136.17 | 63.24 | 77.35 | 4891.86 |  | 933.35 | 91.71 | 59028.03 | 3.44 | 40498.18 | 6
19-015-0376.03 | SUNY Demo 34th St Park Garage 141057-01 | Burke, Stephen | 2.04 | 2.1 | 275814 | 131340 | 40 | 3283.5 |  | 3157 | 3334 | 177 | 18323.44 | 103.52 | 3157 | 138340.34 |  | 3334 | 5.31 | 156663.78 | 1.76 | -21445.63 | 2
19-018-0276.01 | FDNY-EMS20 - Multi Component Renovation | Blum, Walter | 2.04 | 2.1 | 354856 | 168979.05 | 63.93 | 2643.19 | 2020-01-31 | 749.83 | 3528.83 | 2779 | 183100.8 | 65.89 | 749.83 | 49404.27 | 2020-01-31 | 3528.83 | 78.75 | 232505.08 | 1.53 | -57983.01 | 97
19-018-0276.02 | FDNY - EC-24 Female Firefighter Toilet U | Reo, Jennifer | 2.04 | 2.1 | 357390 | 170185.71 | 56.77 | 2997.81 | 2020-02-28 | 897.36 | 3642.86 | 2745.5 | 156709.21 | 57.08 | 897.36 | 51220.03 | 2020-02-28 | 3642.86 | 75.37 | 207929.24 | 1.72 | -32593.71 | 97
19-018-0276.03 | FDNY- EC253 Multi-Component Reno COMM#2 | Reo, Jennifer | 2.04 | 2.1 | 355700.52 | 169381.2 | 71.68 | 2363.02 | 2020-01-31 | 799.7 | 2641.45 | 1841.75 | 111714.55 | 60.66 | 799.7 | 48507.19 | 2020-01-31 | 2641.45 | 69.72 | 160221.75 | 2.22 | 14137.54 | 1.5
19-018-0276.04 | FDNY FEMA Fiber Project-FINO-Proof of Co | Blum, Walter | 2.15 | 2.1 | 11349 | 5404.29 | 40 | 135.11 |  | 135.11 | 135.11 | 0 | 0 | 0 | 135.11 | 5404.4 |  | 135.11 | 0 | 5404.4 | 2.1 | 0 | 0
19-030-0821 | Roswell 2019 Term Constr Agreement | Kreuzer, Robert | 2.04 | 2 | 469379.81 | 234689.96 | 40.93 | 5733.33 |  | 1055.45 | 5720.31 | 5618.25 | 250307.3 | 44.55 | 102.06 | 7452.63 |  | 5720.31 | 98.22 | 257759.93 | 1.82 | -58928.12 | 218.75
19-034-0269 | DHS - CM Svcs Reno Proj at Shelter Site | Franco, Frank | 2.05 | 2.1 | 2227621.2 | 1060772 | 55.89 | 18980.01 | 2022-11-12 | 25858.09 | 27152.84 | 1294.75 | 80236.94 | 61.97 | 25858.09 | 1517493.73 | 2022-11-12 | 27152.84 | 4.77 | 1597730.68 | 1.39 | -257459.22 | 89.5
19-065-0113.01 | DASNY - FIT 30% Cost Estimate | Frysztacki, Edward | 2.04 | 1.9 | 60000 | 31578.95 | 65.59 | 481.46 |  | 258.47 | 756.97 | 498.5 | 32998.77 | 66.2 | 258.47 | 17109.71 |  | 756.97 | 65.85 | 50108.48 | 1.2 | -18421.05 | 0
19-072-0347.01 | RIOC - Motorgate Garage | Franco, Frank | 2.04 | 2.1 | 1327600 | 632190.48 | 40 | 15804.76 |  | 14558.01 | 15804.76 | 1246.75 | 86903.99 | 69.7 | 14558.01 | 1014757.64 |  | 15804.76 | 7.89 | 1101661.63 | 1.21 | -446405.77 | 36
19-072-0347.02 | RIOC - Bridges | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 13.22 | 494.47 | 481.25 | 33488.18 | 69.59 | 13.22 | 919.92 |  | 494.47 | 97.33 | 34408.11 | 0 | -33488.18 | 0
19-072-0347.03 | RIOC - Lighthouse Restoration | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 110.5 | 6083.46 | 55.05 | -110.5 | -6083.46 |  | 0 | 0 | 0 | 0 | -6083.46 | 9
19-072-0347.04 | RIOC - Seawall Railings | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 80.25 | 6025.94 | 75.09 | -80.25 | -6025.94 |  | 0 | 0 | 0 | 0 | -6025.94 | 0
19-072-0347.05 | RIOC - Youth Center | Franco, Frank | 2.04 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 955.5 | 58080.17 | 60.79 | -955.5 | -58080.17 |  | 0 | 0 | 0 | 0 | -58080.17 | 56
19-072-0347.06 | RIOC - Water Distribution | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 740.06 | 773.81 | 33.75 | 2185.83 | 64.77 | 740.06 | 45048 |  | 773.81 | 4.36 | 47233.83 | 1.38 | -15294.75 | 0
19-072-0347.07 | RIOC - AVAC Upgrades | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 646.56 | 773.81 | 127.25 | 9095.38 | 71.48 | 646.56 | 34788.22 |  | 773.81 | 16.44 | 43883.6 | 1.48 | -12111.04 | 22
19-072-0347.08 | RIOC - Sportspark Renovation | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 476.19 | 773.81 | 304.25 | 22238.49 | 73.09 | 469.56 | 18562.99 |  | 773.81 | 39.32 | 40801.49 | 1.59 | -8924.01 | 10
19-072-0347.09 | RIOC - Octagon Field | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 247.62 | 773.81 | 635.75 | 45004.13 | 70.79 | 138.06 | 3041.85 |  | 773.81 | 82.16 | 48045.97 | 1.35 | -16217.74 | 0
19-072-0347.10 | RIOC - Small Pox Hospital | Franco, Frank | 2.04 | 2.1 | 65000 | 30952.38 | 40 | 773.81 |  | 688.06 | 773.81 | 85.75 | 6414.11 | 74.8 | 688.06 | 34895.5 |  | 773.81 | 11.08 | 41309.61 | 1.57 | -9506.31 | 4
19-072-0347.11 | RIOC - Octogon Field Phase 2 | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 429.25 | 812.5 | 383.25 | 27062.67 | 70.61 | 429.25 | 32253.05 |  | 812.5 | 47.17 | 59315.72 | 1.1 | -26886.65 | 30
19-072-0347.12 | RIOC - Firefighters Field | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 691 | 812.5 | 121.5 | 8832.56 | 72.7 | 691 | 33884.93 |  | 812.5 | 14.95 | 42717.49 | 1.52 | -10227.27 | 2.5
19-072-0347.13 | RIOC - Hope Memorial | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 679.5 | 812.5 | 133 | 9484.24 | 71.31 | 679.5 | 44492.79 |  | 812.5 | 16.37 | 53977.03 | 1.2 | -21633.72 | 30
19-072-0347.14 | RIOC - Blackwell House | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 622.25 | 812.5 | 190.25 | 13043.72 | 68.56 | 622.25 | 42154.07 |  | 812.5 | 23.42 | 55197.79 | 1.18 | -22816.09 | 21
19-072-0347.15 | RIOC - SOSP Rip Rap Reventment | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 628.5 | 812.5 | 184 | 13545.81 | 73.62 | 628.5 | 25045.48 |  | 812.5 | 22.65 | 38591.29 | 1.68 | -6092.17 | 3.5
19-072-0347.16 | RIOC - AVAC Maintenance | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 799 | 812.5 | 13.5 | 1144.26 | 84.76 | 799 | 53735.74 |  | 812.5 | 1.66 | 54880 | 1.18 | -22553.19 | 0
19-072-0347.17 | RIOC - Assessments & Graphics | Franco, Frank | 2.04 | 2 | 65000 | 32500 | 40 | 812.5 |  | 812.5 | 812.5 | 0 | 0 | 0 | 812.5 | 32500 |  | 812.5 | 0 | 32500 | 2 | 0 | 0
19-072-0347.18 | RIOC - Misc OR Requests | Engblom, Trevor | 2.04 | 2 | 20000 | 10000 | 40 | 250 |  | 0 | 250 | 695.5 | 48764.88 | 70.11 | -445.5 | -31236.17 |  | 250 | 278.2 | 17528.71 | 1.14 | -7543.86 | 72
19-072-0347.19 | RIOC - Tramway Elevator | Engblom, Trevor | 2.11 | 2 | 411800 | 205900 | 40 | 5147.5 |  | 5104 | 5147.5 | 43.5 | 2632.98 | 60.53 | 5104 | 204652.68 |  | 5147.5 | 0.85 | 207285.66 | 1.99 | -1390.91 | 19
19-082-0093 | Columbia University CM Svcs Lerner Hall | Burke, Stephen | 2.04 | 2.1 | 60000 | 28571.43 | 40 | 714.27 |  | 515.2 | 714.27 | 223.5 | 18376.68 | 82.22 | 490.77 | 20091.2 |  | 714.27 | 31.29 | 38467.88 | 1.56 | -9005.07 | 0
19-117-0278.01 | NYCHA-Boiler Replacemnt-Sotomayor Houses | Choudhury, Faisal | 2.04 | 2.2 | 5549782 | 2522628.18 | 40 | 63065.7 |  | 57846.95 | 63065.7 | 5218.75 | 294747.7 | 56.48 | 57846.95 | 3216294.25 |  | 63065.7 | 8.28 | 3511041.95 | 1.58 | -786461.4 | 523
19-117-0278.02 | NYCHA-Boiler Replacemnt-Taft Houses | Choudhury, Faisal | 2.04 | 2.2 | 4080108 | 1854594.54 | 40 | 46364.86 |  | 42064.86 | 46364.86 | 4300 | 245923.7 | 57.19 | 42064.86 | 2412994.48 |  | 46364.86 | 9.27 | 2658918.18 | 1.53 | -656246.36 | 287
19-117-0278.03 | NYCHA - Harborview Terrace Balconies | Wong, David | 2.15 | 2.2 | 1652037 | 750925.91 | 40 | 18773.14 |  | 18773.14 | 18773.14 | 0 | 0 | 0 | 18773.14 | 750925.6 |  | 18773.14 | 0 | 750925.6 | 2.2 | 17463.39 | 0
19-117-0278.04 | NYCHA-Ingersoll Exter Reno Contract 2 | Choudhury, Faisal | 2.04 | 2.2 | 3826218 | 1739190 | 40 | 43479.75 |  | 42671.25 | 43479.75 | 808.5 | 43148.02 | 53.37 | 42671.25 | 2277278.84 |  | 43479.75 | 1.86 | 2320426.86 | 1.65 | -443322.94 | 257.5
19-117-0278.05 | NYCHA-Ingersoll Exter Reno Contract 1 | Choudhury, Faisal | 2.04 | 2.2 | 2970852 | 1350387.27 | 40 | 33759.68 |  | 33645.68 | 33759.68 | 114 | 5381.94 | 47.21 | 33645.68 | 1588412.55 |  | 33759.68 | 0.34 | 1593794.49 | 1.86 | -140932.26 | 0
19-117-0278.06 | NYCHA-Whitman Houses Exterior Renovation | Choudhury, Faisal | 2.04 | 2.2 | 2699379 | 1226990.45 | 40 | 30674.76 |  | 25472.51 | 30674.76 | 5202.25 | 293320.71 | 56.38 | 25472.51 | 1436227.48 |  | 30674.76 | 16.96 | 1729548.18 | 1.56 | -407146.15 | 76
19-195-0290.01 | OPRHP - RCSP - South Playground | Franco, Frank | 2.15 | 2.1 | 338300 | 161095.24 | 40 | 4027.38 |  | 3405.38 | 4027.38 | 622 | 38235.96 | 61.47 | 3405.38 | 209337.56 |  | 4027.38 | 15.44 | 247573.52 | 1.37 | -85839.07 | 141.5
19-195-0290.02 | OPRHP - RCSP - Electrical Upgrade | Franco, Frank | 2.15 | 2.1 | 338300 | 161095.24 | 40 | 4027.38 |  | 367 | 367 | 0 | 0 | 0 | 367 | 14680 |  | 367 | 0 | 14680 | 23.04 | 146412.08 | 0
19-201-0248.01 | NCDPW - Mission 4 CPM Scheduler | Hurley, Joseph | 2.15 | 2.2 | 73000 | 33181.82 | 40 | 829.55 |  | 764.55 | 829.55 | 65 | 4360.9 | 67.09 | 764.55 | 51294.25 |  | 829.55 | 7.84 | 55655.15 | 1.31 | -21771.7 | 0
19-217-0271 | DSNY Bronx District 9, 10, 11 Facility | Choudhury, Faisal | 2.15 | 2.1 | 14384757 | 6849884.29 | 40 | 171247.11 |  | 170281.36 | 171247.11 | 965.75 | 69319.43 | 71.78 | 170281.36 | 7030132.56 |  | 171247.11 | 0.56 | 7099452 | 2.03 | -250171.7 | 27
19-225-0282 | NYCSCA - CM Contingent & Temp Staffing | Frangas, Andrew | 2.15 | 1.97 | 1250000 | 634517.77 | 40 | 15862.94 |  | 11601.44 | 15862.94 | 4261.5 | 228271.3 | 53.57 | 11601.44 | 621442.15 |  | 15862.94 | 26.86 | 849713.45 | 1.47 | -215822.37 | 984.5
19-238-0270 | NYCP&R - Highbridge Park Comfort Station | Hurley, Joseph | 2.15 | 2.4 | 15109.73 | 6295.72 | 40 | 157.39 |  | 102.39 | 157.39 | 55 | 5009.08 | 91.07 | 102.39 | 9325.09 |  | 157.39 | 34.95 | 14334.17 | 1.05 | -7362.44 | 0
19-242-2292 | Broad Channel VFD-PLA Feasibility Study | Hurley, Joseph | 2.15 | 2.57 | 13572.89 | 5281.28 | 40 | 132.03 |  | 69.03 | 132.03 | 63 | 5713.08 | 90.68 | 69.03 | 6259.9 |  | 132.03 | 47.72 | 11972.98 | 1.13 | -5698.43 | 0
19-243-0031.01 | Battery Pk Resiliency- Feasibility Analy | Franco, Frank | 2.15 | 2.4 | 29495.62 | 12289.84 | 40 | 307.25 |  | 241.25 | 307.25 | 66 | 5800.08 | 87.88 | 241.25 | 21201.05 |  | 307.25 | 21.48 | 27001.13 | 1.09 | -13341.31 | 0
19-243-0031.02 | Battery Pk City - Rockefeller Park | Franco, Frank | 2.15 | 2.4 | 84000 | 35000 | 40 | 875 |  | 862 | 875 | 13 | 802.88 | 61.76 | 862 | 53237.12 |  | 875 | 1.49 | 54040 | 1.55 | -15123.78 | 4
19-247-1139 | USDOT- PM Oversight Svcs | Valdemira, Vincent | 2.15 | 2.17 | 1602650 | 738548.39 | 40 | 18463.71 |  | 18461.71 | 18463.71 | 2 | 224.08 | 112.04 | 18461.71 | 2068449.99 |  | 18463.71 | 0.01 | 2068674.07 | 0.77 | -1335945.03 | 0
19-248-0245 | MTA-IQ for Federal Construction Projects | Valdemira, Vincent | 2.15 | 2.1 | 30018 | 14294.29 | 40 | 357.36 |  | 267.61 | 357.36 | 89.75 | 7821.7 | 87.15 | 267.61 | 23322.17 |  | 357.36 | 25.11 | 31143.87 | 0.96 | -16974.46 | 29