## PHR WITH WIP & AR
[7 empty] | Architect : WIP and AR Tracking |  |  |  | 2019-12-16 |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Project Name | Contract Amount | LiRo Billed Fee | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Architect | Colon, Erinsson | 13-069-0245 |  | MTA NYCT Sea Beach Renewal Eighth Avenue | 1402147 | 1235050 | 426 | 426 | 2017-09-02 | [7 empty] | N |  | N
2 | Architect | Colon, Erinsson | 13-069-0245 | CA-2 |  |  |  |  | 426
3 | Architect | Colon, Erinsson | 13-104-0278.01 |  | NYCHA HSCIP Phase 3 Riis | 2086519 | 1682816 | 84745 | 34036 | 2019-09-27 | 11.29.19 SantanaL: 1 invoice in October and 4 in November totaling to $ 51,878.66 went out to client. 6/5-milestone payments are based on % of construction. | [6 empty] | N |  | N
4 | Architect | Colon, Erinsson | 13-104-0278.01 | CA |  |  |  |  | 33350
5 | Architect | Colon, Erinsson | 13-104-0278.01 | CO-062 |  |  |  |  | 686 |  | 6/5-milestone payments are based on % of construction. Next milestone should be by 7/15/19
6 | Architect | Colon, Erinsson | 13-131-0278.02 |  | NYCHA HSCIP PH3 East River Houses | 602615 | 493727 | 145573 | 132292 | 2019-09-16 | 12.9.19 SantanaL: Per Erinsson - The job is currently at 43%. We also have an Add Service for (Extension of Time) for another $57,062.50; we need to get this approved and then we should be able to invoice for 50% of that value. | [6 empty] | N |  | N
7 | Architect | Colon, Erinsson | 13-131-0278.02 | CA |  |  |  |  | 132292
8 | Architect | Colon, Erinsson | 17-143-0113 |  | DASNY TOH Inwood Gardens | 114463 | 27897 | 64330 | 63313 | 2019-01-09 | 12.9.2019: Per Erinsson: We owed DASNY some information on Inwood. Erinsson is following up with Heather Heustis at DASNY regarding the outstanding info she needs for final payment on Inwood. | [6 empty] | N |  | N
9 | Architect | Colon, Erinsson | 17-143-0113 | ARCH |  |  |  |  | 51309
10 | Architect | Colon, Erinsson | 17-143-0113 | SURVEY |  |  |  |  | 12004
11 | Architect | Colon, Erinsson | 17-144-0113 |  | DASNY TOH Mill River Houses | 260830 | 40812 | 73079 | 64318 | 2019-02-01 | 12.9.19 Per Erinsson: We have NOT gotten a response for Mill River. Argiris is following up with client re: Mill River. | [6 empty] | N |  | N
12 | Architect | Colon, Erinsson | 17-144-0113 | ARCH |  |  |  |  | 50475
13 | Architect | Colon, Erinsson | 17-144-0113 | SURVEY |  |  |  |  | 13844
14 | Architect | Colon, Erinsson | 18-128-0281 |  | NYPD Design Svcs Requirements Contract | 663935 | 339249 | 83456 | 39465 | 2019-07-19 | 10.3.19 SantanaL: Per Joe Grant: Invoice will be issued by end of next week. Open WIP $77,685.60 | [6 empty] | N |  | N
15 | Architect | Colon, Erinsson | 18-128-0281 | 1 |  |  |  |  | 15865
16 | Architect | Colon, Erinsson | 18-128-0281 | 8 |  |  |  |  | 4652
17 | Architect | Colon, Erinsson | 18-128-0281 | 15 |  |  |  |  | 9629
18 | Architect | Colon, Erinsson | 18-128-0281 | TEMP |  |  |  |  | 9320
19 | Architect | Colon, Erinsson | 19-168-2222 |  | MLJ Contracting - PANYNJ Police Dept | 2616313 | 1308157 | 252099 | 7294 | 2019-10-11 | 12.9.19 Invoicing 80% of Phase 003 Final01 and 007 Final02, waiting on transferred time to post to invoice. Time was charged to Phase 006 100%Sub02 incorrectly. | [6 empty] | N |  | N
20 | Architect | Colon, Erinsson | 19-168-2222 | 7 |  |  |  |  | 4591
21 | Architect | Colon, Erinsson | 19-168-2222 | 8 |  |  |  |  | 2703
22 | Architect | Giorgou, Argiris | 15-359-1719 |  | RB BETHPAGE REALTY/120 HICKSVILLE RD | 100000 | 91111 | 3383 | 3383 | 2018-05-25 | 12.9.19: Invoice to clear WIP will go out this month. | [6 empty] | N |  | N
23 | Architect | Giorgou, Argiris | 15-359-1719 | 102 |  |  |  |  | 1200
24 | Architect | Giorgou, Argiris | 15-359-1719 | 104 |  |  |  |  | 1626
25 | Architect | Giorgou, Argiris | 15-359-1719 | 851 |  |  |  |  | 557
26 | Architect | Giorgou, Argiris | 16-384-0425 |  | OB HSING/CCTV INSTALLATIONS | 28500 | 27525 | 4263 | 4263 | 2018-05-25 | 12.9.19: Invoice to clear balance of contract amount will go ut this month in the amount of $975. The remaining WIP balance will need to be written off $3,287.60 | [6 empty] | N |  | N
27 | Architect | Giorgou, Argiris | 16-384-0425 | 900 |  |  |  |  | 4263
28 | Architect | Giorgou, Argiris | 17-269-1089 |  | AECOM/SCC STEM BUILDING | 287550 | 45069 | 38002 | 38002 | 2018-05-25 | 12/2/19 - Project is on Hold letter being sent to AECOM for additional funding. "Final" invoice for Design in the amount of $47K may be at risk. 100% design has been submitted to AECOM, pending SCCC review and the estimate from the Architect. There is $149K in budget for the CI. Joe Grant anticipates $400K in CI will be required. In addition, if the estimate comes in over the $17M construction budget VE will be required which is also not billable (approx $20 -$25K). When we acquired this project from Bowne, we were told that they were 90% complete (billings represented milestones), were in actuality, they were 30% complete. |  | 143 |  |  |  |  | N |  | Y
29 | Architect | Giorgou, Argiris | 17-269-1089 | 102 |  |  |  |  | 33043
30 | Architect | Giorgou, Argiris | 17-269-1089 | 103 |  |  |  |  | 4959
31 | Architect | Giorgou, Argiris | 17-269-1089 | [10 empty] | 143.2 | 277612 | 2017-10-31 | Frank Lowe working on rate/contract issue SCC
32 | Architect | Giorgou, Argiris | 18-123-1855 |  | Fox Hollow TOB Permit Issues | 26169 | 26169 | 1787 | 0 | 2019-06-19 |  |  | 26169 |  |  |  |  | N |  | N
33 | Architect | Giorgou, Argiris | 18-123-1855 | [10 empty] | 26169.42 | 1 | 2019-08-13 | 12.9.19 PM in contact with Mauricio "General Manager" at Fox Hollow who requested additional work from our team; However, PM advised previous invoice paymet is required prior to providing add'l services. Mauricio is following up with his accounting team on payment status.
34 | Architect | Giorgou, Argiris | 18-237-1954 |  | LI Script - 333 Crossways-Interior Alter | 55097 | 55097 | 5124 | 4163 | 2019-04-12 | [7 empty] | N |  | N
35 | Architect | Giorgou, Argiris | 18-237-1954 | 1 |  |  |  |  | 4163
36 | Architect | Giorgou, Argiris | 18-323-0247 |  | NCC - SSC Fire Area | 23000 | 12060 | 1626 | 1060 | 2019-04-12 | [7 empty] | N |  | N
37 | Architect | Giorgou, Argiris | 18-323-0247 | 2 |  |  |  |  | 1060
38 | Architect | Grant, Joseph | 15-094-0113 |  | DASNY City College Compton Hall Fire Res | 73492 | 65512 | 892 | 892 | 2017-08-04 | 12.9.19 LS: Per Joe Grant - Closing job, unable to bill until close out proces starts. Anticipated to begin end of year. | [6 empty] | N |  | N
39 | Architect | Grant, Joseph | 15-094-0113 | ARCH |  |  |  |  | 892
40 | Architect | Grant, Joseph | 18-246-0190 |  | Loring Eng-70 Mulberry St/FA Upgrade Bac | 19379 | 19379 | 0 | 0 | 2019-01-04 |  |  | 19379 |  |  |  |  | N |  | N
41 | Architect | Grant, Joseph | 18-246-0190 | [10 empty] | 19379.44 | 00000001-REV | 2019-01-16 | 12.9.19 Joe Grant sent emailon 12.2.19 to client requesting update on payment status.
42 | Architect | Miller, Lee | 19-079-1413 |  | Artimus- 126th St & Park Ave | 27600 | 0 | 13734 | 11162 |  | 12.9.19: New PM assigned to this job. Joe Grant finding out from PM if we can invoice. | [6 empty] | N |  | N
43 | Architect | Miller, Lee | 19-079-1413 | 1 |  |  |  |  | 2230
44 | Architect | Miller, Lee | 19-079-1413 | 2 |  |  |  |  | 8932
45 | Architect | Niewiadomska, Katarzyna | 18-236-0472 |  | Westchester DPW-Woodfield Cottage Securi | 132000 | 80592 | 7031 | 7031 | 2019-01-04 | 12.9.19 Per Joe Grant - invoice went out to client in the amount of 15,000 for approval. This will clear outstanding WIP when posted in Vision. | [6 empty] | N |  | N
46 | Architect | Niewiadomska, Katarzyna | 18-236-0472 | 1 |  |  |  |  | 7031
47 | Architect | Niewiadomska, Katarzyna | 19-060-0190 |  | Loring Engineers- Carroll Gardens Librar | 50000 | 8867 | 24692 | 19911 | 2019-08-02 | 11.08.19 WongK: I spoke with Edgar Eweka. We can bill up to 25% of total project value. 25% of 50K is $12,500. We have billed $8,866.90 already so remaining is $3,633.10. 11.06.19 WongK: FlorenceL emailed Lorring/DDC how much we can billed. Waiting for answers.10.2.19 SantanaL: Per Kathy Wong next 25% invoice is being prepared.7/23/19 SantanaL: Milestone billing - Per Joe Grant: Open WIP will be billed by Aug. 15th | [6 empty] | N |  | N
48 | Architect | Niewiadomska, Katarzyna | 19-060-0190 | 1 |  |  |  |  | 19911
49 | Architect | Niewiadomska, Katarzyna | 19-226-0305 |  | NYCDCAS- Bronx Supreme Courthouse | 538395 | 0 | 40087 | 5917 |  | 11.06.2019 WongK: After 12.02.2019 please prepare an invoice for SD Submission (SD Submission was sent to Client on11.02.2019. Right now the project is under DCAS Review) | [6 empty] | N |  | N
50 | Architect | Niewiadomska, Katarzyna | 19-226-0305 | 1 |  |  |  |  | 5917
51 | Architect | Parengkuan, Lilyanne | 18-028-0425 |  | TOBHA - Misc Services | 121975 | 96063 | 4265 | 972 | 2019-10-31 | 11.5.19 SantanaL: Billed $48,314.31 on 10/11/19.10.2.19 SantanaL: Billed $ 47,748.39 on 8/26/196/5/19- per Joe Grant, T & M contract | [6 empty] | N |  | N
52 | Architect | Parengkuan, Lilyanne | 18-028-0425 | APART |  |  |  |  | 648
53 | Architect | Parengkuan, Lilyanne | 18-028-0425 | WINDOW |  |  |  |  | 324
54 | Architect | Pohlsander, Dianne | 16-350-0472 |  | WCDPW - Rye Playland - Switchgear Bldg. | 9207839 | 2605868 | 163071 | 17328 | 2019-09-27 | 11.5.19 DP: Draft Invoice #12 submitted to the County 2019.10.15 | [6 empty] | N |  | N
55 | Architect | Pohlsander, Dianne | 16-350-0472 | ADDSV4 |  |  |  |  | 1024
56 | Architect | Pohlsander, Dianne | 16-350-0472 | RP006 |  |  |  |  | 1827
57 | Architect | Pohlsander, Dianne | 16-350-0472 | RP025 |  |  |  |  | 154
58 | Architect | Pohlsander, Dianne | 16-350-0472 | RP033 |  |  |  |  | 4765
59 | Architect | Pohlsander, Dianne | 16-350-0472 | RP040 |  |  |  |  | 6552
60 | Architect | Pohlsander, Dianne | 16-350-0472 | SWITCH |  |  |  |  | 3007
61 | Architect | Pohlsander, Dianne | 16-350-0472 | [10 empty] | -3611.81 | 000000007R-2 | 2018-08-17
62 | Architect | Pohlsander, Dianne | 18-042-0472 |  | WCDPW Mt Vernon District Office Reno | 423135 | 105612 | 10285 | 10285 | 2019-09-27 | [7 empty] | N |  | N
63 | Architect | Pohlsander, Dianne | 18-042-0472 | CD/CA |  |  |  |  | 10285
64 | Architect | Pohlsander, Dianne | 18-285-0265 |  | NYCDDC Capital Proj Snug Harbor Cultural | 1241979 | 704932 | 288792 | 204297 | 2019-07-31 | 12.9.19 Per Joe Grant - invoice went out to client and it was approved last week. WIP will clear when invoice is posted.11.5.19 DP: Draft invoice #5 submitted to DDC 2019.10.29. | [6 empty] | N |  | N
65 | Architect | Pohlsander, Dianne | 18-285-0265 | 1 |  |  |  |  | 13651
66 | Architect | Pohlsander, Dianne | 18-285-0265 | 2 |  |  |  |  | 126866
67 | Architect | Pohlsander, Dianne | 18-285-0265 | 3 |  |  |  |  | 63780
68 | Architect | Yam, Cindy | 13-104-0278.03 |  | NYCHA HSCIP Phase 3 Wald | 1191468 | 976096 | 45518 | 12030 | 2019-09-06 | 12.9.19 Per Joe Grant: Job is billed by percentage of construction. | [6 empty] | N |  | N
69 | Architect | Yam, Cindy | 13-104-0278.03 | CA |  |  |  |  | 12030
Total | [5 empty] | 21294400 | 10047660 | 1356260 | 681841 | [6 empty] | 0 | 45691