## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Blond, Lawrence | 06-10-100CP |  | HHC Emerg Power Gen Construction Phase | 6456843 | 6199299 | 6938 | 6938 | 2014-09-30 | LB Final invoice requires facility to get C of O | [6 empty] | N |  | N
2 | CM | Blond, Lawrence | 06-10-100CP | LINCLN |  |  |  |  | 6938
3 | CM | Blond, Lawrence | 07-31-200B |  | NYCDOS Marine Transfer St LIRO-URS 50-50 | 7714983 | 7718246 | 8705 | 0 | 2019-10-11 |  | 18676 | 164355 |  |  |  |  | N |  | N
4 | CM | Blond, Lawrence | 07-31-200B | [10 empty] | 66319.68 | 110 | 2019-01-24
5 | CM | Blond, Lawrence | 07-31-200B | [10 empty] | 84588.82 | 111 | 2019-06-05
6 | CM | Blond, Lawrence | 07-31-200B | [10 empty] | 13446.44 | 112 | 2019-07-17
7 | CM | Blond, Lawrence | 15-016-0276 |  | FDNY CM Services | 10672726 | 7355560 | 16451 | 16451 | 2019-08-02 | 9/9/19-$50,000 at Risk. Current staff billing exisitng projects with the assumption new projects will start and time will be transfered. New projects were cancelled. JR 8/1/19 EC227 - Awaiting registration of additional funds in the amount of $128,569.40 in order to complete the extended work at this project. Current WIP $ 108K ,EC237 - The remaining WIP balance of $12k will be final invoiced upon contract completion anticipated late Summer. ,PROP2 - The remaining WIP balance of $16k will be final invoiced upon contract completion late Summer. EC55 - Final Invoice will be submitted next week to include current Pay Period. | 12464 | [5 empty] | N |  | Y
8 | CM | Blond, Lawrence | 15-016-0276 | FIBER2 |  |  |  |  | 851
9 | CM | Blond, Lawrence | 15-016-0276 | PROP2 |  |  |  |  | 15600
Total |  |  |  |  | 32094 | 46778 |  |  | 31140 | 164355