## PHR WITH WIP & AR
[7 empty] | Boston Architectural : WIP and AR Tracking |  |  |  | 2019-12-16 |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Project Name | Contract Amount | LiRo Billed Fee | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Boston Architectural | Anderson, Mark | 16-452-1824.01 |  | UMass Memorial ED V Addition/Reno T&M | 35074 | 35074 | 1156 | 1156 | 2018-10-31 | JP 12/4/19 emailed Mark again and his response was "I sent a schedule request for a meeting to him. The discussion may happen next week but historically they are not able to spin on a dime with any contractual sign-offs. Optimistically he could sign-off on this add services before year end. " JP 11/12/19 emailed Mark Anderson again about the Additional services and if he has spoken to Tom Skowren - 11/15/19 have not heard back from Mark, as he has been in Minnesota for the Shriners project10/21/19 JP sent Mark another email to see if he has spoken to Tom Skowron regarding the additional services. Asked him to let me know in time for our 10/29/19 meeting - Mark has not spoken to Tom but did tell me the additional services proposal is for $274,000.009/11/19 JP sent Mark Anderson an email to see if he has reached out to Tom Skowron regarding additional services8/20/19 JP rec'd email from MA he just received the efforts from MEP and he will have a conversation with Tom Skowron when Tom returns from vacation - check back on 9/6/198/6/19 JP reached MAnderson and he has not asked for additional services - prepping for meeting to ask - check back 8/30/197/12/19 JP reached out to Mark Anderson (PM) on if decision has been made on additional scope, have not heard back from Mark4/9/19 JP tracking time for additional scope per Mark Anderson(PM) | [6 empty] | N |  | N
2 | Boston Architectural | Anderson, Mark | 16-452-1824.01 | ADDSVC |  |  |  |  | 1156
3 | Boston Architectural | Anderson, Mark | 18-139-1824 |  | UMass Mem Hosp LS/SOC Drawings | 40200 | 578 | 35620 | 31660 | 2019-11-07 | [7 empty] | N |  | N
4 | Boston Architectural | Anderson, Mark | 18-139-1824 | 1 |  |  |  |  | 31660
5 | Boston Architectural | Anderson, Mark | 18-346-1828 |  | MRH - Pham/Oncology Reno | 42800 | 31250 | 1477 | 0 | 2019-09-27 | JP 9/16/19 - Job has started up again and billing has started this WIP will be cleared when I enter the 9/1/19 invoice into VisionJP 8/6/19 Paperwork from Fire Marshall was received on 8/2/19 - Construction starts on 8/12/19, so these hours should be cleared when we bill CAJP 7/16/19 spoke with PM - Mark Anderson and he is waiting on State Fire Marshall for project to continue - check back 8/19/19 | 600 | 6375 |  |  |  |  | N |  | N
6 | Boston Architectural | Anderson, Mark | 18-346-1828 | [10 empty] | 5650 | DG-000035088 | 2019-02-28 | JP 12/5/19 heard from Suzanne, check # 291099 in amt of $2,000.00 was mailed today leaving balance on this date $5650 - Suzanne also stated they hope to have this paid by year end.JP 11/18/19 check in amt of $2,000.00 is being sent 11/19/19 ck # 290891JP 11/15/19 heard back from Suzanne - hoping to give me an update on Monday 11/18/19JP 11/12/19 sent another request as to when we may receive additional payment on this claim.JP 11/8/19 sent email to Suzanne asking for payment update as to when we may be paid additionally on this o/s invoice9/27/19 received email from Suzanne in AP a check has been cut in the amount of $3,711.48 ck # 290149 dated 9/26/19 covering $2,500.00 partial pmt for # 35088, $725.00 for 35104 and $468.48 for 35150. This leave a balance owed on the Pharmacy portion of the invoices as $ 11,650.00. Suzanne is hoping to pay the balance on # 35088 on 10/3/19 - check back on 10/4/199/16/19 JP received email from Shelly stating she is meeting with AP on 9/17/19 and is hoping to get answers as to why we have not been paid and she will let me know after the meeting
7 | Boston Architectural | Anderson, Mark | 18-346-1828 | [10 empty] | 725 | DG-000035129 | 2019-04-30 | JP 12/5/19 emailed Shelly again to see when we may receive payment.JP 11/12/19 sent copies of invoices to Shelly Drew asking when we may be paid on the total outstanding $2,225.00.9/30/19 this is an Oncology invoice need to check back with Shelly as to when the oncology invoices will be paid.9/16/19 JP received email from Shelly stating she is meeting with AP on 9/17/19 and is hoping to get answers as to why we have not been paid and she will let me know after the meeting
8 | Boston Architectural | Anderson, Mark | 19-184-1817 |  | Baystate- ML - Sputum Induction DPH | 6045 | 0 | 5870 | 5870 | [8 empty] | N |  | N
9 | Boston Architectural | Anderson, Mark | 19-184-1817 | 1 |  |  |  |  | 5870
10 | Boston Architectural | Chase, Todd | 15-376-1807 |  | Mayo Regional - Patient Floor/MEP | 749310 | 349859 | 37637 | 32439 | 2019-09-13 | 12/2/19-Todd and Kovacs are working on getting pricing for requried repairs. LiRo is at Risk for WIP of $30,332 and up to potentially $150K for the replacement of the roof top unit. 8/21/19-Brian advised that until the mechanical issue with the rooftop ERV unit is settled (Al is also assisting) the WIP cannot be billed and pending the outcome of the mechanical issue this time is at Risk. | [6 empty] | N |  | Y
11 | Boston Architectural | Chase, Todd | 15-376-1807 | ADDSVC |  |  |  |  | 1400
12 | Boston Architectural | Chase, Todd | 15-376-1807 | CONST |  |  |  |  | 24536
13 | Boston Architectural | Chase, Todd | 15-376-1807 | MEPD/C |  |  |  |  | 6928
14 | Boston Architectural | Chase, Todd | 15-376-1807 | ONSITE |  |  |  |  | -425
15 | Boston Architectural | Lam, Thomas | 18-103-1817 |  | Baystate Mary Lane Women's Health Reno | 45581 | 47331 | -295 | 0 | 2019-07-31 |  | 52 | 1698 |  |  |  |  | N |  | N
16 | Boston Architectural | Lam, Thomas | 18-103-1817 | ARCHA1 |  |  |  |  | -295 |  | 07/31/18Tom LamHistorical data not complete for billing
17 | Boston Architectural | Lam, Thomas | 18-103-1817 | [10 empty] | 830 | DG-000035132 | 2019-04-30 | JP 11/12/19 emailed Donna again regarding the outstanding balance.JP 9/17/19 received email from Donna - she has supplemented the PO's for the amendments and now she needs to wait till that goes through - check back 10/2/19JP 9/6/19 - received an email back from Donna and she is working with her AP department to get us paid in full
18 | Boston Architectural | Lam, Thomas | 18-103-1817 | [10 empty] | 27.75 | DG-000035142 | 2019-05-15 | JP 11/12/19 emailed Donna again regarding the outstanding balance.JP 9/17/19 received email from Donna - she has supplemented the PO's for the amendments and now she needs to wait till that goes through - check back 10/2/19
19 | Boston Architectural | Lam, Thomas | 18-103-1817 | [10 empty] | 2820 | DG-000035160 | 2019-05-31 | JP 11/12/19 emailed Donna again regarding the outstanding balance.JP 9/17/19 received email from Donna - she has supplemented the PO's for the amendments and now she needs to wait till that goes through - check back 10/2/19
20 | Boston Architectural | Lam, Thomas | 18-103-1817 | [10 empty] | -1980 | DG-000035180 | 2019-06-24 | JP 11/12/19 emailed Donna again regarding the outstanding balance.JP 9/17/19 received email from Donna - she has supplemented the PO's for the amendments and now she needs to wait till that goes through - check back 10/2/19
21 | Boston Architectural | Lam, Thomas | 18-271-1870 |  | Harbor CHC Cordage Park - Plymouth | 18731 | 18721 | 0 | 0 | 2019-03-31 | JP 11/19/19 this WIP will be moved to the new Harbor Health # once the project is opened - PIF sent to Audrey 11/19/19 |  | 11 |  |  |  |  | N |  | N
22 | Boston Architectural | Lam, Thomas | 18-271-1870 | [10 empty] | 10.98 | DG-000035199 | 2019-07-30
23 | Boston Architectural | Lam, Thomas | 18-271-1870.01 |  | Harbor CHC Cordage Park - Plymouth T&M | 2793 | 2793 | 0 | 1725 | 2019-07-31 | JP 11/19/19 this WIP will be moved to the new Harbor Health # once the project is opened - PIF sent to Audrey 11/19/19 | 2793 | [5 empty] | N |  | N
24 | Boston Architectural | Lam, Thomas | 18-271-1870.01 | 1 |  |  |  |  | 1725
25 | Boston Architectural | Lam, Thomas | 19-035-1818 |  | SHC - Outpatient Rehab Expansions CD-CA | 14500 | 10900 | 1253 | 204 | 2019-06-22 | [7 empty] | N |  | N
26 | Boston Architectural | Lam, Thomas | 19-035-1818 | 1 |  |  |  |  | 204
27 | Boston Architectural | Lam, Thomas | 19-063-2004 |  | Comm Health Connect - Planning Study | 8275 | 9613 | 230 | 230 | 2019-05-31 | [7 empty] | N |  | N
28 | Boston Architectural | Lam, Thomas | 19-063-2004 | 1 |  |  |  |  | 230
29 | Boston Architectural | Lam, Thomas | 19-090-2155 |  | Manet - Study-HRSA New Access Point Gran | 2530 | 2530 | 1380 | 0 | 2019-04-30 |  |  | 2530 |  |  |  |  | N |  | N
30 | Boston Architectural | Lam, Thomas | 19-090-2155 | [10 empty] | 2530 | DG-000035195 | 2019-07-23 | JP 12/9/19 emailed Linda again as we never received replacement checkJP11/19/19 heard back from Linda, this invoice was paid on 8/29/19 and mailed to Syosset, she will stop payment on the check and reissue as it was never cashedJP 11/18/19 emailed invoice to Linda in accounts payable, she is checking into it. .
31 | Boston Architectural | Lam, Thomas | 19-110-1818 |  | SHC- Master Plan & DPH Assessment | 30150 | 0 | 65730 | 51120 | 2019-09-25 | JP 11/15/19 PM - TL has asked that I hold the invoice until amendment is done to increase the fee | [6 empty] | N |  | N
32 | Boston Architectural | Lam, Thomas | 19-110-1818 | 1 |  |  |  |  | 43938
33 | Boston Architectural | Lam, Thomas | 19-110-1818 | 2 |  |  |  |  | 7182
34 | Boston Architectural | Shah, Amit | 17-307-1812 |  | MPX-Health for Life Dispensary -Fall Riv | 92015 | 91843 | 5652 | 5652 | 2019-01-31 | JP 11/19/20 same note - this needs to be written offJP 9/17/19 same note as previouslyJP 7/23/19 need to write this WIP off as the project was overbilled per Amit Shah (PM)JP 4/11/19 per PM(AS) This project was overbilled and and this WIP needs to be written off. | [6 empty] | N |  | Y
35 | Boston Architectural | Shah, Amit | 17-307-1812 | CONADM |  |  |  |  | 6172
36 | Boston Architectural | Shah, Amit | 17-307-1812 | CONDOC |  |  |  |  | -520
37 | Boston Architectural | Shah, Amit | 17-307-1812 | [10 empty] | -14053.13 | 00000ADVANCE | 2017-11-30 | JP- 11/19/19 not sure if this can be transferred to MB project or needs to be refunded to client - need to check with SK - he is out of the office till 11/21/19 - will check with Steve thenQP 8/14/19 There is a $14,053.13 credit on DG project #17-307 which may need to be applied to open AR on MB project #16-454 (CGX, MPX, PMB have merged). SK has meeting scheduled with client on 8/26/19 to review outstanding invoices on #16-454. Check back with SK at the end of the month.
38 | Boston Architectural | Shah, Amit | 17-313-1820 |  | Allen & Major-Washington Square Facade | 51172 | 51204 | 3728 | 3728 | 2019-08-02 | JP 11/20/19 spoke with Amit (PM) this project got over billed and this WIP needs to be written offP 9/17/19 need to check with PM on this WIP as project billed 100% back on 6/24/19 | [6 empty] | N |  | N
39 | Boston Architectural | Shah, Amit | 17-313-1820 | CO#3 |  |  |  |  | 2419
40 | Boston Architectural | Shah, Amit | 17-313-1820 | CONADM |  |  |  |  | 1309
41 | Boston Architectural | Shah, Amit | 17-323-1840.01 |  | Golden Pond Phase III - T&M | 0 | 2565 | 0 | 0 |  |  |  | 2565 |  |  |  |  | N |  | Y
42 | Boston Architectural | Shah, Amit | 17-323-1840.01 | [10 empty] | 2565 | 28736 | 2017-07-31 | JP 11/20/19 same note as before8/21/19- Brian advised thie AR is at Risk (2017 invoice). Amit Shah advised the client feels the estimate provided for this invoice is "useless and worth nothing".JP 8/20/19 Brian wants to reach out to Doug Noble and Amit to discuss this invoice.JP 7/22/19 - need to confirm with Brian this can be written offJP-4/11/19 this should be written off - per PM(AS) giving to Brian to review/approve so it may be sent to Christine in NYJP-11/30/18 according to the PM on the job - Amit Shah - this invoice will never be paid and should be written off
43 | Boston Architectural | Shah, Amit | 18-194-1880 |  | CCMC Pharmacy Renovation | 62050 | 42490 | 4266 | 321 | 2019-09-27 | [7 empty] | N |  | N
44 | Boston Architectural | Shah, Amit | 18-194-1880 | CONADM |  |  |  |  | 321
45 | Boston Architectural | Shah, Amit | 18-245-1812 |  | MPX - Cannatech Grow Facility | 63625 | 60875 | 2905 | 2905 | 2019-04-30 | JP 11/20/19 - this WIP needs to be written off as this project was overbilled per Amit (PM)JP 09/17/19 same note as beforeJP 7/23/19 need to write this WIP off as the project was overbilled per Amit Shah (PM)JP 4/11/19 need to speak to PM | [6 empty] | N |  | N
46 | Boston Architectural | Shah, Amit | 18-245-1812 | 1 |  |  |  |  | 2905
47 | Boston Architectural | Shah, Amit | 18-259-1945 |  | Huggins Hospital - CSR/MOB | 122950 | 119090 | 18807 | 2642 | 2019-09-27 | [7 empty] | N |  | N
48 | Boston Architectural | Shah, Amit | 18-259-1945 | 1 |  |  |  |  | 369
49 | Boston Architectural | Shah, Amit | 18-259-1945 | 2 |  |  |  |  | 369
50 | Boston Architectural | Shah, Amit | 18-259-1945 | 3 |  |  |  |  | 1831
51 | Boston Architectural | Shah, Amit | 18-259-1945 | 6 |  |  |  |  | 72
52 | Boston Architectural | Shah, Amit | 18-347-1809 |  | NSCH - Gloucester Behavioral Health | 21615 | 18824 | 1292 | 184 | 2019-09-27 | [7 empty] | N |  | N
53 | Boston Architectural | Shah, Amit | 18-347-1809 | 1 |  |  |  |  | 184
54 | Boston Architectural | Shah, Amit | 18-354-2065 |  | Southcoast - Charlton Memorial Hosp | 28475 | 26186 | 1478 | 369 | 2019-09-27 |  |  | 2820 |  |  |  |  | N |  | N
55 | Boston Architectural | Shah, Amit | 18-354-2065 | 1 |  |  |  |  | 369
56 | Boston Architectural | Shah, Amit | 18-354-2065 | [10 empty] | 2820 | DG-000035209 | 2019-08-01 | JP 11/20/19 sent o/s invoices to Helio Rosa @ SCHG asking for payment information
57 | Boston Architectural | Shah, Amit | 19-159-2216 |  | Genesis - Clinic Space @ Golden Pond | 11975 | 11900 | 813 | 813 | 2019-06-22 | JP 11/20/19 - this WIP needs to be written off as billing was billed 100% on 6/24/19 and these services are from July and Aug - job overbilled per Amit(PM) |  | 11900 |  |  |  |  | N |  | N
58 | Boston Architectural | Shah, Amit | 19-159-2216 | 1 |  |  |  |  | 813
59 | Boston Architectural | Shah, Amit | 19-159-2216 | [10 empty] | 11900 | DG-000035186 | 2019-06-24 | JP 12/12/19 received emaiol from Roni Davis @ Genesis that we have been set up as a vendor and they are processing invoice now - check back on 12/20/19JP 12/9/19 resent invoice asking for update since W9 had been sent.JP 11/26/19 sent W9 to Genesis in order for them to pay usJP 11/20/19 sent invoice via email to elizabeth.thomas52@genesishcc.com asking for payment status.
60 | Boston Architectural | Shah, Amit | 19-175-2036 |  | BNHC - Optometry Clinic Reno | 2575 | 0 | 435 | 435 |  | JP 11/20/19 - this WIP will be billed - job started and then stopped, expected to start up again. | [6 empty] | N |  | N
61 | Boston Architectural | Shah, Amit | 19-175-2036 | 1 |  |  |  |  | 435
62 | Boston Architectural | Sullivan, Christopher | 17-314-0884 |  | U. RI Dept of Admin-Health Lab Prog Stdy | 59678 | 37135 | 341 | 0 | 2019-10-25 | JP 4/11/19 will f/u with PM | 2772 | 3813 |  |  |  |  | N |  | N
63 | Boston Architectural | Sullivan, Christopher | 17-314-0884 | [10 empty] | 1162.5 | DG-000035174 | 2019-06-24 | JP 11/22/19 received email back Armando is out on leave of absense, was asked to forward all invoices to Simidele Mabray, which I did, check back on 12/9/19JP 11/22/19 sent copies of all o/s invoices and PO showing increase to Armando Goncalves asking for payment update
64 | Boston Architectural | Sullivan, Christopher | 17-314-0884 | [10 empty] | 2650 | DG-000035204 | 2019-08-01 | JP 11/22/19 received email back Armando is out on leave of absense, was asked to forward all invoices to Simidele Mabray, which I did, check back on 12/9/19JP 11/22/19 sent copies of all o/s invoices and PO showing increase to Armando Goncalves asking for payment update
65 | Boston Architectural | Sullivan, Christopher | 17-323-1840 |  | Golden Pond Residential - Phase III | 277664 | 273232 | 120 | 120 | 2019-08-30 | 11/26/19-open AR of $13K is at risk. |  | 6665 |  |  |  |  | N |  | Y
66 | Boston Architectural | Sullivan, Christopher | 17-323-1840 | STAIR |  |  |  |  | 120
67 | Boston Architectural | Sullivan, Christopher | 17-323-1840 | [10 empty] | 2602.75 | DG-000035173 | 2019-06-24 | JP 11/21/19 sent email to Doug Noble with balance owed asking for payment status.JP 9/11/19 sent email to Doug Noble checking on September pymt due on 9/1/19 $5,000.00 - no responseJP 8/26/19 August pmnt was receivedJP 8/19/19 the July pmt was received and I contacted D. Noble on his Aug pmt and have not heard back with check info will email him on 8/20/19JP 5/30/19 Doug Noble requested a pyment plan $9,100.00 on 6/1, $5,000.00 on 7/1, $5,000.00 on 8/1, $5,000.00 on 9/1 and $5,000.00 on 10/1 - checked with Andrea and she approved it
68 | Boston Architectural | Sullivan, Christopher | 17-323-1840 | [10 empty] | 4062.67 | DG-000035203 | 2019-08-01 | JP 11/21/19 sent email to Doug Noble with balance owed asking for payment status.JP 9/11/19 sent email to Doug Noble checking on September pymt due on 9/1/19 $5,000.00 - no responseJP 8/26/19 August pmnt was receivedJP 8/19/19 the July pmt was received and I contacted D. Noble on his Aug pmt and have not heard back with check info will email him on 8/20/19JP 5/30/19 Doug Noble requested a pyment plan $9,100.00 on 6/1, $5,000.00 on 7/1, $5,000.00 on 8/1, $5,000.00 on 9/1 and $5,000.00 on 10/1 - checked with Andrea and she approved it
69 | Boston Architectural | Sullivan, Christopher | 17-326-1819 |  | LRGH ED SD through CA | 353036 | 364648 | -575 | 1497 | 2019-05-15 | [7 empty] | N |  | N
70 | Boston Architectural | Sullivan, Christopher | 17-326-1819 | CONADM |  |  |  |  | -570
71 | Boston Architectural | Sullivan, Christopher | 17-326-1819 | CONDOC |  |  |  |  | 1342
72 | Boston Architectural | Sullivan, Christopher | 17-326-1819 | DESDEV |  |  |  |  | 725
73 | Boston Architectural | Sullivan, Christopher | 18-109-1843.01 |  | Joseph A. Russo MD-Feasibility Study T&M | 8575 | 4368 | 8545 | 7513 | 2019-04-30 | JP 11/22/19 Remaining WIP $6565 to be billed 12/2/19 | [6 empty] | N |  | N
74 | Boston Architectural | Sullivan, Christopher | 18-109-1843.01 | 1 |  |  |  |  | 7513
75 | Boston Architectural | Sullivan, Christopher | 19-080-2140 |  | Bountiful Farms - Natick Dispensary | 50275 | 46979 | 4768 | 2443 | 2019-07-19 | JP - 11/24/19 client wants invoice when construction documents are complete - wants to be invoiced at completion and acceptance - checking with Chris Sullivan as to where we are on this project. |  | 14146 |  |  |  |  | N |  | N
76 | Boston Architectural | Sullivan, Christopher | 19-080-2140 | 1 |  |  |  |  | 2094
77 | Boston Architectural | Sullivan, Christopher | 19-080-2140 | 2 |  |  |  |  | 349
78 | Boston Architectural | Sullivan, Christopher | 19-080-2140 | [10 empty] | 14146.25 | DG-000035163 | 2019-05-31 | JP 11/22/19 received partial payment in Sept, client feels we overbilled in relation to how contract is written, looking into this with the PM - Chris SullivanJP 9/10/19 emailed all outstanding invoices to Jeff Barton, apparently they share a mailbox and he has never received the invoices - he called asking for them, will followup on 10/10/19 if pymt is not received
79 | Boston Architectural | Sullivan, Christopher | 19-089-1839 |  | Wayside Youth-Administration Wing Reno | 3575 | 3920 | 765 | 765 | 2019-05-31 | JP 9/18/19 this WIP will be cleared when I do my billing this week | [6 empty] | N |  | N
80 | Boston Architectural | Sullivan, Christopher | 19-089-1839 | 1 |  |  |  |  | 765
81 | Boston Architectural | Sullivan, Christopher | 19-202-1824 |  | UMass - Burbank Pharmacy Upgrade | 42750 | 11250 | 47704 | 9838 | 2019-09-27 | [7 empty] | N |  | N
82 | Boston Architectural | Sullivan, Christopher | 19-202-1824 | 1 |  |  |  |  | 3426
83 | Boston Architectural | Sullivan, Christopher | 19-202-1824 | 2 |  |  |  |  | 6412
84 | Boston Architectural | Young, Paul | 17-324-1818 |  | SHC - Cardio Relocation Study | 106731 | 111379 | 0 | 0 | 2019-04-30 | [7 empty] | N |  | N
85 | Boston Architectural | Young, Paul | 17-324-1818 | 2 |  |  |  |  | -1838
86 | Boston Architectural | Young, Paul | 17-324-1818 | PREDES |  |  |  |  | 1838
Total | [5 empty] | 2354725 | 1786537 | 251102 | 163481 | [6 empty] | 6217 | 52523