## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Bradley, Daniel | 13-142-0275 |  | NYCEDC On Call Facilities Management Con | 861014 | 876510 | 9046 | 7710 | 2019-09-30 | 11-22-19 - Req. 17 through 09-30-19 submitted by 10-28-19. EDC released most of previously held funds related to Carrier Corp. Passport issue. Release of balance of payment of $2,979 is anticipated. Anticipate Balance of WIP about $8K can be billed at years end upon transfer of reimbursable funds to staffing. |  | 3488 |  |  |  |  | N |  | N
2 | CM | Bradley, Daniel | 13-142-0275 | 2 |  |  |  |  | 7710
3 | CM | Bradley, Daniel | 13-142-0275 | [10 empty] | 3488.49 | 00000MUSEO16 | 2019-07-10 | 10/28/2019 DB -Short pay of $5,317.75 received 8/9. $3,504 cut pending staffing approval.10/31/2019 BC - Ambica will reclass misapllied receipt from 13-142-00275.01
4 | CM | Bradley, Daniel | 14-094-0275 |  | NYCEDC Box Street Newtown Barge Parks CM | 2813498 | 2343798 | 57138 | 9278 | 2019-09-30 | 11-22-19: Requisition for October and November to be submitted by 12-15-19. | 66165 | [5 empty] | N |  | N
5 | CM | Bradley, Daniel | 14-094-0275 | BOXST |  |  |  |  | 8068
6 | CM | Bradley, Daniel | 14-094-0275 | NEWTOW |  |  |  |  | 1210
7 | CM | Bradley, Daniel | 15-091-0275 |  | MARSHES Mitigation Banking Pilot CM & In | 1259443 | 983651 | 19733 | 9948 | 2019-08-31 | 11-22-19: Req 13 for july/aug submitted on 09-30-19. September through November req will be submitted by 12-15-19. | [6 empty] | N |  | N
8 | CM | Bradley, Daniel | 15-091-0275 | STAFF |  |  |  |  | 9948
9 | Field-REI | Bradley, Daniel | 11-66-0275 |  | NYCEDC Hudson Park Boulevard and Streets | 4255191 | 4006704 | 9796 | 4388 | 2019-06-30 | 11-22-19: Requistion 48 through 11-30-19 anticipated to be submitted 12-15-19. | [6 empty] | N |  | N
10 | Field-REI | Bradley, Daniel | 11-66-0275 | CONSTR |  |  |  |  | 3380 |  | 8-15-18 Requisition for period ending 6/30/18 was submitted to EDC on 7/13 including $37,390.31 in staffing.
11 | Field-REI | Bradley, Daniel | 11-66-0275 | PHASE2 |  |  |  |  | 1008 |  | 8-15-18 Requisition for period ending 6/30/18 was submitted to EDC on 7/13 including $37,390.31 in staffing.
12 | Field-REI | Bradley, Daniel | 11-66-0275 | [10 empty] | -60 | 40 | 2017-03-08
13 | Field-REI | Bradley, Daniel | 11-66-0275 | [10 empty] | 0.01 | 41 | 2017-07-10 | Requisition for period ending 6/30/18 was submitted to EDC on 7/13 including $37,390.21 in staffing.
14 | Field-REI | Bradley, Daniel | 11-66-0275 | [10 empty] | 0.01 | 44 | 2018-11-06
15 | Field-REI | Bradley, Daniel | 12-100-0275 |  | NYCEDC Highline Section 3 | 1798009 | 1768738 | 0 | 0 | 2019-06-30 | 11-22-19: Submitted requisition for period ending 06-30-19 on 07-10-19. EDC processing Amendment to facilitate payment anticipated 12-31-19. Job is complete. Requested accounting to write off all remaining reimbursables on WIP. Accounting replied:There is still $13K in expenses on the wip that will need to be billed, moved or approved for write off before the project can be set to dormant.I requested accounting to provide receipts for all expenses for my review. Awaiting response. |  | 1783 |  |  |  |  | N |  | N
16 | Field-REI | Bradley, Daniel | 12-100-0275 | [10 empty] | -267.58 | 24 | 2018-06-30
17 | Field-REI | Bradley, Daniel | 12-100-0275 | [10 empty] | 2050.23 | 26 | 2019-07-10
18 | Field-REI | Bradley, Daniel | 19-113-0275.01 |  | NYCEDC - On Call Civil & Res Eng Retaine | 905967 | 0 | 0 | 1274 | 2019-11-30 | 10-22-19: will submit req. through 10-31 by 11-15. | [6 empty] | N |  | N
19 | Field-REI | Bradley, Daniel | 19-113-0275.01 | 1 |  |  |  |  | 1274
Total |  |  |  |  | 95713 | 65196 |  |  | 66165 | 5271