## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Castagna, Joseph | 08-100-0712 |  | PATCHOGUE CDA/RECONSTRUCT STREETS 2008 | 401700 | 240600 | 81126 | 74345 | 2019-01-04 | 12/6/19 Castagna J - no news on approval of additional fee. Joe will contact Village and inquire. Next update will be 12/6/19. Historical Info to remain:11/22/19 Castagna J - proposal ($113,400) submitted to Village on 11/6/19. I discussed status of approval with Mayor on 11/14. Said it was being reviewed for processing. Next update will be 12/6/19. | [6 empty] | N |  | N
2 | Design | Castagna, Joseph | 08-100-0712 | 440 |  |  |  |  | 74345
3 | Design | Castagna, Joseph | 09-78-0666 |  | GCPW/GARVIES PT-HERB HILL DET CSS | 236710 | 206079 | 261501 | 234803 | 2019-09-30 | 12/6/19 - Castagna J - left voicemail message with H2M on 12/4/19 requesting update on status of execution of sub agreement. Emailed GF today to request update. Awaiting response to both. Next update 12/20/19.Historical notes to remain:11/22/19 Castagna J - Disputes with GF resolved. Awaiting execution of sub agreement. Joe C again emailed H2M on 11/15 and left voicemail with PM for status update, but no response. Associate of PM said that he has been out. May be back on 11/26. I asked him to please ask PM to call me with info. Next update will be 12/6/19.10/30/19 Castagna J - Al Bereche has a tentative tel meeting with GF legal to discuss disputes in the agreement language. Joe C emailed H2M legal counsel on 10/29 to request update on status of the agreement execution (H2M PM on vacation until 11/11). Next update will be 11/8/19.10/14/19 - Castagna J - PS&S executed agreement & checklist signed by Mike S on 9/27/19. Revised agreements returned to GF on 9/17/19 and to H2M on 9/18/19. GF COI ok, H2M COI still needs correction. GF has disputed insurance requirement comments by LiRo on 9/30/19. Legal reviewing dispute. Next update will be 10/25/19.9/13/19 - Castagna J -No Cost Supplemental via transfer from three subs to LiRo fee in the amount of $274K pending sub agreement execution and client approval of transfer. PS&S agreement completed. Received comments on sub agreement from H2M and forwarded to Legal on 9/9/19. Waiting for LiRo legal to complete review of red-lined agreement from GF. Upon submission of executed subagreements to Glen Cove, Director of Public Works should be able to approve LiRo Supplemental Agreement within a day or two. Upon approval we will bill open WIP. Next update will be 9/27/19. | [6 empty] | N |  | N
4 | Design | Castagna, Joseph | 09-78-0666 | 801 |  |  |  |  | 234803
5 | Design | Castagna, Joseph | 16-430-0383 |  | SCPW/IMPROVEMENTS TO CR40 | 473538 | 37995 | 24420 | 46955 | 2019-11-22 | 12/6/19 - Castagna J - Invoice for $138,004 was submitted on December 2, 2019. Cover letter explains how PWR are calculated. Joe C will call County next week to inquire on progress of processing the invoice. The overrun of $17,543 is in preliminary survey work that was estimated very low on original Bowne proposal. Most of this work was completed in 2017, prior to the acquisition. Next update will be 12/20/19.12/2/19-Joe Castagna advised that the WIP of $17,543 is an overrun and at Risk. Joe is following up with Eisman to see if there is anything that can be done. | [6 empty] | N |  | Y
6 | Design | Castagna, Joseph | 16-430-0383 | 200 |  |  |  |  | 24014
7 | Design | Castagna, Joseph | 16-430-0383 | 201 |  |  |  |  | 22111
8 | Design | Castagna, Joseph | 16-430-0383 | 203 |  |  |  |  | 1302
9 | Design | Castagna, Joseph | 16-430-0383 | 204 |  |  |  |  | -472
10 | Design | Castagna, Joseph | 17-006-0248 |  | NCDPW Mission 17-Resurfacing various | 130000 | 130000 | 0 | 0 | 2017-10-13 | 12/6/19 Castagna J - received email response from County today that construction has been completed and we can submit for final payment. Next update will be 12/20/19.Historical info to remain:11/22/19 - Castagna J - emailed NCDPW today to request status of construction completion. Will update WIP/AR notes upon reply.10/30/19 - Castagna J - NC responded on 10/22 that there was one more road to be completed and then final construction acceptance County. Once the County has accepted the construction contract, I am told that we will need to resubmit the invoice for $26,000 because it was submitted in 2017 before it should have been. It is now too old and will require resubmission. Next update will be 11/8/19. |  | 26000 |  |  |  |  | N |  | N
11 | Design | Castagna, Joseph | 17-006-0248 | [10 empty] | 26000 | 2 | 2017-12-01 | 11-22-19 - Castagna J - emailed NCDPW today to request status of construction completion. Will update WIP/AR notes upon reply.10-14-19 - Castagna J - NC has replied that Mission 17 is still under construction and that it is anticipated to be completed by the end of this year. 9/27/19 Castagna J - Final invoice for $26,000 confirmed to be at NC, but I was informed that it will need to be resubmitted when construction is completed. NC will notify LiRo when this occurs. Follow up request on status of completion of construction sent 9/27/19. Next update will be November 1st.3.14.19 SantanaL: This payment is the 20% payment and cannot be padi until construction completion or 2 years from the approval of the final LiRo deliverable, which was submitted October 2017.
12 | Design | Castagna, Joseph | 17-117-0248 |  | NCDPW Mission 19, Resurfacing Various Rd | 97500 | 78000 | 1125 | 1125 | 2019-03-01 | 12/6/19 - Castagna J - received response on 11/25/19 that no additional info is required on payment of $39,000. County responded today that construction will not be completed until the spring of 2020. The final bill can be submitted at that point. Next update will be 12/20/19.Historical note to remain:11/22/19 Castagna J - received email from NCDPW requesting additional info, but LiRo received payment of $39,000 on 11/20/19. I emailed NCDPW today requesting clarification. Next update will be 12/6/19.9/13/19 Castagna J - Joe was informed that Claim Number 2 for $39,000 (balance of 80% payment) was processed and signed in June. County will advise where in the payment process it is. Remaining 20% will not be paid until construction is complete Joe confirmed that there is a limit of 2 years to award a construction contract after written acceptance of the design or after final construction to have the final 20% released. Next update will be 9/27/19. | [6 empty] | N |  | N
13 | Design | Castagna, Joseph | 17-117-0248 | PHSE57 |  |  |  |  | 1125
14 | Design | Castagna, Joseph | 18-006-0407 |  | Town of Babylon Geiger Pk Fence Install | 19000 | 13979 | 9193 | 9193 | 2019-03-05 | 12/6/19 - Castagna J - No new direction from Babylon has been received so project is on hold. 12/2/19 Heather and Castagna advised the WIP is not collectable.Historical info to remain:10/11/19 - Castagna J - Babylon has been advised that completion of project is dependent upon results of Babylon's meeting with cell tower owner. New anticipated completion date is now end of October. Digitized map of Geiger Park was submitted. Next update will be 10/25/19. $28K of WIP is at Risk.8/26/19-Ray Ribeiro was advised by Babylon that there was no additional scope from the original contract and requested a full plan of all projects at Geiger Park to determine possible next steps and LiRo's role in the new work.5/23/9 - Castagna J - This project is anticipated to overrun by $15,000 in labor cost. At the time, this project was an enticement to Babylon to award Wyandanch Rising 2 to Bowne. Maximum fee collectible is $19,000. Next update will be 6/7/19. | [6 empty] | N |  | Y
15 | Design | Castagna, Joseph | 18-006-0407 | DESIGN |  |  |  |  | 8945
16 | Design | Castagna, Joseph | 18-006-0407 | SURVEY |  |  |  |  | 248
17 | Design | Castagna, Joseph | 18-158-1891 |  | Town of Hemp DoE-Oceanside Drainage Impr | 262293 | 204041 | 76674 | 68002 | 2019-03-01 | 12/6/19 - Castagna J - Joe met with TOH on 11/25. Additional comments provided. Number of easement maps increased over proposal so Joe in the process of requesting an increase in fee of approximately $20,000. Next update will be 12/20/19.Historical notes to remain:11/22/19 - Castagna J - drafting changes completed. Joe meeting with TOH on 11/25 to go over final plans. Next update will be 12/6/19.11.12.19 SantanaL: Waiting on milestone (next month) to invoice a third of open WIP. Remaining WIP is at risk due to project overrun.11/7/19 _Sonnenberg - Joe met with me to complete a recovery schedule.8/1/19 - Castagna J - Billed by milestone - 60% plans submitted on 5/3/19. Rec'd verbal review comments from Town. Upon acceptance of plans, we will complete 100% design and bill remainder of fee at $34,000. The final design phase is anticipated to overrun the budget line by $80,000 in labor due to complexity of road raising design. | [6 empty] | N |  | Y
18 | Design | Castagna, Joseph | 18-158-1891 | 3 |  |  |  |  | 68002
Total |  |  |  |  | 454039 | 868846 |  |  | 0 | 26000