## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Franco, Frank | 11-68-0533 |  | Hudson River Park Trust Pier 40 Construc | 6953923 | 5659574 | 84742 | 84742 | 2019-07-31 | 11/15/19-Marvin is drafting a law suit to be filed. HRPT is requesting a meeting to discuss un-completed wotk from ITC and their sub (Vitale) that LiRo signed off on as being completed. 3/2019 LT and JM met with HRPT, HRPT will not release any funds for LiRo or subs until the FDNY fire sprinkler tests passes. |  | 84990 |  |  |  |  | N |  | Y
2 | CM | Franco, Frank | 11-68-0533 | A-D |  |  |  |  | 404
3 | CM | Franco, Frank | 11-68-0533 | AC-AF |  |  |  |  | 1009
4 | CM | Franco, Frank | 11-68-0533 | C4813 |  |  |  |  | 13197
5 | CM | Franco, Frank | 11-68-0533 | LC4541 |  |  |  |  | -452
6 | CM | Franco, Frank | 11-68-0533 | LC4542 |  |  |  |  | 92
7 | CM | Franco, Frank | 11-68-0533 | LC4543 |  |  |  |  | 5202
8 | CM | Franco, Frank | 11-68-0533 | LC4547 |  |  |  |  | 74
9 | CM | Franco, Frank | 11-68-0533 | LC4551 |  |  |  |  | 4253
10 | CM | Franco, Frank | 11-68-0533 | LC4559 |  |  |  |  | -4593
11 | CM | Franco, Frank | 11-68-0533 | M-P |  |  |  |  | 2197
12 | CM | Franco, Frank | 11-68-0533 | MOLMEP |  |  |  |  | -1259
13 | CM | Franco, Frank | 11-68-0533 | Q-T |  |  |  |  | 1101
14 | CM | Franco, Frank | 11-68-0533 | UNALL |  |  |  |  | 1492
15 | CM | Franco, Frank | 11-68-0533 | Y-AB |  |  |  |  | 62026
16 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 1500 | 14558 | 2013-10-03
17 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 2765.09 | 114539 | 2013-12-30
18 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 605.75 | 124548 | 2014-01-03
19 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 134.14 | 164550 | 2014-01-24
20 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 4420.32 | 0000021-4548 | 2014-01-27
21 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 2.94 | 0000022-4560 | 2014-01-28
22 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 123.08 | 0000024538R1 | 2013-11-25
23 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 228.8 | 0000027-4543 | 2014-02-19
24 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 360.8 | 0000028-4559 | 2014-02-19
25 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 8.8 | 0000031-4544 | 2014-02-19
26 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 61.61 | 0000032-4560 | 2014-02-25
27 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 39.6 | 0000034-4550 | 2014-03-04
28 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 30.8 | 0000037-4543 | 2014-03-04
29 | CM | Franco, Frank | 11-68-0533 | [10 empty] | -0.1 | 000035LC4542 | 2014-03-25
30 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 123.2 | 000040LC4548 | 2014-03-31
31 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 875.52 | 000041LC4559 | 2014-03-28
32 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 4.5 | 000043LC4555 | 2014-04-08
33 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 5995.56 | 0000LC453962 | 2014-06-04
34 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 8307.7 | 0000LC456053 | 2014-05-23 | Cut - Paid 8/2014 Paul Ersboll is working with them to get these issues resolved
35 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 123.2 | 00044-LC4544 | 2014-04-01
36 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 9.6 | 00LC-4544-92 | 2014-08-28
37 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 480.01 | 00LC4539-193 | 2015-07-02
38 | CM | Franco, Frank | 11-68-0533 | [10 empty] | -154.91 | 00LC4539-229 | 2015-12-14
39 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 21624.78 | 00LC4543-305 | 2016-11-08
40 | CM | Franco, Frank | 11-68-0533 | [10 empty] | -250.8 | 00LC4549-339 | 2017-05-25
41 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 200 | 00LC4551-102 | 2014-09-22
42 | CM | Franco, Frank | 11-68-0533 | [10 empty] | -0.03 | 00LC4555-346 | 2017-08-21
43 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 286.35 | 00LC4559-322 | 2018-01-17
44 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 8812.16 | 00LC4813-347 | 2017-08-21
45 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 12098.46 | 00LC4813-377 | 2018-08-13
46 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 61.07 | 025-4539REV. | 2014-03-14
47 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 6742.06 | 0LC-4813-366 | 2017-12-28
48 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 9248.93 | 0LC-4813-373 | 2018-04-13
49 | CM | Franco, Frank | 11-68-0533 | [10 empty] | 121.14 | 0LC4550-302A | 2016-11-08
50 | CM | Franco, Frank | 11-82-0265 |  | NYCDDC - MCC Theater Fit Outs | 1664503 | 1931698 | 783041 | 780514 | 2018-01-05 | 11/30/19- LB signed the Supplemental for MCC in the amount of $ 660K. Still need ARTNY approved and registered. as of 11/19/19 there is $1.1M in open WIP. | [6 empty] | N |  | Y
51 | CM | Franco, Frank | 11-82-0265 | ARTNY |  |  |  |  | 109306
52 | CM | Franco, Frank | 11-82-0265 | MCC |  |  |  |  | 671207
53 | CM | Franco, Frank | 12-042-0277 |  | NYCHHC On Call Construction Management B | 704544 | 673587 | 0 | 0 | 2019-07-31 |  |  | 15223 |  |  |  |  | N |  | Y
54 | CM | Franco, Frank | 12-042-0277 | [10 empty] | 15223.08 | 00007-TBUILD | 2013-10-11 | 11/30/19-LT reached out to Christine Flaherty for assistance with all open AR, some Env invoices have been paid the remainder are under review with HHC. 6/5/19-Frank Franco is continuing to attempt to get the payment approved with HHC (Iglhaut).
55 | CM | Franco, Frank | 13-064-0113 |  | DASNY Term On-Call CM | 5174507 | 4453184 | 52978 | 32004 | 2019-08-02 | 10/29/2019 Addl Cave Project # 20 $ 6500 , DASNY requeted WO, # 25 8/5-date to be billed this week $ 28K 86K in Expenses Still open on WIP and 1 invoice , AG resubmitting invoice and sending new invoice for WIP Expenses this week | 3103 | 5196 |  |  |  |  | N |  | N
56 | CM | Franco, Frank | 13-064-0113 | 20 |  |  |  |  | 6552
57 | CM | Franco, Frank | 13-064-0113 | 23 |  |  |  |  | 240
58 | CM | Franco, Frank | 13-064-0113 | 24 |  |  |  |  | 2058
59 | CM | Franco, Frank | 13-064-0113 | 25 |  |  |  |  | 22488
60 | CM | Franco, Frank | 13-064-0113 | 31 |  |  |  |  | 665
61 | CM | Franco, Frank | 13-064-0113 | [10 empty] | -28.38 | 01A-34WRIVER | 2018-09-05
62 | CM | Franco, Frank | 13-064-0113 | [10 empty] | 0.01 | 05A-17FNBATH | 2019-04-23
63 | CM | Franco, Frank | 13-064-0113 | [10 empty] | 5224.41 | 1-26HAMBEACH | 2018-01-04 | AG Resubmitting invoice 10/31
64 | CM | Franco, Frank | 13-142-0275.01 |  | NYCEDC St. George Theater Restoration | 367509 | 367525 | 37068 | 18141 | 2019-07-31 | 10/5/2019 FF ADDITIONAL WO IN PLACE ($220K). WE WILL INVOICE THIS WEEK. | 219 | [5 empty] | N |  | N
65 | CM | Franco, Frank | 13-142-0275.01 | CONSTR |  |  |  |  | 18141
66 | CM | Franco, Frank | 14-015-0265.04 |  | NYCDDC Croton Water Treatment Plant | 2684214 | 665091 | 204903 | 99855 | 2019-08-02 | Billed thru 5/24/2019 on 7/30/2019 | 2231 | [5 empty] | N |  | N
67 | CM | Franco, Frank | 14-015-0265.04 | STAFF |  |  |  |  | 99855
68 | CM | Franco, Frank | 17-120-0113.05 |  | DASNY BMCC - Feeder Project | 418024 | 167685 | 1159 | 1159 | 2019-03-29 | 10/1/2019 Awaiting Funding -3/5/19-$30K supplemental pending | [6 empty] | N |  | N
69 | CM | Franco, Frank | 17-120-0113.05 | STAFF |  |  |  |  | 1159
70 | CM | Franco, Frank | 17-120-0113.08 |  | DASNY BMCC - Generator Project | 599392 | 211013 | 337493 | 297202 | 2019-09-30 | 10/3/19 Awaiting Funding $210K supplemental pending sent query today | [6 empty] | N |  | N
71 | CM | Franco, Frank | 17-120-0113.08 | CONSTR |  |  |  |  | 182537
72 | CM | Franco, Frank | 17-120-0113.08 | STAFF |  |  |  |  | 114665
73 | CM | Franco, Frank | 17-120-0113.09 |  | DASNY BMCC - GYM AHU | 419750 | 228855 | 13144 | 13144 | 2019-03-29 | 10/3/19 Awaiting Funding 3/5/19- $20K Supplemental pending Additional amendment sent 4/3/2019 Sent query 10/4 | [6 empty] | N |  | N
74 | CM | Franco, Frank | 17-120-0113.09 | CONSTR |  |  |  |  | 8430
75 | CM | Franco, Frank | 17-120-0113.09 | STAFF |  |  |  |  | 4714
76 | CM | Franco, Frank | 17-120-0113.10 |  | DASNY Minnewaska State Park Phase 1 | 1804604 | 309045 | 286477 | 182931 | 2019-11-22 | 11/5/19: ST: Frank notified DASNY to question status, and, was told - amendment is in process . Currently in Albany contracts for processing.10/29/19 - No change. Frank will follow up to inquire when work order will be approved. | [6 empty] | N |  | N
77 | CM | Franco, Frank | 17-120-0113.10 | PHASE1 |  |  |  |  | 182931
78 | CM | Franco, Frank | 17-120-0113.14 |  | DASNY - BMCC Plaza Restoration | 530300 | 311398 | 184093 | 105047 | 2019-08-02 | 10/4/19 Awaiting Funding sent query today |  | 142571 |  |  |  |  | N |  | N
79 | CM | Franco, Frank | 17-120-0113.14 | 1 |  |  |  |  | 105047
80 | CM | Franco, Frank | 17-120-0113.14 | [10 empty] | 142571.41 | 3 | 2019-08-07
81 | CM | Franco, Frank | 17-120-0113.17 |  | DASNY - York College | 417845 | 0 | 74875 | 26849 |  | Project commenced 9/2019, on tracker as an hour was from May | [6 empty] | N |  | N
82 | CM | Franco, Frank | 17-120-0113.17 | 1 |  |  |  |  | 26849
83 | CM | Franco, Frank | 17-159-0865 |  | NYU Winthrop Hosp - Program Management | 1176778 | 616699 | 0 | 0 | 2019-05-10 |  |  | 44400 |  |  |  |  | N |  | N
84 | CM | Franco, Frank | 17-159-0865 | [10 empty] | 17330.56 | 0017159754-2 | 2018-08-27
85 | CM | Franco, Frank | 17-159-0865 | [10 empty] | 25329.28 | 0017159754-4 | 2018-11-21 | Jesse, director @ NYUW has the current AR log of all liro projects and is working on it he is trying to clear the backlog as soon as possible. the delay in the billing and payments due to the Winthrop transition to NYU financial system since we have now task order signed the billing is processed and getting into the sequence.
86 | CM | Franco, Frank | 17-159-0865 | [10 empty] | 499.92 | 0017159889-2 | 2018-07-02
87 | CM | Franco, Frank | 17-159-0865 | [10 empty] | 0.32 | 0017159910-3 | 2018-09-28 | 3/21/2019 KA Jesse has the current AR log of all liro projects and is working on it he is trying to clear the backlog as soon as possible.
88 | CM | Franco, Frank | 17-159-0865 | [10 empty] | -2166.32 | 0017159WED-3 | 2018-05-11 | H. Travis - spoke with Ambica. We were paid twice on this invoice. Should be returned to client unless we bill again on this phase.
89 | CM | Franco, Frank | 17-159-0865 | [10 empty] | 3406.32 | 17159SUR.002 | 2018-04-05
90 | CM | Franco, Frank | 18-088-0277.01 |  | NYCHHC - Sea View | 8421 | 8421 | 0 | 0 | 2019-02-28 |  |  | 1578 |  |  |  |  | N |  | N
91 | CM | Franco, Frank | 18-088-0277.01 | [10 empty] | -934.38 | 1 | 2018-07-03 | 4/12/19 - J. Gavras corresponded with, Scott Rasnow 4/4/19. Invoices/requisitions got rejected and kicked back to Scott Rasnow for his signature/approval. He sent the signed requisitions back to HHC central office. dealing with Shelley Mathor (senior person having overall responsibility for payments) and Chariss, who “does the payments.” Payment is expected by 4/19.
92 | CM | Franco, Frank | 18-088-0277.01 | [10 empty] | 2512.18 | 2 | 2018-10-29 | 9/25 last contact made by J. Gavras with, Scott Rasnow 4/4/19. Req got rejected sent back forScott's signature/approval. he sent to Shelley Mathor (senior person for payments) and Chariss, who “does the payments.
93 | CM | Franco, Frank | 18-360-0315.03 |  | WSP - RCSP Shoreline | 204707 | 49965 | 0 | 0 | 2019-08-30 | 10/01/19: Inv. 2 submitted to WSP 9/17 - $49,024.39. WIll enter into Vision today. Includes #598 for Baptiste. 9/4/19: INV1 submitted -- $14,369.38 - WSP changed our multiplier to 2.20 and asked us to resubmit Invoices 1 and 2. | 18 | [5 empty] | N |  | N
94 | CM | Franco, Frank | 18-360-0315.04 |  | WSP - RCSP Upper Plaza | 204707 | 166672 | 0 | 0 | 2019-07-19 | 10/1/19 - INV 2 submitted to WSP $109,956.53 on 9/17. WSP has not yet submitted to Parks. Will enter on Vision today. | 260 | [5 empty] | N |  | N
95 | CM | Franco, Frank | 19-034-0269 |  | DHS - CM Svcs Reno Proj at Shelter Site | 2227621 | 47620 | 85494 | 56372 | 2019-08-30 | Billed first invoice on 9/23/2019 $ 47,619.60 | [6 empty] | N |  | N
96 | CM | Franco, Frank | 19-034-0269 | 1 |  |  |  |  | 10886
97 | CM | Franco, Frank | 19-034-0269 | 3 |  |  |  |  | 13865
98 | CM | Franco, Frank | 19-034-0269 | 4 |  |  |  |  | 1210
99 | CM | Franco, Frank | 19-034-0269 | 5 |  |  |  |  | 15889
100 | CM | Franco, Frank | 19-034-0269 | 6 |  |  |  |  | 14522
101 | CM | Franco, Frank | 19-072-0347.01 |  | RIOC - Motorgate Garage | 1327600 | 143630 | 52118 | 9793 | 2019-09-30 | [7 empty] | N |  | N
102 | CM | Franco, Frank | 19-072-0347.01 | 1 |  |  |  |  | 9793
103 | CM | Franco, Frank | 19-072-0347.03 |  | RIOC - Lighthouse Restoration | 0 | 10744 | 6650 | 650 | 2019-09-30 | [7 empty] | N |  | N
104 | CM | Franco, Frank | 19-072-0347.03 | 1 |  |  |  |  | 650
105 | CM | Franco, Frank | 19-072-0347.05 |  | RIOC - Youth Center | 0 | 79588 | 61568 | 14510 | 2019-09-30 | [7 empty] | N |  | N
106 | CM | Franco, Frank | 19-072-0347.05 | 1 |  |  |  |  | 14510
107 | CM | Franco, Frank | 19-072-0347.07 |  | RIOC - AVAC Upgrades | 75000 | 9371 | 12198 | 1535 | 2019-09-30 | [7 empty] | N |  | N
108 | CM | Franco, Frank | 19-072-0347.07 | 2 |  |  |  |  | 1535
109 | CM | Franco, Frank | 19-072-0347.08 |  | RIOC - Sportspark Renovation | 75000 | 45128 | 19160 | 5758 | 2019-09-30 | [7 empty] | N |  | N
110 | CM | Franco, Frank | 19-072-0347.08 | 1 |  |  |  |  | 5758
111 | CM | Franco, Frank | 19-072-0347.09 |  | RIOC - Octagon Field | 75000 | 91414 | 4075 | 820 | 2019-09-30 | [7 empty] | N |  | N
112 | CM | Franco, Frank | 19-072-0347.09 | 2 |  |  |  |  | 235
113 | CM | Franco, Frank | 19-072-0347.09 | 3 |  |  |  |  | 585
114 | CM | Franco, Frank | 19-072-0347.10 |  | RIOC - Small Pox Hospital | 75000 | 14138 | 5288 | 353 | 2019-09-30 | [7 empty] | N |  | N
115 | CM | Franco, Frank | 19-072-0347.10 | 1 |  |  |  |  | 353
116 | CM | Franco, Frank | 19-072-0347.11 |  | RIOC - Octogon Field Phase 2 | 75000 | 19593 | 37765 | 7678 | 2019-09-30 | [7 empty] | N |  | N
117 | CM | Franco, Frank | 19-072-0347.11 | 1 |  |  |  |  | 1528
118 | CM | Franco, Frank | 19-072-0347.11 | 2 |  |  |  |  | 6150
119 | CM | Franco, Frank | 19-072-0347.12 |  | RIOC - Firefighters Field | 75000 | 16558 | 10105 | 3290 | 2019-09-30 | [7 empty] | N |  | N
120 | CM | Franco, Frank | 19-072-0347.12 | 1 |  |  |  |  | 3290
121 | CM | Franco, Frank | 19-072-0347.13 |  | RIOC - Hope Memorial | 75000 | 15125 | 8523 | 353 | 2019-09-30 | [7 empty] | N |  | N
122 | CM | Franco, Frank | 19-072-0347.13 | 1 |  |  |  |  | 353
123 | CM | Franco, Frank | 19-072-0347.14 |  | RIOC - Blackwell House | 75000 | 11040 | 18598 | 2545 | 2019-09-30 | [7 empty] | N |  | N
124 | CM | Franco, Frank | 19-072-0347.14 | 2 |  |  |  |  | 2545
125 | CM | Franco, Frank | 19-072-0347.15 |  | RIOC - SOSP Rip Rap Reventment | 75000 | 29889 | 5758 | 2585 | 2019-09-30 | [7 empty] | N |  | N
126 | CM | Franco, Frank | 19-072-0347.15 | 1 |  |  |  |  | 2585
127 | CM | Franco, Frank | 19-072-0347.16 |  | RIOC - AVAC Maintenance | 75000 | 0 | 2025 | 600 | 2019-10-31 | [7 empty] | N |  | N
128 | CM | Franco, Frank | 19-072-0347.16 | 2 |  |  |  |  | 600
129 | CM | Franco, Frank | 19-243-0031.01 |  | Battery Pk Resiliency- Feasibility Analy | 29496 | 0 | 12180 | 8797 | [8 empty] | N |  | N
130 | CM | Franco, Frank | 19-243-0031.01 | 1 |  |  |  |  | 8797
Total |  |  |  |  | 2401478 | 3514453 |  |  | 5831 | 293958