## PHR WITH WIP & AR
[7 empty] | GIS : WIP and AR Tracking |  |  |  | 2019-12-16 |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Project Name | Contract Amount | LiRo Billed Fee | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | GIS | Annitto, Richard | 17-289-0244 |  | METRO-NORTH/GIS RAILROAD PROPERTY MGMT | 595527 | 581307 | 0 | 0 | 2019-07-12 |  | 1135 | 138 |  |  |  |  | N |  | N
2 | GIS | Annitto, Richard | 17-289-0244 | [10 empty] | 137.5 | 1728911 | 2018-04-18 | 9/9/2019 DFunaro (Prior comments deleted and replaced with this summary). This invoice has been paid; however a small retainage amount will remain until the close of the contract. This retainage must remain open in order to keep the contract open.
3 | GIS | Bailey, Leland | 18-120-1796 |  | Town of Yorktown-Biannual Tax Map Maint | 19000 | 16625 | 1465 | 657 | 2019-09-30 | 9/11/2019 - Same comment applies. Next quarterly invoice will be after 9/30/2019.3/22/19 DFunaro - Invoicing is quarterly. Will be billed after the close of each quarter in 2019. | [6 empty] | N |  | N
4 | GIS | Bailey, Leland | 18-120-1796 | PROJEC |  |  |  |  | 657
5 | GIS | Bailey, Leland | 19-180-1738 |  | Mt Pleasant 2019-2020 Tax Map Maint Svc | 11330 | 0 | 1304 | 620 |  | 10/15/2019 DFunaro - Billed lump sum in 2 halves. 1st half will be billed in January 2020. | [6 empty] | N |  | N
6 | GIS | Bailey, Leland | 19-180-1738 | 1 |  |  |  |  | 620
7 | GIS | Bailey, Leland | 19-187-2255 |  | Rockland County Maint of Digital Tax Map | 114636 | 0 | 30368 | 10187 |  | 12/11/2019 ABonilla: email to PM- 496 hours in WIP-11/12/2019 DFunaro Five year project with start up costs rolled into 1st month billing. Monthly billing - month one will be billed in December. | [6 empty] | N | 2019-01-07 | N
8 | GIS | Bailey, Leland | 19-187-2255 | 1 |  |  |  |  | 4358
9 | GIS | Bailey, Leland | 19-187-2255 | 4 |  |  |  |  | 5830
10 | GIS | de Sciora, Peter | 17-286-1414 |  | SLEEPY HOLLOW/WQIP ROUND 12 FOR SHMC | 198717 | 191465 | 7497 | 7497 | 2019-09-30 | 11/12/2019 DFunaro - Hard copy maps will be delivered in batches. Once all are delivered, the final bill will be issued. Estimated date is by 12/1/19.10/29/19 ABonilla- awaiting to bill client. PM is working on switching payment status from Bowne to LiRo.7/10/2019 PdeSciora - 2nd qaurter invoice in process. 3/26/2019 - PDeSciora - will bill after 1st quarter closes. See previous comments. Old comments pertain to AR.3/20/18 - Jim Hall - Spoke to customer (Anthony V) today - had lost invoice - I re-sent same day.4/9/18 - Jim Hall - Customer (Fiona H) questioned who LiRo was - I explained in an e-mail. She also wrote "Accounts payable has it [the invoice] now and has promised to include it on this next warrant, which I believe is this week." AR is not at risk. |  | 55578 |  |  |  |  | N |  | N
11 | GIS | de Sciora, Peter | 17-286-1414 | 300 |  |  |  |  | 7497
12 | GIS | de Sciora, Peter | 17-286-1414 | [10 empty] | 55577.6 | 1728613 | 2019-07-31 | 11/12/2019 DFunaro - Client contract is with Sidney Bowne and was not assigned for several reasons - primarily because it is grant based and required a licensed survey company which LiRo did not have at the time. Accounting advised on 10/8 that the SBB accounts are closed and the client can no longer issue payment to us via the Gold Coast bank previously used. Notified the client and are awaiting their acceptance on options to pay LiRo either electronically or by check to RLT. Also tied to the delivery of the 1st set of hard copy maps to be delivered.
13 | GIS | de Sciora, Peter | 19-140-0089 |  | City of Yonkers Water Digitization | 225000 | 46733 | 16090 | 11993 | 2019-09-13 | 8/27/2019 DFunaro - Phase 1 is lump sum billed and cannot be invoiced until the work is complete. (Fee is $107k). Work is only about 25% complete. No risk - will be billed when phase is complete. | [6 empty] | N | 2018-07-10 | N
14 | GIS | de Sciora, Peter | 19-140-0089 | 1 |  |  |  |  | 11993
15 | GIS | de Sciora, Peter | 19-218-1891.01 |  | TOH - GIS User Needs Assessment | 11448 | 0 | 653 | 174 | [8 empty] | N |  | N
16 | GIS | de Sciora, Peter | 19-218-1891.01 | 1 |  |  |  |  | 174
17 | GIS | Funaro, Donna | 07-077-0425 |  | OB HSING/IT SUPPORT | 83425 | 60094 | 1612 | 645 | 2019-08-30 | [7 empty] | N |  | N
18 | GIS | Funaro, Donna | 07-077-0425 | 650 |  |  |  |  | 645
19 | GIS | Funaro, Donna | 16-436-0383 |  | SCPW/2016 DRIVE SYSTEM ENHANCEMENTS | 423109 | 276029 | 4007 | 2652 | 2019-09-28 | 9/11/2019 DFunaro - will bill after 3rd quarter closes. 5/14/2019 - Dfunaro - Invoice ready to be posted. Status reports and budget report ready.3/26/2019 DFunaro - will bill after the close of 1st quarter of 2019.2/20/19 - invoice sent 2/12/19 - WIP current2/6/19- New invoice created to include the last sub consultant invoice for 2018. With Accounting awaiting posting - should be posted this week..Status reports and budget are in progress. 1/25/19 - Draft invoice in review. Needed to be revised due to previously unknown rate cap. Waiting on Sub's invoice to include | [6 empty] | N |  | N
20 | GIS | Funaro, Donna | 16-436-0383 | 605.A |  |  |  |  | 2548
21 | GIS | Funaro, Donna | 16-436-0383 | 606 |  |  |  |  | 104
22 | GIS | Funaro, Donna | 19-001-1741 |  | TOB IT 2019 Staffing Svcs - CAPITAL | 375000 | 126312 | 85141 | 13492 | 2019-11-30 | 12/10/2019 ABonilla: Waiting on PM to invoice October and November9/9/2019 DFunaro - awaiting sub invoice to merge into our invoice. Advised sub that without their July invoice, we cannot submit to the Town. They have not submitted it so we can no longer pay their fees. Requested Accounting create both July and August invoices and the sub will have to absorb any fees for these periods. | [6 empty] | N |  | N
23 | GIS | Funaro, Donna | 19-001-1741 | 1 |  |  |  |  | 1869
24 | GIS | Funaro, Donna | 19-001-1741 | 5 |  |  |  |  | 1853
25 | GIS | Funaro, Donna | 19-001-1741 | 9 |  |  |  |  | 865
26 | GIS | Funaro, Donna | 19-001-1741 | 13 |  |  |  |  | 727
27 | GIS | Funaro, Donna | 19-001-1741 | 14 |  |  |  |  | 6899
28 | GIS | Funaro, Donna | 19-001-1741 | 17 |  |  |  |  | 333
29 | GIS | Funaro, Donna | 19-001-1741 | 18 |  |  |  |  | 499
30 | GIS | Funaro, Donna | 19-001-1741 | 19 |  |  |  |  | 449
31 | GIS | Funaro, Donna | 19-062-0911 |  | TOH Sanitation - 2019 CSR & Route Lookup | 33296 | 9880 | 608 | 608 | 2019-05-31 | [7 empty] | N |  | N
32 | GIS | Funaro, Donna | 19-062-0911 | 1 |  |  |  |  | 608
33 | GIS | Mckillen, Timothy | 16-437-1703 |  | MEDFORD FD/DISTRICT MAPPING | 18350 | 18350 | 0 | 0 | 2018-11-23 |  |  | 3350 |  |  |  |  | Y | 2019-07-10 | Y
34 | GIS | Mckillen, Timothy | 16-437-1703 | [10 empty] | 3350 | 1643701 | 2018-11-28 | 11/12/219 DFunaro - Allyson Ford has sent several emails to attorney Brad Pinksy regarding payment. We suggested a conference call to resolve and he has not replied to our request. RA followed up with with Allyson today. Allysone emailed attorney again10/9/19-Allyson spoke to the Medford Atty and he is discussing the letter Rich Annitto sent on 9/5/19-Allyson to follow up.7/9/19-Collection letter sent8/9/2019 DFunaro - Dispatch vendor finally contacted us. However, what they are asking for is outside the scope of our agreement with the Fire District. Preparing response. (PM on vacation until 8/19/19.)
Total | [5 empty] | 2108838 | 1326795 | 148745 | 48526 | [6 empty] | 1135 | 59066