## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Field-REI | Gadbois, Joseph | 16-035-0816 |  | TGI Facilities Mngmt and CM Services | 11717321 | 9377372 | 264904 | 23776 | 2019-12-31 | CM020 8-16-18, Related to air monitoring testing under Chris Zanoni. The proposal for these services were lump sum and they were to be billed as a vendor to LiRo Program & Construct. Mgmt. GI staff did not charge tothis work order.CM022 8-16-18, Related to Bldg. 400 artwork installation. The proposal for these services were lump sum and they were to be billed as a vendor to LiRo Program & Construct. Mgmt. GI staff did not charge to this work.5-6-19, Phase FM001, These individuals on Open WIP should have not billed under this Project Code. They were to bill as a vendor to LiRo and TGI under their own Project Code and invoice us separately. | [6 empty] | N |  | N
2 | Field-REI | Gadbois, Joseph | 16-035-0816 | CM020 |  |  |  |  | 5972
3 | Field-REI | Gadbois, Joseph | 16-035-0816 | CM022 |  |  |  |  | 1048
4 | Field-REI | Gadbois, Joseph | 16-035-0816 | CM026 |  |  |  |  | 17788
5 | Field-REI | Gadbois, Joseph | 16-035-0816 | FM001 |  |  |  |  | -1031
6 | Field-REI | Gadbois, Joseph | 16-035-0816 | [10 empty] | -0.01 | 0OPS-34-JUNE | 2019-07-24
7 | Field-REI | Gadbois, Joseph | 16-035-0816 | [10 empty] | -14999 | CAP-19-MARCH | 2018-04-26 | 9-21-18, Related to B&G Invoice, TGI has paid LiRo for Invoice. Payment to B&G being held until B&G completes work.
Total |  |  |  |  | 264904 | 47553 |  |  | 0 | 0