## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | CM | Gaspari, James | 10-58-515 |  | CUNY - Baruch College - Field Bld | 10351392 | 6151125 | 106760 | 454 | 2019-11-08 | [7 empty] | N |  | N
2 | CM | Gaspari, James | 10-58-515 | CONSTR |  |  |  |  | 454
3 | CM | Gaspari, James | 14-058-0286.05 |  | NYPA Bronx Community College CM Svcs | 1166233 | 745706 | 308374 | 306540 | 2019-07-19 | Balance of Fee projected to be payable December 2019. NYPA made a perliminary offer of $332,367 for project related delays, currently reviewing. | [6 empty] | N |  | N
4 | CM | Gaspari, James | 14-058-0286.05 | STAFF |  |  |  |  | 306540
5 | CM | Gaspari, James | 14-058-0286.14 |  | NYPA Bronx Community College Utility | 2483770 | 982426 | 244204 | 169069 | 2018-12-07 | 10/28/2019 JG Construction at 11% as of 9/2019 | [6 empty] | N |  | N
6 | CM | Gaspari, James | 14-058-0286.14 | 01-AE |  |  |  |  | 10535
7 | CM | Gaspari, James | 14-058-0286.14 | 02-CA |  |  |  |  | 61579
8 | CM | Gaspari, James | 14-058-0286.14 | 03-CM |  |  |  |  | 94027
9 | CM | Gaspari, James | 14-058-0286.14 | 04-ENG |  |  |  |  | 2928 |  | 5/10/2019 J. Gaspari - Next Milestone 25% of Construction. NYPA Phase V milestone is projected for Fall 2019.
10 | CM | Gaspari, James | 15-045-0265 |  | NYCDDC Firehouse Rescue 2 | 1956541 | 1719116 | 668330 | 592104 | 2019-02-15 | 10/24/2019 JG - CO to increase LiRo contract w/EAO 1 Month to Register then submit Task Order for Registration DDC anticipates 1 month until billable. Current WIP exceeds pending staffing amendment. Additional funds required. Amendment request to be prepared. |  | 2423 |  |  |  |  | N |  | N
11 | CM | Gaspari, James | 15-045-0265 | STAFF |  |  |  |  | 592104
12 | CM | Gaspari, James | 15-045-0265 | [10 empty] | 2423.12 | 19 | 2019-04-12 | 10/29/2019 JG Following up
13 | CM | Gaspari, James | 15-056-0265 |  | NYCDDC Gut Rehab of Engine Company 293 | 1045982 | 943683 | 23798 | 23798 | 2019-01-04 | 10/21/2019 JG Follow up with DDC PM no approval waiting for registration. No ETA. 8/2019 DDC processing a No Cost Task Order to reallocate monies from Add'l Serv. to Staffing | [6 empty] | N |  | N
14 | CM | Gaspari, James | 15-056-0265 | CONSTR |  |  |  |  | 23798
15 | CM | Gaspari, James | 15-125-0265 |  | NYCDDC Rehab of Hook & Ladder Company 08 | 1267130 | 1176179 | 228970 | 221821 | 2018-07-06 | 10/24/2019 JG - CO to increase LiRo contract w/EAO 1 Month to Register then submit Task Order for Registration DDC anticipates a month until billable | [6 empty] | N |  | N
16 | CM | Gaspari, James | 15-125-0265 | STAFF |  |  |  |  | 221821
17 | CM | Gaspari, James | 17-044-0265 |  | NYCDDC Engine 23 Multi Component Reno | 540075 | 435796 | 107227 | 104803 | 2019-01-04 | 10/24/2019 JG - CO to increase LiRo contract w/EAO 1 Month to Register then submit Task Order for Registration DDC anticipates 1 month until billable | [6 empty] | N |  | N
18 | CM | Gaspari, James | 17-044-0265 | STAFF |  |  |  |  | 104803
Total |  |  |  |  | 1687663 | 2837178 |  |  | 0 | 2423