## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | MEP | Grigortsevich, Yauheni | 17-127-1570 |  | Hostos CC A/C Unit Replacement | 32400 | 32050 | 2879 | 2287 | 2018-03-16 | 11/22/2019 - awaiting DOB approval of installation for final invoice to be submitted. | [6 empty] | N |  | N
2 | MEP | Grigortsevich, Yauheni | 17-127-1570 | 1 |  |  |  |  | 2287
3 | MEP | Grigortsevich, Yauheni | 17-127-1570 | [10 empty] | -850.46 | 17127.001 | 2018-03-20
4 | MEP | Grigortsevich, Yauheni | 18-151-1876 |  | Blackstone-ES Stuytown CHP & Gas Convers | 893760 | 847875 | 90237 | 41453 | 2019-08-31 | 11/22/19 - EG - invoice to be issued to clear WIP next week. Recovery budget 90% expended. Last C/O work 95% completed. | 21 | [5 empty] | N |  | N
5 | MEP | Grigortsevich, Yauheni | 18-151-1876 | 3 |  |  |  |  | 5049
6 | MEP | Grigortsevich, Yauheni | 18-151-1876 | 4 |  |  |  |  | -59
7 | MEP | Grigortsevich, Yauheni | 18-151-1876 | 5 |  |  |  |  | 995
8 | MEP | Grigortsevich, Yauheni | 18-151-1876 | 6 |  |  |  |  | 35468
9 | MEP | Grigortsevich, Yauheni | 18-312-1650 |  | Stony Brook - Fire Pump Study | 90160 | 49864 | 19239 | 12503 | 2019-09-13 | 11/22/2019 - EG - Bid package completed, invoice submitted to clear WIP. Next invoice expected after Bid award. | [6 empty] | N |  | N
10 | MEP | Grigortsevich, Yauheni | 18-312-1650 | 2 |  |  |  |  | 12503 |  | 12/21/2018 -AT hold until end Feb 2019 full contract value1-23-2019 - AT wip thru 1-18 contract value
11 | MEP | Grigortsevich, Yauheni | 19-151-0865 |  | NYUWH-200 OCR Cooling Tower Chiller Repl | 61025 | 0 | 8606 | 54 | [8 empty] | N |  | N
12 | MEP | Grigortsevich, Yauheni | 19-151-0865 | 1 |  |  |  |  | 54
13 | MEP | Grigortsevich, Yauheni | 19-208-2269 |  | Mt. Kisco HA - Gas Piping Replacement | 42500 | 0 | 18735 | 4854 |  | 11/22/2019 - EG - Design drawings completed. Will generate invoice to clear WIP. Bid process expected to proceed 02/2020 | [6 empty] | N |  | N
14 | MEP | Grigortsevich, Yauheni | 19-208-2269 | 1 |  |  |  |  | 4749
15 | MEP | Grigortsevich, Yauheni | 19-208-2269 | 2 |  |  |  |  | 105
Total |  |  |  |  | 139696 | 122302 |  |  | 21 | 0