## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Architect | Miller, Lee | 19-079-1413 |  | Artimus- 126th St & Park Ave | 27600 | 0 | 13734 | 11162 |  | 12.9.19: New PM assigned to this job. Joe Grant finding out from PM if we can invoice. | [6 empty] | N |  | N
2 | Architect | Miller, Lee | 19-079-1413 | 1 |  |  |  |  | 2230
3 | Architect | Miller, Lee | 19-079-1413 | 2 |  |  |  |  | 8932
4 | VDC | Miller, Lee | 17-001-1413 |  | Artimus - 147-20 94th Avenue, Jamaica | 153333 | 101075 | 863 | 863 | 2018-05-25 | 2019-12-06 - Lee MillerCause of AR delay: Due to the small amount L. Anderssen wanted to combine with other Artimus projects. Will include one invoice for multiple projects.PM Action Plan: Spoke with F. Lim on 2019-12-06 to send invoices out on Tues 12/10. | [6 empty] | N |  | N
5 | VDC | Miller, Lee | 17-001-1413 | 117TH |  |  |  |  | 863
6 | VDC | Miller, Lee | 17-098-1413 |  | Artimus - Jamaica II | 41231 | 38588 | 10630 | 10630 | 2019-03-29 | Same as Project 17-001-14132019-12-06 - Lee MillerCause of AR delay: Due to the small amount L. Anderssen wanted to combine with other Artimus projects. Will include one invoice for multiple projects.PM Action Plan: Spoke with F. Lim on 2019-12-06 to send invoices out on Tues 12/10. | [6 empty] | N |  | N
7 | VDC | Miller, Lee | 17-098-1413 | COORD |  |  |  |  | 9516
8 | VDC | Miller, Lee | 17-098-1413 | IMPLEM |  |  |  |  | 1114
9 | VDC | Miller, Lee | 18-334-2052 |  | DTF - 1921 Atlantic Avenue | 0 | 0 | 7817 | 7817 |  | 2019-12-06 - Lee MillerCause of AR delay: Lapse in request. Invoice to be sent for work up to date on TUes 12/10 | [6 empty] | N |  | N
10 | VDC | Miller, Lee | 18-334-2052 | 1 |  |  |  |  | 7817
11 | VDC | Miller, Lee | 19-114-0816 |  | Trust for Governors Island - VDC | 9328 | 0 | 8381 | 8381 |  | 2019-12-06 - Lee MillerCause of AR delay: The VDC group billed LiRo Program and Construction Management. So basically the VDC group was a vendor for the BIM project on Governors Island. | [6 empty] | N |  | N
12 | VDC | Miller, Lee | 19-114-0816 | 1 |  |  |  |  | 8381
13 | VDC | Miller, Lee | 19-115-2182 |  | Yale Club of NY - VDC | 60300 | 0 | 56366 | 32524 |  | 2019-12-06 - Lee MillerCause of AR delay: Lapse in Request. Invoice will be sent out Tues, 12/10. | [6 empty] | N |  | N
14 | VDC | Miller, Lee | 19-115-2182 | 1 |  |  |  |  | 14162
15 | VDC | Miller, Lee | 19-115-2182 | 2 |  |  |  |  | 10384
16 | VDC | Miller, Lee | 19-115-2182 | 3 |  |  |  |  | 7978
Total |  |  |  |  | 97791 | 142754 |  |  | 0 | 0