## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | MEP | Sajjal, Mirza | 17-301-0090.01 |  | CUNY-DASNY CCNY Spitzer Fab Lab | 27729 | 0 | 21100 | 19426 |  | 11/27/2019 - MSa will prepare invoice after 30% submisson is accepted by DASNY. Expected invoice date+amount 12/31/2019; $27,897 . Expected invoice date 1/31/2020. WIP category: F. | [6 empty] | N |  | N
2 | MEP | Sajjal, Mirza | 17-301-0090.01 | 1 |  |  |  |  | 18549
3 | MEP | Sajjal, Mirza | 17-301-0090.01 | 2 |  |  |  |  | 877
4 | MEP | Sajjal, Mirza | 17-301-0090.02 |  | CUNY-DASNY York College BMS Upgrade-SDC | 165092 | 0 | 10690 | 3787 |  | 11/27/2019 - MSa construction is expected to start 12/2/19; will prepare invoice once more work has been billed to this project. Expected invoice date+ 1/31/2020; TBD. Expected invoice date 1/31/2020. WIP category: G. | [6 empty] | N |  | N
5 | MEP | Sajjal, Mirza | 17-301-0090.02 | 1 |  |  |  |  | 2609
6 | MEP | Sajjal, Mirza | 17-301-0090.02 | 2 |  |  |  |  | 1178
Total |  |  |  |  | 31790 | 46426 |  |  | 0 | 0