## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Env | Salerno, Rosemarie | 18-251-0113 |  | DASNY-IKON 5 BMCC Student Commons Env In | 8000 | 0 | 4376 | 4376 |  | SZ 11/15/19 Per Chris Z. DASNY will not pay us until the design portion is completely done. 90% of design expected to be done in Feb 2020. | [6 empty] | N |  | N
2 | Env | Salerno, Rosemarie | 18-251-0113 | 1 |  |  |  |  | 4376
3 | Env | Salerno, Rosemarie | 18-333-0113 |  | DASNY - CSI Bldg 1M Roof Replacement | 16300 | 13602 | 3482 | 873 | 2019-09-05 | SZ 10/24 phase 1 invoiced 10/21, phase 2 still active project | [6 empty] | N |  | N
4 | Env | Salerno, Rosemarie | 18-333-0113 | 1 |  |  |  |  | 788
5 | Env | Salerno, Rosemarie | 18-333-0113 | 3 |  |  |  |  | 84
6 | Env | Salerno, Rosemarie | 19-033-0816 |  | Trust for GI Bldg 108 IAQ Assessment Ins | 4000 | 4985 | 621 | 621 | 2019-04-13 | 10/24 SZ - active project. | [6 empty] | N |  | N
7 | Env | Salerno, Rosemarie | 19-033-0816 | 1 |  |  |  |  | 621
8 | Env | Salerno, Rosemarie | 19-239-0419 |  | Huntington -Dix Hills Ice Skating Rink | 2000 | 0 | 1627 | 1545 | 2019-11-30 | [7 empty] | N |  | N
9 | Env | Salerno, Rosemarie | 19-239-0419 | 1 |  |  |  |  | 1545
Total |  |  |  |  | 10106 | 14829 |  |  | 0 | 0