## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Sonnenberg, Heather | 18-001-0424 |  | TOBDPW Exp of Ellsworth W. Allen Pk | 964910 | 1239371 | 18555 | 17149 | 2019-05-31 | 12/10/19_Sonnenberg - Mike Smith is negotiations with Commissioner Lenz on approval of final additional services.12/2/19-Mike Smith met with he Town and presented a request for $326K. Commissioner Lenz has pushed back and said he thinks the $ is excessive and does not agree with most of the design costs. Mike is reviewing the costs to present a final draft to the Commissioner. At Risk for $75K. | [6 empty] | N |  | Y
2 | Design | Sonnenberg, Heather | 18-001-0424 | BID |  |  |  |  | 3500
3 | Design | Sonnenberg, Heather | 18-001-0424 | CM/INS |  |  |  |  | 1925
4 | Design | Sonnenberg, Heather | 18-001-0424 | CONAD |  |  |  |  | 3325
5 | Design | Sonnenberg, Heather | 18-001-0424 | DESIGN |  |  |  |  | 8400
6 | Design | Sonnenberg, Heather | 18-357-2045 |  | Acadia - Village Commons Shopping Center | 10700 | 12244 | 0 | 0 | 2019-10-11 | 12/10/19_Sonnenberg - Emailed client today for payment status.11/11/19_Sonnenberg - Client's accounting department sent final approval for payment verification on 11/4/19. Payment should be received within the next few weeks. |  | 10374 |  |  |  |  | N |  | N
7 | Design | Sonnenberg, Heather | 18-357-2045 | [10 empty] | 10373.59 | 1835701 | 2019-08-08
8 | Design | Sonnenberg, Heather | 19-077-0248 |  | Nassau Count DPW Eisenhower Pk Spray Pk | 58000 | 27102 | 6870 | 316 | 2019-09-27 | 12/10/19_Sonnenberg - NCDPW is slower on payment requests.11/11/19_Sonnenberg - emailed additional rates requested by NCDPW to Bob LaBaw. | 5274 | 17731 |  |  |  |  | N |  | N
9 | Design | Sonnenberg, Heather | 19-077-0248 | 2 |  |  |  |  | 316
10 | Design | Sonnenberg, Heather | 19-077-0248 | [10 empty] | 17730.59 | 1907701 | 2019-06-10
11 | Env | Sonnenberg, Heather | 18-169-0493 |  | Town of E. Hampton-Prof Eng Svcs Accabon | 66448 | 0 | 28551 | 23151 | 2019-08-02 | 10/09/19 - Inv#1 had to be voided and in the process of changing and redoing as per client's request . | [6 empty] | N |  | N
12 | Env | Sonnenberg, Heather | 18-169-0493 | 1 |  |  |  |  | 23151
Total |  |  |  |  | 53976 | 81233 |  |  | 5274 | 28105