## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Upadhyay, Anurag | 17-172-0272 |  | NYCDOT Total Design and CSS Cedarview Br | 246307 | 24732 | 122237 | 121848 | 2019-08-31 | 11/30/19-Anurag is working with DOT to utilize the allowances in the contract to bill for some of the overruns. At risk $25,000. 7/20/19-Hutteman-Subhash and Peter Vysotsky were managing the project. Subhash was charging excessive time to the project to get the sub-agreements in place and coordinating with NYCDOT. His rate of over $95/hr could not be supported by the project. I had to hold a significant number of hours on the first invoice to be within the budgeted amounts for the individual tasks. | [6 empty] | N |  | Y
2 | Design | Upadhyay, Anurag | 17-172-0272 | A |  |  |  |  | 22066
3 | Design | Upadhyay, Anurag | 17-172-0272 | B |  |  |  |  | 7836
4 | Design | Upadhyay, Anurag | 17-172-0272 | BUDGET |  |  |  |  | -3132
5 | Design | Upadhyay, Anurag | 17-172-0272 | C |  |  |  |  | 32655
6 | Design | Upadhyay, Anurag | 17-172-0272 | D |  |  |  |  | 5229
7 | Design | Upadhyay, Anurag | 17-172-0272 | E |  |  |  |  | 57194
8 | Design | Upadhyay, Anurag | 19-131-0272 |  | NYCDOT Total Design and CSS for Rehab o | 389839 | 0 | 144120 | 108836 |  | 12/12/19 Anurag Upadhyay: NYCDOT notified that LiRo's SI-2000 packet is approved and we are OK to submit the first invoice upto the amount of $100,000. The invoice is anticipated to be prepared in the month of December and submitted to NYCDOT.11.11.19 SantanaL: Per Anurag U. we are unable to clear WIP of 122,237.46 until January, we may be able to bill $75,000 by end of November if SI2000 submittal is approved.10-22-19 - Anurag Upadhyay : Cause of invoice delay: NYCDOT needs to approve SI-2000 packet of the consultant team (new client process), before invoicing may begin. SI-2000 process is fairly new process of NYCDOT and NYCDOT administration is still in the process of implementing it smoothly. SI-2000 packet submitted to NYCDOT on 8-7-19. Received comments on 8-30-19 on SI-2000 to be incorporated for resubmission on 9-10-19. Again received comments on SI-2000 and Resubmitted SI-2000 packet with second Rivisions on 10-10-19. It is anticipated to be approved by 11-8-19.Date invoice is expected to be issued: 11-15-19Projected amount of next invoice: $77,967 (Till November 1st Work percentage finish (20% of total project)PM Action Plan: Follow up with NYCDOT on approval of SI-2000 and start billing monthly from then onwards, as per the NYCDOT rule of billing only upto the percent complete project. | [6 empty] | N |  | N
9 | Design | Upadhyay, Anurag | 19-131-0272 | 1 |  |  |  |  | 108836
Total |  |  |  |  | 266357 | 461368 |  |  | 0 | 0