## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Field-REI | Wagh, Vikas | 10-55-200 |  | NYCDOT Engineering Service Agreement | 10508413 | 8690747 | 37397 | 11080 | 2019-10-25 | 2/7/19-This a multiple phased project. 09B is the largest amount of unbilled WIP. Supplemental has been approved and registered for 1.1M, Contract Value will be updated and the next invoice will be submitted through 2/15/19. |  | 27075 |  |  |  |  | N |  | N
2 | Field-REI | Wagh, Vikas | 10-55-200 | 149DCK |  |  |  |  | 2389
3 | Field-REI | Wagh, Vikas | 10-55-200 | SDR |  |  |  |  | 1779
4 | Field-REI | Wagh, Vikas | 10-55-200 | TASK03 |  |  |  |  | -130
5 | Field-REI | Wagh, Vikas | 10-55-200 | TASK11 |  |  |  |  | 1084
6 | Field-REI | Wagh, Vikas | 10-55-200 | TASK2 |  |  |  |  | 5958
7 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 1045.01 | 000007TASK04 | 2017-08-07
8 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 2861.73 | 00010TASK09B | 2016-09-21
9 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 14077.39 | 00014TASK09B | 2017-12-28
10 | Field-REI | Wagh, Vikas | 10-55-200 | [10 empty] | 9091.02 | 00017TASK09B | 2019-03-19
11 | Field-REI | Wagh, Vikas | 14-001-0238 |  | MTA B&T CA and Insp. for RK 65 and RK 75 | 11176265 | 10469536 | 63742 | 1543 | 2019-09-27 | 12-4-19, CO submitted early Nov.; approval expected soon. | [6 empty] | N |  | N
12 | Field-REI | Wagh, Vikas | 14-001-0238 | 2.1.A |  |  |  |  | 1543
Total |  |  |  |  | 101139 | 25246 |  |  | 0 | 27075