## PHR WITH WIP & AR
[10 empty] | 2019-12-16 |  |  |  | Open Invoices
Row Count | Department | Project Mgr | Project | Phase | Total WIP as of 12/13/2019 | WIP > 60 as of 12/13/2019 | LiRo Billed Fee | WIP Amount (DLR * Multiplier) | WIP Amount (DLR * Multiplier) | Billed Thru Date | WIP Comments | AR FEE 91-120 | AR FEE Over 120 | Invoice Amount | Invoice Number | Invoice Date | AR Comments | AR Collection Letter Sent | Date Collection Letter Sent | High Risk
1 | Design | Weber, Anthony | 15-095-0418 |  | TOH Newbridge Road Park Shoreline Beach | 47000 | 54591 | 0 | 0 | 2019-09-13 |  |  | 21133 |  |  |  |  | N |  | N
2 | Design | Weber, Anthony | 15-095-0418 | [10 empty] | 16592.69 | 9 | 2019-02-28 | 12/11/19 Anthony Weber: Invoice is pending approval by Town. Followed up with client in Novement on payment status, waiting for their response.7/9/2019 SantanaL: KwaschynM wrote on 7/2/19 " Awaiting response from Town on the status of the AR"6/11/2019 SantanaL: Per PM "According to John L this project was cancelled. The project appears to have re-started" there is a potential Risk on this project in the amount of $17,000.
3 | Design | Weber, Anthony | 15-095-0418 | [10 empty] | 4540.47 | 10 | 2019-07-03 | 12/11/19 Anthony Weber: Invoice is pending approval by Town. Followed up with client in Novement on payment status, waiting for their response.
4 | Design | Weber, Anthony | 17-129-0248 |  | NCDPW Grand Ave Complete Sts Design Svc | 429051 | 343860 | 52607 | 49142 | 2019-09-30 | The final invoice of $49,683.3 can be billed until the final design is accepted. It is expected between 12/15 to 12/31/2019. | [6 empty] | N |  | N
5 | Design | Weber, Anthony | 17-129-0248 | IA |  |  |  |  | 350
6 | Design | Weber, Anthony | 17-129-0248 | IIB |  |  |  |  | 44337
7 | Design | Weber, Anthony | 17-129-0248 | IIE |  |  |  |  | 4456
8 | Design | Weber, Anthony | 17-164-0089 |  | City of Yonkers-Grassy Sprain Dam Ph 3 R | 57580 | 34089 | 7680 | 7437 | 2019-06-07 | 11.11.19 SantanaL: Per AnthonyW. Invoicing by end of month --Open WIP 7,436.687/9/19 SantanaL: KwaschynM wrote on 7/2/19 " Outstanding WIP is being billed $4,123" | [6 empty] | N |  | N
9 | Design | Weber, Anthony | 17-164-0089 | CONINS |  |  |  |  | 6783
10 | Design | Weber, Anthony | 17-164-0089 | CSS |  |  |  |  | 654
11 | Design | Weber, Anthony | 18-340-0270.01 |  | NYCP&R - Little Bush Playground | 47663 | 41681 | 3369 | 3369 | 2019-06-28 | 12/10/19 - Anthony Weber - No changes. See below comment.08/06/19 - Anthony Weber - Per On-Call agreement, Final 10% design fee to be held until completion of Construction. Date Invoice is expected: TBD. Amount of next invoice: $3,966.2707/22/19MessinaS - sent out invoice thru 06/28/1906/04/19 MessinaS-spoke with Anthony Weber, wait till next month.04/22/19- MessinaS - waiting for new phase to be opened and labor transfers.2/25/19 - Anthony Weber - Hold off on invoice until project completion.Date invoice is expected to be issued: 4/23/19Projected amount of next invoice: $39,662.73 | [6 empty] | N |  | N
12 | Design | Weber, Anthony | 18-340-0270.01 | 2 |  |  |  |  | 3369
13 | Design | Weber, Anthony | 18-340-0270.04 |  | NYCP&R - Recon Poor Richard's Playground | 41057 | 33217 | 317 | 317 | 2019-10-18 | 12/10/19 - Anthony Weber - Per On-Call agreement, Final 10% design fee to be held until completion of Construction. Date Invoice is expected: TBD. Amount of next invoice: $3,305.679/20/19 - Anthony Weber - Per On-Call agreement, waiting for completion of next milestone to bill 15% design fee. Date Invoice is expected: TBD. Amount of next invoice: $4,958.5108/06/19 - Anthony Weber - 75% design fee invoice plus allowances is expected to be issued at end of month. Projected amount of invoice: $38,106.3406/04MessinaS- Hold off till June Cycle. | [6 empty] | N |  | N
14 | Design | Weber, Anthony | 18-340-0270.04 | 3 |  |  |  |  | 317
15 | Design | Weber, Anthony | 18-340-0270.05 |  | NYCP&R Recon William E Sheridan Playgrou | 113063 | 0 | 29812 | 18221 |  | 12/10/19 - Anthony Weber - Per On-Call agreement, waiting for completion of next milestone to bill 25% design fee. Date Invoice is expected: TBD. Amount of next invoice: $27,123.17 | [6 empty] | N |  | N
16 | Design | Weber, Anthony | 18-340-0270.05 | 1 |  |  |  |  | 13642
17 | Design | Weber, Anthony | 18-340-0270.05 | 2 |  |  |  |  | 3571
18 | Design | Weber, Anthony | 18-340-0270.05 | 3 |  |  |  |  | 1008
19 | Design | Weber, Anthony | 18-340-0270.06 |  | NYCP&R Recon Synthetic Turf Harlem River | 49711 | 0 | 10266 | 3474 |  | 12/10/19 - Anthony Weber - Next milestone will be TBD. Amount of next invoice: 25% Design Fee | [6 empty] | N |  | N
20 | Design | Weber, Anthony | 18-340-0270.06 | 1 |  |  |  |  | 3474
21 | Design | Weber, Anthony | 18-340-0270.07 |  | NYCP&R Recon Ballfield 3 McCarren Park | 116123 | 0 | 20954 | 3898 |  | 12/10/19 - Anthony Weber - Per On-Call agreement, waiting for completion of next milestone to bill 25% design fee. Date Invoice is expected: TBD. Amount of next invoice: $29,030.63 | [6 empty] | N |  | N
22 | Design | Weber, Anthony | 18-340-0270.07 | 1 |  |  |  |  | 3898
23 | Design | Weber, Anthony | 19-198-0416.01 |  | TOH Parks - Harbor Isle Park Retaining W | 13500 | 0 | 7505 | 7375 |  | 12/10/19 - Anthony Weber - Waiting for completion of Design phase to invoice. Date Invoice is expected: End of Month. Amount of next invoice: $10,870.44 | [6 empty] | N |  | N
24 | Design | Weber, Anthony | 19-198-0416.01 | 1 |  |  |  |  | 1546
25 | Design | Weber, Anthony | 19-198-0416.01 | 2 |  |  |  |  | 5829
26 | Design | Weber, Anthony | 19-250-0248.01 |  | NCDPW-TO5 Long Beach Rd,Oceanside,Draina | 185540 | 0 | 14163 | 325 | [8 empty] | N |  | N
27 | Design | Weber, Anthony | 19-250-0248.01 | 1 |  |  |  |  | 325
Total |  |  |  |  | 146673 | 187117 |  |  | 0 | 21133